## Start Here
APQP Timeline
| Read this first: what the workbook does and how to use it. |  |  |  | mfgcalcs.com
APQP Timeline
Plan an APQP launch in five phases, track progress against plan and see when start of production is really forecast and what a slip would cost.
For: Program and launch managers, APQP leads, quality and manufacturing engineers at automotive, medical device and other suppliers launching new parts.
Version 1.0.0 · updated 15 October 2026
Quick start
| 1. | On Setup, type the program, the plan start, the customer's SOP date and the status date, then the delay-cost figures and your phase and owner lists.
| 2. | On Plan, list every task or deliverable with phase, owner, start, duration, its predecessor and whether it is needed for SOP; copy the approved end dates into Baseline end.
| 3. | Each week, update Complete (%) for each task and move the status date forward.
| 4. | Read Status and Check: Overdue and Below target tasks need action; when Check says a task starts before its predecessor ends, re-plan its start.
| 5. | Open the Dashboard for progress against plan, the phase and task Gantt charts and the forecast SOP slip.
What is in this workbook
|  | Start Here | Read this first: what the workbook does and how to use it.
|  | Setup | Program, plan start, SOP and status dates, progress tolerance, delay-cost figures, and the phase and owner lists.
|  | Plan | One row per task or deliverable: dates, progress and predecessor. Forecast, slip and status are calculated.
|  | Dashboard | Progress against plan, overdue and behind-plan tasks, the phase and task Gantt charts and the forecast SOP.
|  | Method | How every number is calculated, with assumptions, limits and sources.
|  | Verify | Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference.
Colour key
|  | Input | Yellow cells are yours: type a value or pick from the list. Each one says what it accepts when you click it.
|  | Calculated | Blue cells are formulas. They update as you type; overwrite one and that row stops calculating.
|  | Note | Grey boxes are guidance and labelled example data.
|  | Status words | On target / PASS / OK | Near target / Check | Below target / FAIL
Status is always written in words; the colour only repeats it, so the workbook reads the same in black-and-white print and for colour-blind readers.
Self-check and links
|  | Self-check | PASS | 19 of 19 checks pass
The Verify sheet recomputes this workbook's formulas on fixed test inputs and compares them with an independent reference calculation. PASS means every check agreed when you opened the file.
|  | Run it live | Launch Delay Cost Calculator on mfgcalcs.com
|  | Latest version | mfgcalcs.com/templates/apqp-timeline
|  | More free templates | mfgcalcs.com/templates
|  | Version | 1.0.0 (updated 15 October 2026)
About the example data
Every number already in this workbook is example data for Ardent Plastics, a fictional business invented for this template, so the dashboard and charts show something meaningful on day one. It covers the launch of a sensor housing for a vehicle program from 2 March 2026 to SOP on 14 December 2026, status date 9 October 2026. To clear it: on each working sheet, select the example rows of the table, right-click and choose Delete > Table Rows. The formulas stay, and every new row you type below the table picks them up.
Good to know
| • | Sheets Start Here, Dashboard, Method, Verify are protected without a password so formulas and layout are not overwritten by accident. To change them: Review > Unprotect Sheet.
| • | Setup and the working sheets are not protected, so tables grow as you add rows.
| • | Works in Excel 2016 and later, Microsoft 365, LibreOffice 24 and Google Sheets (File > Import). No macros, no external links, no add-ins.
| • | Money is shown in the currency you type on Setup; no exchange rates are applied.
Free from MFG Calcs - keep this credit when you share it.
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Setup
APQP Timeline
| Program, plan start, SOP and status dates, progress tolerance, delay-cost figures, and the phase and owner lists. |  | mfgcalcs.com
Program and dates
| Program or part | SH-40 sensor housing (example)
| Customer | Northline Motors (example)
| Currency label | USD
| Plan start (kickoff) | 2026-03-02
| Start of production (SOP) | 2026-12-14
| Status date (as of) | 2026-10-09
| Due soon window | 14 | days
| Progress tolerance | 10%
Cost of a late SOP (estimates you set)
| Margin lost per week of slip | 18000 | USD per week
| Unrecoverable share | 70%
| Expedite and rework cost | 12000 | USD
Cost figures are your estimates; nothing here assumes an industry figure. The delay cost is a planning estimate: forecast slip in weeks x margin per week x unrecoverable share + expedite cost.
Lists that feed the dropdowns
Edit, add or remove rows; the Plan dropdowns read these lists. The five phases follow the APQP structure (AIAG APQP reference manual); rename them to your own launch process if you use another (for example a medical device design-transfer plan). Keep names unique.
Phases
| Phase | Description
| 1 Plan and define | Voice of the customer, design goals, preliminary BOM, process flow and special characteristics
| 2 Product design | Design FMEA, DFM/DFA, drawings, prototypes and design verification
| 3 Process design | Tooling, process flow, PFMEA, pre-launch control plan, instructions, MSA plan
| 4 Validation | Trials, significant production run, MSA, capability, validation testing, PPAP
| 5 Launch and feedback | Safe launch, reduced variation, lessons learned
Owners
| Owner | Notes
| Program | Program manager
| Product eng. | Product design engineering
| Process eng. | Manufacturing engineering
| Quality | Quality engineering and metrology
| Tooling | Mould design, build and trials
| Production | Moulding and assembly
| Purchasing | Material, components and packaging

## Plan
APQP Timeline
| One row per task or deliverable: dates, progress and predecessor. Forecast, slip and status are calculated. | [19 empty] | mfgcalcs.com
Example data for Ardent Plastics (fictional). Replace it with your own: select the example rows, right-click, Delete > Table Rows. Yellow = you type; blue = calculated; Check names any problem. Dates are calendar days; progress and forecasts are measured to the status date on Setup.
| No. | Phase | Task or deliverable | Owner | Predecessor | Baseline end | Start | Duration (days) | Complete | Needed for SOP | End | Offset (days) | Planned (days) | Done (days) | Remaining (days) | Forecast end | Slip (days) | SOP finish | Status | Check | Notes
| 1 | 1 Plan and define | Kickoff and customer requirements | Program |  | 2026-03-06 | 2026-03-02 | 5 | 100% | Yes | 2026-03-06 | 0 | 5 | 5 | 0 | 2026-03-06 | 0 | 2026-03-06 | Complete | OK
| 2 | 1 Plan and define | Design goals and reliability targets | Product eng. | 1 | 2026-03-18 | 2026-03-09 | 10 | 100% | Yes | 2026-03-18 | 7 | 10 | 10 | 0 | 2026-03-18 | 0 | 2026-03-18 | Complete | OK
| 3 | 1 Plan and define | Preliminary BOM and process flow | Process eng. | 1 | 2026-03-20 | 2026-03-09 | 12 | 100% | Yes | 2026-03-20 | 7 | 12 | 12 | 0 | 2026-03-20 | 0 | 2026-03-20 | Complete | OK
| 4 | 1 Plan and define | Preliminary special characteristics | Quality | 2 | 2026-04-01 | 2026-03-23 | 10 | 100% | Yes | 2026-04-01 | 21 | 10 | 10 | 0 | 2026-04-01 | 0 | 2026-04-01 | Complete | OK
| 5 | 1 Plan and define | Gate 1: program approval | Program | 4 | 2026-04-06 | 2026-04-06 | 1 | 100% | Yes | 2026-04-06 | 35 | 1 | 1 | 0 | 2026-04-06 | 0 | 2026-04-06 | Complete | OK
| 6 | 2 Product design | Design FMEA | Product eng. | 5 | 2026-04-26 | 2026-04-07 | 20 | 100% | Yes | 2026-04-26 | 36 | 20 | 20 | 0 | 2026-04-26 | 0 | 2026-04-26 | Complete | OK
| 7 | 2 Product design | DFM and DFA review | Process eng. | 5 | 2026-04-22 | 2026-04-13 | 10 | 100% | Yes | 2026-04-22 | 42 | 10 | 10 | 0 | 2026-04-22 | 0 | 2026-04-22 | Complete | OK
| 8 | 2 Product design | Drawing and specification release | Product eng. | 6 | 2026-05-21 | 2026-04-27 | 25 | 100% | Yes | 2026-05-21 | 56 | 25 | 25 | 0 | 2026-05-21 | 0 | 2026-05-21 | Complete | OK
| 9 | 2 Product design | Prototype build and control plan | Production | 8 | 2026-06-10 | 2026-05-22 | 20 | 100% | Yes | 2026-06-10 | 81 | 20 | 20 | 0 | 2026-06-10 | 0 | 2026-06-10 | Complete | OK
| 10 | 2 Product design | Design verification testing | Product eng. | 9 | 2026-07-10 | 2026-06-11 | 30 | 100% | Yes | 2026-07-10 | 101 | 30 | 30 | 0 | 2026-07-10 | 0 | 2026-07-10 | Complete | OK
| 11 | 2 Product design | Gate 2: design freeze | Program | 10 | 2026-07-13 | 2026-07-13 | 1 | 100% | Yes | 2026-07-13 | 133 | 1 | 1 | 0 | 2026-07-13 | 0 | 2026-07-13 | Complete | OK
| 12 | 3 Process design | Mould design and build | Tooling | 8 | 2026-08-14 | 2026-05-25 | 103 | 100% | Yes | 2026-09-04 | 84 | 103 | 103 | 0 | 2026-09-04 | 21 | 2026-09-04 | Complete | OK | Steel delivered late; finished 3 weeks behind the baseline
| 13 | 3 Process design | Process flow diagram | Process eng. | 3 | 2026-06-10 | 2026-06-01 | 10 | 100% | Yes | 2026-06-10 | 91 | 10 | 10 | 0 | 2026-06-10 | 0 | 2026-06-10 | Complete | OK
| 14 | 3 Process design | Process FMEA | Quality | 13 | 2026-06-30 | 2026-06-11 | 20 | 100% | Yes | 2026-06-30 | 101 | 20 | 20 | 0 | 2026-06-30 | 0 | 2026-06-30 | Complete | OK
| 15 | 3 Process design | Pre-launch control plan | Quality | 14 | 2026-07-15 | 2026-07-01 | 15 | 100% | Yes | 2026-07-15 | 121 | 15 | 15 | 0 | 2026-07-15 | 0 | 2026-07-15 | Complete | OK
| 16 | 3 Process design | Work and inspection instructions | Production | 15 | 2026-08-04 | 2026-07-16 | 20 | 100% | Yes | 2026-08-04 | 136 | 20 | 20 | 0 | 2026-08-04 | 0 | 2026-08-04 | Complete | OK
| 17 | 3 Process design | MSA plan and gauges | Quality | 15 | 2026-10-01 | 2026-08-03 | 60 | 85% | Yes | 2026-10-01 | 154 | 60 | 51 | 9 | 2026-10-18 | 17 | 2026-10-18 | Overdue | OK | Checking fixture still at the gauge maker
| 18 | 3 Process design | Packaging specification | Purchasing | 13 | 2026-10-20 | 2026-09-21 | 30 | 40% | Yes | 2026-10-20 | 203 | 19 | 12 | 18 | 2026-10-27 | 7 | 2026-10-27 | Below target | OK | Returnable tray waiting for customer approval
| 19 | 3 Process design | Gate 3: process readiness | Program | 16 | 2026-08-24 | 2026-09-07 | 1 | 100% | Yes | 2026-09-07 | 189 | 1 | 1 | 0 | 2026-09-07 | 14 | 2026-09-07 | Complete | OK | Held after the mould build
| 20 | 4 Validation | Mould trials and first shots | Tooling | 12 | 2026-09-11 | 2026-09-08 | 25 | 60% | Yes | 2026-10-02 | 190 | 25 | 15 | 10 | 2026-10-19 | 38 | 2026-10-19 | Overdue | OK | Cavity 2 venting fix after trial 2
| 21 | 4 Validation | Significant production run | Production | 20 | 2026-09-18 | 2026-10-20 | 5 | 0% | Yes | 2026-10-24 | 232 | 0 | 0 | 5 | 2026-10-24 | 36 | 2026-10-24 | OK | OK | Re-planned 31 Aug
| 22 | 4 Validation | MSA studies | Quality | 17 | 2026-10-02 | 2026-10-26 | 15 | 0% | Yes | 2026-11-09 | 238 | 0 | 0 | 15 | 2026-11-09 | 38 | 2026-11-09 | OK | OK | Re-planned 31 Aug
| 23 | 4 Validation | Preliminary process capability | Quality | 21 | 2026-10-02 | 2026-10-26 | 15 | 0% | Yes | 2026-11-09 | 238 | 0 | 0 | 15 | 2026-11-09 | 38 | 2026-11-09 | OK | OK | Re-planned 31 Aug
| 24 | 4 Validation | Production validation testing | Product eng. | 21 | 2026-10-23 | 2026-10-26 | 35 | 0% | Yes | 2026-11-29 | 238 | 0 | 0 | 35 | 2026-11-29 | 37 | 2026-11-29 | OK | OK | Lab slot moved to 26 Oct
| 25 | 4 Validation | PPAP submission and approval | Quality | 24 | 2026-11-20 | 2026-11-30 | 19 | 0% | Yes | 2026-12-18 | 273 | 0 | 0 | 19 | 2026-12-18 | 28 | 2026-12-18 | OK | OK
| 26 | 4 Validation | Gate 4: launch sign-off | Program | 25 | 2026-11-27 | 2026-12-21 | 1 | 0% | Yes | 2026-12-21 | 294 | 0 | 0 | 1 | 2026-12-21 | 24 | 2026-12-21 | OK | OK | Customer told 2 Oct
| 27 | 5 Launch and feedback | Safe-launch containment | Quality | 26 | 2027-02-11 | 2026-12-22 | 60 | 0% | No | 2027-02-19 | 295 | 0 | 0 | 60 | 2027-02-19 | 8 |  | OK | OK | Runs after SOP
| 28 | 5 Launch and feedback | Lessons learned and closure | Program | 27 | 2027-02-25 | 2027-02-22 | 10 | 0% | No | 2027-03-03 | 357 | 0 | 0 | 10 | 2027-03-03 | 6 |  | OK | OK
Formulas:
End = IF(tblTasks[[#This Row],[Task or deliverable]]="","",tblTasks[[#This Row],[Start]]+tblTasks[[#This Row],[Duration (days)]]-1)
SOP finish = IF(tblTasks[[#This Row],[Task or deliverable]]="","",IF(tblTasks[[#This Row],[Needed for SOP]]="Yes",tblTasks[[#This Row],[Forecast end]],""))

## Dashboard
APQP Timeline
| Progress against plan, overdue and behind-plan tasks, the phase and task Gantt charts and the forecast SOP. | [9 empty] | mfgcalcs.com
SH-40 sensor housing (example) for Northline Motors (example). SOP 14 Dec 2026; status date 9 Oct 2026; 28 tasks.
| WORK COMPLETE |  | OVERDUE TASKS |  |  | SOP FORECAST SLIP (WEEKS) |  |  | COST OF THE SLIP (USD, EST.)
| 66.5% |  | 2 |  |  | 1 |  |  | 24600
| 70.92% |  | 0 |  |  | 0 |  |  | Weeks x margin x unrecoverable + expedite
| Below target |  | Above target |  |  | Above target
| FORECAST FINISH, SOP TASKS |  | TASKS LATER THAN BASELINE |  |  | TASKS BELOW TARGET |  |  | DAYS TO SOP
| 2026-12-21 |  | 13 |  |  | 1 |  |  | 66
| Latest forecast end of tasks needed for SOP |  | Forecast end after the baseline end |  |  | Done days trail plan beyond the tolerance |  |  | From the status date
By phase (span from the earliest start to the latest planned end)
| Phase | Tasks | Start | End | Done | Plan | Overdue | Below target | Later than baseline | Offset (days) | Done span (days) | Remaining span (days)
| 1 Plan and define | 5 | 2026-03-02 | 2026-04-06 | 100% | 100% | 0 | 0 | 0 | 0 | 36 | 0
| 2 Product design | 6 | 2026-04-07 | 2026-07-13 | 100% | 100% | 0 | 0 | 0 | 36 | 98 | 0
| 3 Process design | 8 | 2026-05-25 | 2026-10-20 | 89.58% | 95.75% | 1 | 1 | 4 | 84 | 133.4672 | 15.5328
| 4 Validation | 7 | 2026-09-08 | 2026-12-21 | 13.04% | 21.74% | 1 | 0 | 7 | 190 | 13.6957 | 91.3043
| 5 Launch and feedback | 2 | 2026-12-22 | 2027-03-03 | 0% | 0% | 0 | 0 | 2 | 295 | 0 | 72
The phase block shows the 5 phases of the Setup list. If you add phases, extend the block (see Method). The task Gantt plots the example rows' range: if you add tasks below them, extend the chart's data range (right-click the chart, Select Data).
Formulas:
FORECAST FINISH, SOP TASKS = IF(COUNT(tblTasks[SOP finish])=0,"",MAX(tblTasks[SOP finish]))
TASKS LATER THAN BASELINE = IF(B36="","",SUMPRODUCT(MIN(tblTasks[Start]+(tblTasks[Phase]<>B36)*100000)))
End = IF(B36="","",SUMPRODUCT(MAX((tblTasks[Phase]=B36)*(tblTasks[Start]+tblTasks[Duration (days)]-1))))

## Method
APQP Timeline
| How every number is calculated, with assumptions, limits and sources. |  | mfgcalcs.com
What this workbook calculates
Advanced product quality planning (APQP) runs a launch in phases, from planning to validated production. This workbook keeps one row per task or deliverable with a planned start, a duration in calendar days, the share done at the status date, the baseline end the approved plan promised and an optional predecessor. It compares work done with the work the plan expected by the status date, forecasts each task's end from its own progress, measures slip against the baseline and reads the latest forecast end of the tasks needed for SOP against the customer's SOP date. The status date is typed on Setup, so the file never changes by itself.
Calculations
| Quantity | How it is calculated | Units
| End | Start + duration - 1 (calendar days, the start day counts). | date
| Offset | Start - plan start: the invisible part of each Gantt bar. | days
| Planned days | MIN(duration, MAX(0, status date - start + 1)): days that should be done by the status date. | days
| Done, remaining | Done = duration x complete; remaining = duration - done. | days
| Forecast end | Complete: the end. Started: the later of the end and status date + remaining days (rounded up). Not started: the later of the start and the day after the status date, + duration - 1. | date
| Slip | Forecast end - baseline end (- end when no baseline is typed). Positive = later than promised. | days
| Status | Complete; Overdue when the status date is after the end; Below target when done days < planned days - tolerance x duration; Due soon when the end is within the window; otherwise OK. | -
| Predecessor check | Check reads 'Starts before its predecessor ends' when a task not started is planned to start on or before its predecessor's forecast end. | -
| Work complete, plan | Sum of done days / sum of durations; plan = sum of planned days / sum of durations (duration-weighted). | %
| SOP forecast slip | MAX(0, latest forecast end of tasks needed for SOP - SOP date) / 7. | weeks
| Cost of the slip (est.) | Slip weeks x margin per week x unrecoverable share + expedite cost, when the slip is above zero (the Launch Delay Cost calculator's formula). | currency
| Phase start, end, spans | Earliest task start and latest planned end in the phase (SUMPRODUCT with MIN/MAX); the Gantt splits the span by the phase's done share. | date, days
Assumptions
| • | Durations are calendar days. If you plan in working days, convert them or allow for weekends in the duration.
| • | Complete (%) is an honest estimate of work done, not time spent. The forecast assumes the remaining work runs at the planned rate from the day after the status date.
| • | A forecast reads the task's own progress only. A late predecessor does not move its successors by itself: Check flags the successor, and you re-plan its start. (Carrying forecasts down a chain automatically needs a column that reads itself, which Excel reports as a circular reference.)
| • | One finish-to-start predecessor per task. Tasks with several predecessors: name the one expected to finish last.
Limitations
| • | This is a status and forecast tool, not a resource-levelled schedule: it does not know that two tasks share one engineer.
| • | The cost of a slip is an estimate from your own figures, not an accounting number.
| • | The phase block has fixed rows (a warning appears when the list grows); the task Gantt reads the example rows' range and needs extending if you add rows below them.
| • | The phases and task names are a starting point written for this template; the AIAG APQP manual's checklists and forms are not reproduced.
Agreement with the live calculator
The cost tile uses the Launch Delay Cost calculator's formula: total = delay weeks x margin lost per week x unrecoverable share + expedite and rework cost; per week = total / weeks. With the calculator's default example (6 weeks, 18,000 per week, 70%, 12,000) both give 87,600 and 14,600 per week; the template's reference is checked against the engine on every build. One intended difference: the workbook counts the expedite cost only when the forecast slip is above zero, so an on-time plan shows 0.
Open the Launch Delay Cost Calculator
Self-check
The Verify sheet holds fixed test inputs. Its formulas are the same formula text as the working sheets, placed against those inputs, and each result is compared with a value computed independently by the template's Python reference implementation when the file was built. If you edit a formula on a working sheet, the Verify sheet still tests the original formula text, so it will not detect your change.
Sources and standards
| • | AIAG, Advanced Product Quality Planning and Control Plan (APQP), 3rd edition, 2024 (phase structure by reference).
| • | IATF 16949:2016, clause 8.3 Design and development of products and services (referenced, not reproduced).
| • | MFG Calcs Launch Delay Cost calculator: delay weeks x margin per week x unrecoverable share + expedite and rework cost.
Standards are cited by name so you can look them up; no copyrighted standard text or tables are reproduced. Statistical constants used are public.
Version history
| Version | Change | Date
| 1.0.0 | First release. | 15 October 2026
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Verify
APQP Timeline
| Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference. | [19 empty] | mfgcalcs.com
| Self-check status |  | PASS |  | 19 of 19 checks pass
This sheet recomputes the workbook's own formulas on fixed test inputs and compares each result with a value computed independently by the template's Python reference implementation when the file was built. Every row should read PASS. The test inputs are fixed and do not change when you edit Setup or the working sheets.
Checks
| No. | Check |  |  |  | Expected (reference) | Workbook result | Difference | Tolerance | Result
| 1 | Task 2: end |  |  |  | 2026-02-13 | 2026-02-13 | 0 | 1e-09 | PASS
| 2 | Task 2: planned days |  |  |  | 30 | 30 | 0 | 1e-09 | PASS
| 3 | Task 2: forecast end (15 days left after the status date) |  |  |  | 2026-03-07 | 2026-03-07 | 0 | 1e-09 | PASS
| 4 | Task 2: slip against the baseline |  |  |  | 22 | 22 | 0 | 1e-09 | PASS
| 5 | Task 2: status |  |  |  | Overdue | Overdue |  | exact | PASS
| 6 | Task 3: future task, forecast = end |  |  |  | 2026-03-28 | 2026-03-28 | 0 | 1e-09 | PASS
| 7 | Task 4: no baseline, slip against the end |  |  |  | 0 | 0 | 0 | 1e-09 | PASS
| 8 | Task 5: below target |  |  |  | Below target | Below target |  | exact | PASS
| 9 | Task 6: start passed, forecast from the day after the status date |  |  |  | 2026-03-02 | 2026-03-02 | 0 | 1e-09 | PASS
| 10 | Task 6: status |  |  |  | Overdue | Overdue |  | exact | PASS
| 11 | Task 3: Check OK (starts after its predecessor's forecast end) |  |  |  | OK | OK |  | exact | PASS
| 12 | Task 7: Check reports the predecessor |  |  |  | Starts before its predecessor ends | Starts before its predecessor ends |  | exact | PASS
| 13 | Work complete (Dashboard formula) |  |  |  | 27.62% | 27.62% | 0 | 1e-09 | PASS
| 14 | Planned complete (Dashboard formula) |  |  |  | 58.1% | 58.1% | 0 | 1e-09 | PASS
| 15 | Overdue tasks (Dashboard formula) |  |  |  | 2 | 2 | 0 | 1e-09 | PASS
| 16 | Tasks later than baseline (Dashboard formula) |  |  |  | 3 | 3 | 0 | 1e-09 | PASS
| 17 | Forecast finish of SOP tasks (Dashboard formula) |  |  |  | 2026-04-08 | 2026-04-08 | 0 | 1e-09 | PASS
| 18 | SOP slip, weeks |  |  |  | 1 | 1 | 0 | 1e-09 | PASS
| 19 | Cost of the slip: calculator example, 6 weeks |  |  |  | 87600 | 87600 | 0 | 1e-06 | PASS
Fixed test inputs
White cells are fixed test inputs; blue cells are the workbook's formulas evaluated on them.
Parameters
| Plan start |  |  | 2026-01-05
| SOP |  |  | 2026-04-01
| Status date |  |  | 2026-02-20
| Due soon window (days) |  |  | 14
| Progress tolerance |  |  | 10%
| Margin per week (calculator example) |  |  | 18000
| Unrecoverable share |  |  | 70%
| Expedite cost |  |  | 12000
Test table: Phases
| Phase | Description
1 Plan and define
2 Product design
3 Process design
4 Validation
Test table: Tasks
| No. | Phase | Task or deliverable | Owner | Predecessor | Baseline end | Start | Duration (days) | Complete | Needed for SOP | End | Offset (days) | Planned (days) | Done (days) | Remaining (days) | Forecast end | Slip (days) | SOP finish | Status | Check | Notes
| 1 | 1 Plan and define | Task 1 | Quality |  | 2026-01-14 | 2026-01-05 | 10 | 100% | Yes | 2026-01-14 | 0 | 10 | 10 | 0 | 2026-01-14 | 0 | 2026-01-14 | Complete | OK
| 2 | 2 Product design | Task 2 | Quality | 1 | 2026-02-13 | 2026-01-15 | 30 | 50% | Yes | 2026-02-13 | 10 | 30 | 15 | 15 | 2026-03-07 | 22 | 2026-03-07 | Overdue | OK
| 3 | 3 Process design | Task 3 | Quality | 2 | 2026-03-10 | 2026-03-09 | 20 | 0% | Yes | 2026-03-28 | 63 | 0 | 0 | 20 | 2026-03-28 | 18 | 2026-03-28 | OK | OK
| 4 | 4 Validation | Task 4 | Quality | 3 |  | 2026-03-30 | 10 | 0% | Yes | 2026-04-08 | 84 | 0 | 0 | 10 | 2026-04-08 | 0 | 2026-04-08 | OK | OK
| 5 | 2 Product design | Task 5 | Quality |  | 2026-03-01 | 2026-02-10 | 20 | 20% | Yes | 2026-03-01 | 36 | 11 | 4 | 16 | 2026-03-08 | 7 | 2026-03-08 | Below target | OK
| 6 | 2 Product design | Task 6 | Quality |  | 2026-03-04 | 2026-02-10 | 10 | 0% | No | 2026-02-19 | 36 | 10 | 0 | 10 | 2026-03-02 | -2 |  | Overdue | OK
| 7 | 2 Product design | Task 7 | Quality | 2 | 2026-03-06 | 2026-03-02 | 5 | 0% | Yes | 2026-03-06 | 56 | 0 | 0 | 5 | 2026-03-06 | 0 | 2026-03-06 | Due soon | Starts before its predecessor ends
Formulas:
Workbook result = IF(COUNT(tblVerifyTasks[SOP finish])=0,"",MAX(tblVerifyTasks[SOP finish]))
End = IF(tblVerifyTasks[[#This Row],[Task or deliverable]]="","",tblVerifyTasks[[#This Row],[Start]]+tblVerifyTasks[[#This Row],[Duration (days)]]-1)
SOP finish = IF(tblVerifyTasks[[#This Row],[Task or deliverable]]="","",IF(tblVerifyTasks[[#This Row],[Needed for SOP]]="Yes",tblVerifyTasks[[#This Row],[Forecast end]],""))