## Start Here
CAPA and 8D Tracker
| Read this first: what the workbook does and how to use it. |  |  |  | mfgcalcs.com
CAPA and 8D Tracker
Track every corrective and preventive action through the 8D disciplines, see what is overdue and stuck, and measure whether closed CAPAs actually worked.
For: Quality managers, quality and supplier quality engineers, and CAPA owners in plants that answer to ISO 9001, IATF 16949 or ISO 13485.
Version 1.0.0 · updated 15 October 2026
Quick start
| 1. | On Setup, set the status date, your on-time and effectiveness targets, and replace the example priorities (with your containment and closure windows), sources and owners.
| 2. | On CAPA Log, add one row per CAPA: number, opened date, source, type, priority, product, problem statement and owner.
| 3. | As the CAPA moves, type the date each discipline was reached (D3 contained to D8 closed); the stage, due date and status follow.
| 4. | After closure, record the effectiveness check (Effective, Not effective or Pending) and the date it was verified.
| 5. | Open the Dashboard; filter by source or owner for a review meeting. Update the status date on Setup each time you review.
What is in this workbook
|  | Start Here | Read this first: what the workbook does and how to use it.
|  | Setup | Status date, targets, and the priority, source and owner lists that feed the CAPA Log.
|  | CAPA Log | One row per CAPA: the date each 8D discipline was reached, the stage and status, and the effectiveness check.
|  | Dashboard | Open, overdue and stuck CAPAs, on-time closure and effectiveness, for the source and owner you choose.
|  | Method | How every number is calculated, with assumptions, limits and sources.
|  | Verify | Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference.
Colour key
|  | Input | Yellow cells are yours: type a value or pick from the list. Each one says what it accepts when you click it.
|  | Calculated | Blue cells are formulas. They update as you type; overwrite one and that row stops calculating.
|  | Note | Grey boxes are guidance and labelled example data.
|  | Status words | On target / PASS / OK | Near target / Check | Below target / FAIL
Status is always written in words; the colour only repeats it, so the workbook reads the same in black-and-white print and for colour-blind readers.
Self-check and links
|  | Self-check | PASS | 32 of 32 checks pass
The Verify sheet recomputes this workbook's formulas on fixed test inputs and compares them with an independent reference calculation. PASS means every check agreed when you opened the file.
|  | Run it live | CAPA Effectiveness Rate Calculator on mfgcalcs.com
|  | Latest version | mfgcalcs.com/templates/capa-8d-tracker
|  | More free templates | mfgcalcs.com/templates
|  | Version | 1.0.0 (updated 15 October 2026)
About the example data
Every number already in this workbook is example data for Linden Precision Moulding, a fictional business invented for this template, so the dashboard and charts show something meaningful on day one. It holds 44 CAPAs opened between November 2025 and October 2026 at a fictional moulder of medical and automotive parts, with the status date 9 Oct 2026, generated from a fixed seed. To clear it: on each working sheet, select the example rows of the table, right-click and choose Delete > Table Rows. The formulas stay, and every new row you type below the table picks them up.
Good to know
| • | Sheets Start Here, Dashboard, Method, Verify are protected without a password so formulas and layout are not overwritten by accident. To change them: Review > Unprotect Sheet.
| • | Setup and the working sheets are not protected, so tables grow as you add rows.
| • | Works in Excel 2016 and later, Microsoft 365, LibreOffice 24 and Google Sheets (File > Import). No macros, no external links, no add-ins.
| • | Money is shown in the currency you type on Setup; no exchange rates are applied.
Free from MFG Calcs - keep this credit when you share it.
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Setup
CAPA and 8D Tracker
| Status date, targets, and the priority, source and owner lists that feed the CAPA Log. |  |  | mfgcalcs.com
Site, status date and targets
| Site or company | Linden Precision Moulding (example)
| Status as of | 2026-10-09
| 'Due soon' warning | 14 | days
| On-time closure target | 85%
| Effectiveness target | 90%
Targets and the containment and closure windows below are yours to set (or your customer's); nothing in this workbook assumes an industry benchmark. A KPI is 'Near target' within 5% of its target.
Lists that feed the dropdowns
Edit, add or remove rows; the CAPA Log's dropdowns read these lists. Keep names unique. The priority windows set each CAPA's containment check and due date (opened + close within).
Priorities and their time windows (example policy)
| Priority | Contain within (days) | Close within (days) | When to use
| High | 1 | 30 | Safety, regulatory or customer line-stop risk; shipped product affected
| Medium | 3 | 60 | Customer-visible or repeat problem, no safety or regulatory impact
| Low | 7 | 90 | Internal problem or improvement, no product shipped
Sources (where the CAPA came from)
| Source | Description
| Customer complaint | Complaint or rejection from a customer
| Internal NCR | NCR raised in receiving, in process or final inspection
| Audit finding | Internal, customer or registrar audit finding
| Supplier issue | Nonconforming purchased material (SCAR raised)
| Field return | Product returned from use or from the end customer
Owners (D1 team leaders)
| Owner | Role
| A. Mensah | Quality engineer
| R. Kowalski | Process engineer, moulding
| S. Iyer | Supplier quality engineer
| J. Ortega | Assembly supervisor
| M. Chen | Quality manager

## CAPA Log
CAPA and 8D Tracker
| One row per CAPA: the date each 8D discipline was reached, the stage and status, and the effectiveness check. | [24 empty] | mfgcalcs.com
Example data for Linden Precision Moulding (fictional). Replace it with your own: select the example rows, right-click, Delete > Table Rows. Type a date when each discipline is reached; leave later ones blank.
| CAPA no. | Opened | Source | Type | Priority | Product or process | Problem statement | Owner | Contained | Root cause found | Actions implemented | Recurrence prevented | Closed | Effectiveness | Verified | Contain within (days) | Close within (days) | Due | Stage | Days open | Contained on time | Status | On time | In view | Check | Root cause
| CA-25-041 | 2025-11-07 | Customer complaint | Corrective | Medium | Luer connector LC-14 | Short shot on cavity 3 found at customer incoming inspection, 2 of 500 sampled | R. Kowalski | 2025-11-12 | 2025-12-11 | 2026-01-01 | 2026-01-15 | 2026-01-27 | Not effective | 2026-03-19 | 3 | 60 | 2026-01-06 | Closed | 81 | No | Complete | No | 1 | OK | Dryer not cleaned between material changes
| CA-25-042 | 2025-11-17 | Internal NCR | Corrective | High | Luer connector LC-14 | Thread gauge failures on 1 lot after resin batch change | R. Kowalski | 2025-11-17 | 2025-11-28 | 2025-12-16 | 2025-12-28 | 2026-01-03 | Effective | 2026-02-04 | 1 | 30 | 2025-12-17 | Closed | 47 | Yes | Complete | No | 1 | OK | Label print file not locked to the released revision
| CA-25-043 | 2025-11-24 | Supplier issue | Corrective | Medium | Seal carrier SC-55 | Resin certificate missing melt flow result for 1 delivery | S. Iyer | 2025-11-27 | 2025-12-12 | 2025-12-31 | 2026-01-07 | 2026-01-15 | Effective | 2026-02-25 | 3 | 60 | 2026-01-23 | Closed | 52 | Yes | Complete | Yes | 1 | OK | Dryer not cleaned between material changes
| CA-25-044 | 2025-11-26 | Internal NCR | Corrective | Medium | Clip assembly CA-7 | Ultrasonic weld strength below minimum on 1 station | J. Ortega | 2025-11-26 | 2025-12-04 | 2025-12-13 | 2025-12-20 | 2025-12-25 | Effective | 2026-02-08 | 3 | 60 | 2026-01-25 | Closed | 29 | Yes | Complete | Yes | 1 | OK | Dryer not cleaned between material changes
| CA-25-045 | 2025-12-04 | Audit finding | Corrective | Medium | Quality system | Work instruction at assembly station 4 is an old revision | M. Chen | 2025-12-07 | 2025-12-25 | 2026-01-08 | 2026-01-19 | 2026-01-24 | Effective | 2026-03-11 | 3 | 60 | 2026-02-02 | Closed | 51 | Yes | Complete | Yes | 1 | OK | Worn vent on cavity 3 not on the PM list
| CA-25-046 | 2025-12-15 | Supplier issue | Corrective | Medium | Housing H-310 | Colour masterbatch shade outside agreed range | S. Iyer | 2025-12-16 | 2026-01-06 | 2026-01-28 | 2026-02-08 | 2026-02-14 | Effective | 2026-03-31 | 3 | 60 | 2026-02-13 | Closed | 61 | Yes | Complete | No | 1 | OK | Worn vent on cavity 3 not on the PM list
| CA-25-047 | 2025-12-22 | Supplier issue | Corrective | Medium | Seal carrier SC-55 | Resin certificate missing melt flow result for 1 delivery | S. Iyer | 2025-12-22 | 2026-01-12 | 2026-02-12 | 2026-02-23 | 2026-03-01 | Effective | 2026-04-24 | 3 | 60 | 2026-02-20 | Closed | 69 | Yes | Complete | No | 1 | OK | Supplier deburr step skipped under schedule pressure
| CA-25-048 | 2025-12-31 | Supplier issue | Corrective | Medium | Housing H-310 | Colour masterbatch shade outside agreed range | S. Iyer | 2026-01-01 | 2026-01-11 | 2026-01-28 | 2026-02-09 | 2026-02-14 | Effective | 2026-04-01 | 3 | 60 | 2026-03-01 | Closed | 45 | Yes | Complete | Yes | 1 | OK | Dryer not cleaned between material changes
| CA-26-001 | 2026-01-08 | Audit finding | Preventive | Medium | Quality system | Work instruction at assembly station 4 is an old revision | M. Chen | 2026-01-13 | 2026-01-27 | 2026-02-16 | 2026-02-21 | 2026-02-23 | Effective | 2026-04-16 | 3 | 60 | 2026-03-09 | Closed | 46 | No | Complete | Yes | 1 | OK | Cooling water flow restriction on one mould half
| CA-26-002 | 2026-01-12 | Internal NCR | Corrective | Medium | Luer connector LC-14 | Thread gauge failures on 1 lot after resin batch change | R. Kowalski | 2026-01-12 | 2026-02-03 | 2026-02-20 | 2026-03-04 | 2026-03-07 | Effective | 2026-05-02 | 3 | 60 | 2026-03-13 | Closed | 54 | Yes | Complete | Yes | 1 | OK | Training matrix not updated when roles changed
| CA-26-003 | 2026-01-21 | Field return | Corrective | High | Valve body VB-220 | Cracked valve body returned after 6 months in use | A. Mensah | 2026-01-21 | 2026-01-28 | 2026-02-09 | 2026-02-13 | 2026-02-17 | Effective | 2026-04-05 | 1 | 30 | 2026-02-20 | Closed | 27 | Yes | Complete | Yes | 1 | OK | Dryer not cleaned between material changes
| CA-26-004 | 2026-01-30 | Customer complaint | Corrective | Low | Valve body VB-220 | Flash on sealing face caused leak at customer end-of-line test | R. Kowalski | 2026-02-05 | 2026-03-05 | 2026-04-05 | 2026-04-29 | 2026-05-03 | Effective | 2026-06-21 | 7 | 90 | 2026-04-30 | Closed | 93 | Yes | Complete | No | 1 | OK | Feeder sensor bypassed after a jam, no error-proofing
| CA-26-005 | 2026-02-09 | Field return | Corrective | Low | Valve body VB-220 | Cracked valve body returned after 6 months in use | A. Mensah | 2026-02-13 | 2026-03-02 | 2026-03-30 | 2026-04-13 | 2026-04-16 | Effective | 2026-05-30 | 7 | 90 | 2026-05-10 | Closed | 66 | Yes | Complete | Yes | 1 | OK | Supplier deburr step skipped under schedule pressure
| CA-26-006 | 2026-02-12 | Audit finding | Preventive | Low | Quality system | Training record missing for a new press operator | A. Mensah | 2026-02-14 | 2026-03-02 | 2026-03-30 | 2026-04-04 | 2026-04-13 | Not effective | 2026-05-31 | 7 | 90 | 2026-05-13 | Closed | 60 | Yes | Complete | Yes | 1 | OK | Cooling water flow restriction on one mould half
| CA-26-007 | 2026-02-20 | Audit finding | Corrective | Medium | Quality system | Two gauges past calibration due date still in use | A. Mensah | 2026-02-25 | 2026-03-17 | 2026-04-04 | 2026-04-16 | 2026-04-19 | Effective | 2026-06-14 | 3 | 60 | 2026-04-21 | Closed | 58 | No | Complete | Yes | 1 | OK | Hold pressure profile changed without validation
| CA-26-008 | 2026-03-03 | Internal NCR | Corrective | High | Seal carrier SC-55 | Black specks from hopper dryer contamination | R. Kowalski | 2026-03-04 | 2026-03-16 | 2026-04-10 | 2026-04-14 | 2026-04-20 | Not effective | 2026-05-24 | 1 | 30 | 2026-04-02 | Closed | 48 | Yes | Complete | No | 1 | OK | Dryer not cleaned between material changes
| CA-26-009 | 2026-03-09 | Internal NCR | Corrective | Medium | Luer connector LC-14 | Thread gauge failures on 1 lot after resin batch change | A. Mensah | 2026-03-09 | 2026-03-25 | 2026-04-11 | 2026-04-15 | 2026-04-19 | Not effective | 2026-06-04 | 3 | 60 | 2026-05-08 | Closed | 41 | Yes | Complete | Yes | 1 | OK | Cooling water flow restriction on one mould half
| CA-26-010 | 2026-03-16 | Internal NCR | Corrective | High | Valve body VB-220 | Bore diameter drifting toward upper limit after mould maintenance | R. Kowalski | 2026-03-17 | 2026-04-04 | 2026-04-23 | 2026-04-27 | 2026-05-03 | Effective | 2026-06-06 | 1 | 30 | 2026-04-15 | Closed | 48 | Yes | Complete | No | 1 | OK | Feeder sensor bypassed after a jam, no error-proofing
| CA-26-011 | 2026-03-25 | Audit finding | Preventive | Medium | Quality system | Training record missing for a new press operator | A. Mensah | 2026-03-25 | 2026-03-31 | 2026-04-30 | 2026-05-11 | 2026-05-16 | Effective | 2026-07-02 | 3 | 60 | 2026-05-24 | Closed | 52 | Yes | Complete | Yes | 1 | OK | Dryer not cleaned between material changes
| CA-26-012 | 2026-04-02 | Customer complaint | Corrective | Medium | Housing H-310 | Wrong label revision on 3 cartons shipped to customer | A. Mensah | 2026-04-05 | 2026-04-13 | 2026-05-04 | 2026-05-14 | 2026-05-18 | Effective | 2026-07-14 | 3 | 60 | 2026-06-01 | Closed | 46 | Yes | Complete | Yes | 1 | OK | Process window too narrow for resin lot variation
| CA-26-013 | 2026-04-06 | Customer complaint | Corrective | High | Luer connector LC-14 | Short shot on cavity 3 found at customer incoming inspection, 2 of 500 sampled | J. Ortega | 2026-04-06 | 2026-04-10 | 2026-04-15 | 2026-04-18 | 2026-04-20 | Effective | 2026-05-31 | 1 | 30 | 2026-05-06 | Closed | 14 | Yes | Complete | Yes | 1 | OK | Cooling water flow restriction on one mould half
| CA-26-014 | 2026-04-16 | Internal NCR | Corrective | High | Clip assembly CA-7 | Ultrasonic weld strength below minimum on 1 station | R. Kowalski | 2026-04-17 | 2026-05-08 | 2026-05-24 | 2026-06-05 | 2026-06-12 | Not effective | 2026-08-07 | 1 | 30 | 2026-05-16 | Closed | 57 | Yes | Complete | No | 1 | OK | Feeder sensor bypassed after a jam, no error-proofing
| CA-26-015 | 2026-04-22 | Customer complaint | Corrective | Low | Valve body VB-220 | Flash on sealing face caused leak at customer end-of-line test | R. Kowalski | 2026-04-24 | 2026-05-16 | 2026-06-11 | 2026-07-01 | 2026-07-14 | Not effective | 2026-08-15 | 7 | 90 | 2026-07-21 | Closed | 83 | Yes | Complete | Yes | 1 | OK | Process window too narrow for resin lot variation
| CA-26-016 | 2026-04-30 | Customer complaint | Corrective | Medium | Valve body VB-220 | Flash on sealing face caused leak at customer end-of-line test | A. Mensah | 2026-04-30 | 2026-05-09 | 2026-05-29 | 2026-06-08 | 2026-06-11 | Effective | 2026-07-30 | 3 | 60 | 2026-06-29 | Closed | 42 | Yes | Complete | Yes | 1 | OK | Cooling water flow restriction on one mould half
| CA-26-017 | 2026-05-06 | Customer complaint | Corrective | Medium | Seal carrier SC-55 | Sink mark on visible face outside customer appearance limit | A. Mensah | 2026-05-07 | 2026-05-15 | 2026-06-10 | 2026-06-23 | 2026-06-27 | Effective | 2026-08-07 | 3 | 60 | 2026-07-05 | Closed | 52 | Yes | Complete | Yes | 1 | OK | Supplier deburr step skipped under schedule pressure
| CA-26-018 | 2026-05-18 | Audit finding | Preventive | Medium | Quality system | Work instruction at assembly station 4 is an old revision | A. Mensah | 2026-05-21 | 2026-05-30 | 2026-06-13 | 2026-06-21 | 2026-06-23 | Effective | 2026-08-04 | 3 | 60 | 2026-07-17 | Closed | 36 | Yes | Complete | Yes | 1 | OK | Gauge recall list not linked to the calibration system
| CA-26-019 | 2026-05-22 | Customer complaint | Corrective | Low | Housing H-310 | Wrong label revision on 3 cartons shipped to customer | J. Ortega | 2026-05-30 | 2026-06-18 | 2026-07-12 | 2026-07-18 | 2026-07-22 | Effective | 2026-09-19 | 7 | 90 | 2026-08-20 | Closed | 61 | No | Complete | Yes | 1 | OK | Dryer not cleaned between material changes
| CA-26-020 | 2026-06-01 | Internal NCR | Corrective | Low | Housing H-310 | Weld line crack found at final inspection on night shift | A. Mensah | 2026-06-08 | 2026-06-22 | 2026-07-22 | 2026-08-01 | 2026-08-06 | Effective | 2026-09-08 | 7 | 90 | 2026-08-30 | Closed | 66 | Yes | Complete | Yes | 1 | OK | Feeder sensor bypassed after a jam, no error-proofing
| CA-26-021 | 2026-06-08 | Internal NCR | Corrective | Medium | Luer connector LC-14 | Thread gauge failures on 1 lot after resin batch change | J. Ortega | 2026-06-08 | 2026-06-25 | 2026-07-23 | 2026-08-01 | 2026-08-07 | Effective | 2026-09-10 | 3 | 60 | 2026-08-07 | Closed | 60 | Yes | Complete | Yes | 1 | OK | Supplier deburr step skipped under schedule pressure
| CA-26-022 | 2026-06-16 | Internal NCR | Corrective | Low | Clip assembly CA-7 | Ultrasonic weld strength below minimum on 1 station | R. Kowalski | 2026-06-16 | 2026-07-14 | 2026-09-02 | 2026-09-24 |  |  |  | 7 | 90 | 2026-09-14 | D8 Close-out | 115 | Yes | Overdue |  | 1 | OK | Training matrix not updated when roles changed
| CA-26-023 | 2026-06-22 | Supplier issue | Corrective | High | Clip assembly CA-7 | Steel clips delivered with burrs above drawing limit | S. Iyer | 2026-06-24 | 2026-07-06 | 2026-07-12 | 2026-07-19 | 2026-07-21 | Effective | 2026-09-15 | 1 | 30 | 2026-07-22 | Closed | 29 | No | Complete | Yes | 1 | OK | Gauge recall list not linked to the calibration system
| CA-26-024 | 2026-06-29 | Supplier issue | Corrective | Low | Housing H-310 | Colour masterbatch shade outside agreed range | S. Iyer | 2026-06-30 | 2026-07-23 | 2026-08-26 | 2026-09-01 | 2026-09-11 | Pending |  | 7 | 90 | 2026-09-27 | Closed | 74 | Yes | Complete | Yes | 1 | OK | Process window too narrow for resin lot variation
| CA-26-025 | 2026-07-08 | Internal NCR | Corrective | Medium | Clip assembly CA-7 | Ultrasonic weld strength below minimum on 1 station | R. Kowalski | 2026-07-10 | 2026-07-20 | [5 empty] | 3 | 60 | 2026-09-06 | D5-D6 Corrective action | 93 | Yes | Overdue |  | 1 | OK | Training matrix not updated when roles changed
| CA-26-026 | 2026-07-14 | Supplier issue | Corrective | Low | Seal carrier SC-55 | Resin certificate missing melt flow result for 1 delivery | S. Iyer | 2026-07-15 | 2026-07-31 | 2026-08-19 | 2026-08-28 | 2026-09-07 | Pending |  | 7 | 90 | 2026-10-12 | Closed | 55 | Yes | Complete | Yes | 1 | OK | Gauge recall list not linked to the calibration system
| CA-26-027 | 2026-07-22 | Audit finding | Preventive | Low | Quality system | Work instruction at assembly station 4 is an old revision | A. Mensah | 2026-07-22 | 2026-08-03 | 2026-08-15 | 2026-08-24 | 2026-09-01 | Pending |  | 7 | 90 | 2026-10-20 | Closed | 41 | Yes | Complete | Yes | 1 | OK | Dryer not cleaned between material changes
| CA-26-028 | 2026-07-31 | Internal NCR | Corrective | High | Valve body VB-220 | Bore diameter drifting toward upper limit after mould maintenance | R. Kowalski | 2026-07-31 | 2026-08-10 | [5 empty] | 1 | 30 | 2026-08-30 | D5-D6 Corrective action | 70 | Yes | Overdue |  | 1 | OK | Label print file not locked to the released revision
| CA-26-029 | 2026-08-10 | Internal NCR | Corrective | Medium | Clip assembly CA-7 | Ultrasonic weld strength below minimum on 1 station | R. Kowalski | 2026-08-12 | 2026-09-15 | [5 empty] | 3 | 60 | 2026-10-09 | D5-D6 Corrective action | 60 | Yes | Due soon |  | 1 | OK | Hold pressure profile changed without validation
| CA-26-030 | 2026-08-17 | Customer complaint | Corrective | Medium | Seal carrier SC-55 | Sink mark on visible face outside customer appearance limit | R. Kowalski | 2026-08-20 | 2026-09-27 | [5 empty] | 3 | 60 | 2026-10-16 | D5-D6 Corrective action | 53 | Yes | Due soon |  | 1 | OK | Process window too narrow for resin lot variation
| CA-26-031 | 2026-08-27 | Internal NCR | Corrective | Low | Valve body VB-220 | Bore diameter drifting toward upper limit after mould maintenance | R. Kowalski | 2026-08-28 | 2026-09-17 | [5 empty] | 7 | 90 | 2026-11-25 | D5-D6 Corrective action | 43 | Yes | In progress |  | 1 | OK | Training matrix not updated when roles changed
| CA-26-032 | 2026-08-31 | Field return | Corrective | Medium | Valve body VB-220 | Cracked valve body returned after 6 months in use | A. Mensah | 2026-08-31 | 2026-09-11 | [5 empty] | 3 | 60 | 2026-10-30 | D5-D6 Corrective action | 39 | Yes | In progress |  | 1 | OK | Label print file not locked to the released revision
| CA-26-033 | 2026-09-07 | Audit finding | Preventive | Low | Quality system | Control plan reaction plan not followed for an out-of-limit check | M. Chen | 2026-09-14 | 2026-09-26 | [5 empty] | 7 | 90 | 2026-12-06 | D5-D6 Corrective action | 32 | Yes | In progress |  | 1 | OK | Training matrix not updated when roles changed
| CA-26-034 | 2026-09-18 | Internal NCR | Corrective | Low | Clip assembly CA-7 | Ultrasonic weld strength below minimum on 1 station | A. Mensah | 2026-09-24 | 2026-10-06 | [5 empty] | 7 | 90 | 2026-12-17 | D5-D6 Corrective action | 21 | Yes | In progress |  | 1 | OK | Supplier deburr step skipped under schedule pressure
| CA-26-035 | 2026-09-21 | Internal NCR | Corrective | High | Valve body VB-220 | Bore diameter drifting toward upper limit after mould maintenance | R. Kowalski | 2026-09-21 | 2026-09-27 | [5 empty] | 1 | 30 | 2026-10-21 | D5-D6 Corrective action | 18 | Yes | Due soon |  | 1 | OK | Cooling water flow restriction on one mould half
| CA-26-036 | 2026-09-30 | Internal NCR | Corrective | Low | Valve body VB-220 | Bore diameter drifting toward upper limit after mould maintenance | J. Ortega | 2026-10-04 | [6 empty] | 7 | 90 | 2026-12-29 | D4 Root cause | 9 | Yes | In progress |  | 1 | OK
Formulas:
Due = IF(tblCapas[[#This Row],[Opened]]="","",IF(tblCapas[[#This Row],[Close within (days)]]="","",tblCapas[[#This Row],[Opened]]+tblCapas[[#This Row],[Close within (days)]]))

## Dashboard
CAPA and 8D Tracker
| Open, overdue and stuck CAPAs, on-time closure and effectiveness, for the source and owner you choose. | [7 empty] | mfgcalcs.com
| Source |  |  |  |  | Owner
Status as of 9 Oct 2026 (Setup). Rates cover the 12 months from 1 Nov 2025. Showing 44 CAPAs; leave the filters blank to include everything.
| OPEN CAPAS |  | OVERDUE |  |  | CLOSED ON TIME (12 MONTHS) |  | EFFECTIVE AT VERIFICATION (12 MONTHS)
| 11 |  | 3 |  |  | 75.76% |  | 80%
| Opened and not yet closed |  | 0 |  |  | 85% |  | 90%
|  |  | Above target |  |  | Below target |  | Below target
| OPENED (12 MONTHS) |  | AVERAGE DAYS TO CLOSE |  |  | CONTAINED IN TIME |  | OLDEST OPEN CAPA (DAYS)
| 44 |  | 52.8485 |  |  | 88.64% |  | 115
| CAPAs opened in the window |  | CAPAs closed in the window |  |  | Within the priority's window (Setup) |  | Days since opened, at the status date
By owner
| Owner | Open | Overdue | Closed (12 months) | Average days to close | Closed on time
| A. Mensah | 2 | 0 | 12 | 48.9167 | 100%
| R. Kowalski | 7 | 3 | 8 | 63.875 | 25%
| S. Iyer | 0 | 0 | 7 | 55 | 71.43%
| J. Ortega | 1 | 0 | 4 | 41 | 100%
| M. Chen | 1 | 0 | 2 | 48.5 | 100%
Open CAPAs by 8D stage
| Stage (open CAPAs) | Open | Overdue | Due soon | In progress | Average days open
| D3 Containment | 0 | 0 | 0 | 0
| D4 Root cause | 1 | 0 | 0 | 1 | 9
| D5-D6 Corrective action | 9 | 2 | 3 | 4 | 47.6667
| D7 Prevent recurrence | 0 | 0 | 0 | 0
| D8 Close-out | 1 | 1 | 0 | 0 | 115
| By month (the 12 months to the status date) |  |  |  |  | CAPAs opened by source, 12 months (Pareto)
| Month | Opened | Closed | Closed on time | Open at month end | Rank | Source | CAPAs | Share | Cumulative | Helper: Source (list order) | Helper: value (-1 = unused slot) | Helper: rank, ties by list order
| 2025-11-01 | 4 | 0 | 0 | 4 |  |  | CAPAs | % | %
| 2025-12-01 | 4 | 1 | 1 | 7 | 1 | Internal NCR | 17 | 38.64% | 38.64% | Customer complaint | 9 | 2
| 2026-01-01 | 4 | 4 | 2 | 7 | 2 | Customer complaint | 9 | 20.45% | 59.09% | Internal NCR | 17 | 1
| 2026-02-01 | 3 | 4 | 3 | 6 | 3 | Audit finding | 8 | 18.18% | 77.27% | Audit finding | 8 | 3
| 2026-03-01 | 4 | 2 | 1 | 8 | 4 | Supplier issue | 7 | 15.91% | 93.18% | Supplier issue | 7 | 4
| 2026-04-01 | 5 | 6 | 5 | 7 | 5 | Field return | 3 | 6.818% | 100% | Field return | 3 | 5
| 2026-05-01 | 3 | 4 | 2 | 6 |  | Total | 44
| 2026-06-01 | 5 | 4 | 3 | 7
| 2026-07-01 | 4 | 3 | 3 | 8
| 2026-08-01 | 4 | 2 | 2 | 10
| 2026-09-01 | 4 | 3 | 3 | 11
| 2026-10-01 | 0 | 0 | 0 | 11
The Dashboard shows the 5 owners and 5 sources of the Setup lists. If you add more, extend the 'By owner' and Pareto blocks (see Method) or they will not appear here.
Formulas:
OPEN CAPAS = COUNTIFS(tblCapas[In view],1,tblCapas[Opened],">="&EDATE(DATE(YEAR(AsOf),MONTH(AsOf),1),-11),tblCapas[Opened],"<="&AsOf)
Closed (12 months) = IF(B37="","",COUNTIFS(tblCapas[Owner],B37,tblCapas[In view],1,tblCapas[Closed],">="&EDATE(DATE(YEAR(AsOf),MONTH(AsOf),1),-11),tblCapas[Closed],"<="&AsOf))
Closed (12 months) = IF(B60="","",COUNTIFS(tblCapas[In view],1,tblCapas[Closed],">="&B60,tblCapas[Closed],"<="&EOMONTH(B60,0),tblCapas[On time],"Yes"))
Average days to close = IF(B37="","",IF((E37)=0,"",(SUMIFS(tblCapas[Days open],tblCapas[Owner],B37,tblCapas[In view],1,tblCapas[Closed],">="&EDATE(DATE(YEAR(AsOf),MONTH(AsOf),1),-11),tblCapas[Closed],"<="&AsOf))/(E37)))
Average days to close = IF(B60="","",COUNTIFS(tblCapas[In view],1,tblCapas[Opened],"<="&MIN(EOMONTH(B60,0),AsOf))-COUNTIFS(tblCapas[In view],1,tblCapas[Closed],"<="&MIN(EOMONTH(B60,0),AsOf)))
CLOSED ON TIME (12 MONTHS) = IF(B37="","",IF((E37)=0,"",(COUNTIFS(tblCapas[Owner],B37,tblCapas[In view],1,tblCapas[Closed],">="&EDATE(DATE(YEAR(AsOf),MONTH(AsOf),1),-11),tblCapas[Closed],"<="&AsOf,tblCapas[On time],"Yes"))/(E37)))
Open = IF(B60="","",COUNTIFS(tblCapas[In view],1,tblCapas[Opened],">="&B60,tblCapas[Opened],"<="&EOMONTH(B60,0)))
OVERDUE = IF(B60="","",COUNTIFS(tblCapas[In view],1,tblCapas[Closed],">="&B60,tblCapas[Closed],"<="&EOMONTH(B60,0)))
Helper: value (-1 = unused slot) = IF(AO61="",-1,COUNTIFS(tblCapas[In view],1,tblCapas[Opened],">="&EDATE(DATE(YEAR(AsOf),MONTH(AsOf),1),-11),tblCapas[Opened],"<="&AsOf,tblCapas[Source],AO61))

## Method
CAPA and 8D Tracker
| How every number is calculated, with assumptions, limits and sources. |  | mfgcalcs.com
What this workbook calculates
Each CAPA is one row. Instead of typing a stage or a status, you type the date each 8D discipline was reached; the workbook derives the stage, the due date from the priority's window, and the status at the status date on Setup. The effectiveness check after closure is recorded as a result and a date, so the share of CAPAs that actually worked can be measured over a 12-month cohort.
Calculations
| Quantity | How it is calculated | Units
| Due date | Opened + close-within days for the CAPA's priority (Setup). | date
| Stage | The discipline after the latest date filled in: D3 Containment, D4 Root cause, D5-D6 Corrective action, D7 Prevent recurrence, D8 Close-out, or Closed. | -
| Days open | Closed - opened; for an open CAPA, status date - opened. | days
| Contained on time | Yes when contained - opened <= the priority's containment window; No when later, or still not contained past the window. | Yes/No
| Status | Complete when closed; Overdue when due < status date; Due soon when due - status date <= the warning days; else In progress. | -
| On time | For closed CAPAs: Yes when closed <= due date. | Yes/No
| Open CAPAs | Rows opened on or before the status date with no closed date. | CAPAs
| Closed on time | Closed on time / closed, for CAPAs closed in the 12 months to the status date. | %
| Effective at verification | Effective / (effective + not effective), for checks verified in the 12 months. Pending results are left out of both. | %
| Average days to close | Sum of days open / count, over CAPAs closed in the 12 months. | days
| Contained in time | Yes / (Yes + No) of Contained on time, for CAPAs opened in the 12 months. | %
| Open at month end | CAPAs opened by the month end (or status date) minus CAPAs closed by then. | CAPAs
| Pareto | CAPAs opened in the 12 months per source, ranked with COUNTIF (ties keep list order). Hidden helper columns AO:AQ hold the unsorted counts and ranks. | CAPAs, %
Assumptions
| • | Dates are calendar days; weekends and holidays count, as most CAPA procedures measure them.
| • | The 12-month window runs from the first day of the month 11 months before the status date to the status date.
| • | A CAPA's due date is its closure (D8) date. If your procedure sets due dates per discipline, keep them in your 8D report; this register tracks the overall commitment.
| • | Reopened CAPAs: record a 'Not effective' result and open a new CAPA row rather than clearing the old dates.
Limitations
| • | The register does not hold the 8D analysis itself (5 whys, fishbone, verification data); link your report in your own system.
| • | Stage assumes the disciplines are reached in order; the Check column flags dates before the opened date but not every out-of-order pair.
| • | The Dashboard has fixed blocks for 5 owners and 5 sources; longer lists need the blocks extended (a warning appears on the Dashboard).
| • | Effectiveness is only as good as the check you define: state the measure and the waiting period in your procedure.
Agreement with the live calculator
The live CAPA Effectiveness Rate calculator takes a cohort of assessed CAPAs and the number that failed verification: effectiveness = (assessed - failed) / assessed x 100. This workbook's 'Effective at verification' tile is the same ratio with the cohort defined by verification date (the 12 months to the status date), Effective counted as passing and Not effective as failing. The reference implementation is checked against the calculator's engine for its default example (250 assessed, 8 failed: 96.8%) and for the example data on every build. The register, stages, due dates and status are this template's own model.
Open the CAPA Effectiveness Rate Calculator
Self-check
The Verify sheet holds fixed test inputs. Its formulas are the same formula text as the working sheets, placed against those inputs, and each result is compared with a value computed independently by the template's Python reference implementation when the file was built. If you edit a formula on a working sheet, the Verify sheet still tests the original formula text, so it will not detect your change.
Sources and standards
| • | Ford Motor Company, Global 8D (G8D) problem-solving method: the D0-D8 disciplines named here.
| • | AIAG CQI-20, Effective Problem Solving Practitioner's Guide.
| • | ISO 9001:2015, clause 10.2 (nonconformity and corrective action), including reviewing the effectiveness of corrective action; ISO 13485:2016, clauses 8.5.2 and 8.5.3; IATF 16949:2016, clause 10.2.3.
| • | MFG Calcs CAPA Effectiveness Rate calculator (capa-effectiveness-rate): the same effectiveness definition.
Standards are cited by name so you can look them up; no copyrighted standard text or tables are reproduced. Statistical constants used are public.
Version history
| Version | Change | Date
| 1.0.0 | First release. | 15 October 2026
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Verify
CAPA and 8D Tracker
| Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference. | [24 empty] | mfgcalcs.com
| Self-check status |  | PASS |  | 32 of 32 checks pass
This sheet recomputes the workbook's own formulas on fixed test inputs and compares each result with a value computed independently by the template's Python reference implementation when the file was built. Every row should read PASS. The test inputs are fixed and do not change when you edit Setup or the working sheets.
Checks
| No. | Check |  |  |  | Expected (reference) | Workbook result | Difference | Tolerance | Result
| 1 | CAPA 1: due date |  |  |  | 2026-02-04 | 2026-02-04 | 0 | 1e-09 | PASS
| 2 | CAPA 1: stage |  |  |  | Closed | Closed |  | exact | PASS
| 3 | CAPA 1: status |  |  |  | Complete | Complete |  | exact | PASS
| 4 | CAPA 2: due date |  |  |  | 2026-03-04 | 2026-03-04 | 0 | 1e-09 | PASS
| 5 | CAPA 2: stage |  |  |  | Closed | Closed |  | exact | PASS
| 6 | CAPA 2: status |  |  |  | Complete | Complete |  | exact | PASS
| 7 | CAPA 3: due date |  |  |  | 2026-06-01 | 2026-06-01 | 0 | 1e-09 | PASS
| 8 | CAPA 3: stage |  |  |  | D5-D6 Corrective action | D5-D6 Corrective action |  | exact | PASS
| 9 | CAPA 3: status |  |  |  | Overdue | Overdue |  | exact | PASS
| 10 | CAPA 4: due date |  |  |  | 2026-07-08 | 2026-07-08 | 0 | 1e-09 | PASS
| 11 | CAPA 4: stage |  |  |  | D3 Containment | D3 Containment |  | exact | PASS
| 12 | CAPA 4: status |  |  |  | Due soon | Due soon |  | exact | PASS
| 13 | CAPA 5: due date |  |  |  | 2026-08-28 | 2026-08-28 | 0 | 1e-09 | PASS
| 14 | CAPA 5: stage |  |  |  | D3 Containment | D3 Containment |  | exact | PASS
| 15 | CAPA 5: status |  |  |  | In progress | In progress |  | exact | PASS
| 16 | CAPA 6: due date |  |  |  | 2026-05-31 | 2026-05-31 | 0 | 1e-09 | PASS
| 17 | CAPA 6: stage |  |  |  | Closed | Closed |  | exact | PASS
| 18 | CAPA 6: status |  |  |  | Complete | Complete |  | exact | PASS
| 19 | CAPA 1: days open (closed 28 days after opening) |  |  |  | 28 | 28 | 0 | 1e-09 | PASS
| 20 | CAPA 3: days open (open, to the status date) |  |  |  | 89 | 89 | 0 | 1e-09 | PASS
| 21 | CAPA 2: closed on time |  |  |  | No | No |  | exact | PASS
| 22 | CAPA 2: contained on time (3 days against 1) |  |  |  | No | No |  | exact | PASS
| 23 | CAPA 4: contained on time (not contained, window passed) |  |  |  | No | No |  | exact | PASS
| 24 | CAPA 5: contained on time (inside the window: blank) | [6 empty] | exact | PASS
| 25 | CAPA 7: Check reports a date before opened |  |  |  | Date before opened | Date before opened |  | exact | PASS
| 26 | CAPA 8: Check reports a duplicate number |  |  |  | Duplicate CAPA number | Duplicate CAPA number |  | exact | PASS
| 27 | All rows: open CAPAs |  |  |  | 4 | 4 | 0 | 1e-09 | PASS
| 28 | All rows: overdue |  |  |  | 1 | 1 | 0 | 1e-09 | PASS
| 29 | All rows: closed on time |  |  |  | 75% | 75% | 0 | 1e-09 | PASS
| 30 | All rows: effective at verification (1 of 2) |  |  |  | 50% | 50% | 0 | 1e-09 | PASS
| 31 | All rows: average days to close |  |  |  | 37.5 | 37.5 | 0 | 1e-09 | PASS
| 32 | All rows: oldest open CAPA (days) |  |  |  | 89 | 89 | 0 | 1e-09 | PASS
Fixed test inputs
White cells are fixed test inputs; blue cells are the workbook's formulas evaluated on them.
Parameters
| Status as of |  |  | 2026-06-30
| 'Due soon' warning (days) |  |  | 14
Filter: source (blank = all)
Filter: owner (blank = all)
Test table: Capas
| CAPA no. | Opened | Source | Type | Priority | Product or process | Problem statement | Owner | Contained | Root cause found | Actions implemented | Recurrence prevented | Closed | Effectiveness | Verified | Contain within (days) | Close within (days) | Due | Stage | Days open | Contained on time | Status | On time | In view | Check | Root cause
| T-1 | 2026-01-05 | Customer complaint | Corrective | High | Part | Test | Owner A | 2026-01-05 | 2026-01-12 | 2026-01-26 | 2026-01-30 | 2026-02-02 | Effective | 2026-03-16 | 1 | 30 | 2026-02-04 | Closed | 28 | Yes | Complete | Yes | 1 | Duplicate CAPA number
| T-2 | 2026-02-02 | Customer complaint | Corrective | High | Part | Test | Owner A | 2026-02-05 | 2026-02-20 | 2026-03-10 | 2026-03-12 | 2026-03-13 | Not effective | 2026-05-04 | 1 | 30 | 2026-03-04 | Closed | 39 | No | Complete | No | 1 | OK
| T-3 | 2026-04-02 | Customer complaint | Corrective | Medium | Part | Test | Owner A | 2026-04-03 | 2026-04-20 | [5 empty] | 3 | 60 | 2026-06-01 | D5-D6 Corrective action | 89 | Yes | Overdue |  | 1 | OK
| T-4 | 2026-04-09 | Customer complaint | Corrective | Low | Part | Test | Owner A | [7 empty] | 7 | 90 | 2026-07-08 | D3 Containment | 82 | No | Due soon |  | 1 | OK
| T-5 | 2026-06-29 | Customer complaint | Corrective | Medium | Part | Test | Owner A | [7 empty] | 3 | 60 | 2026-08-28 | D3 Containment | 1 |  | In progress |  | 1 | OK
| T-6 | 2026-03-02 | Customer complaint | Corrective | Low | Part | Test | Owner A | 2026-03-06 | 2026-03-20 | 2026-04-15 | 2026-04-30 | 2026-05-06 | Pending |  | 7 | 90 | 2026-05-31 | Closed | 65 | Yes | Complete | Yes | 1 | OK
| T-7 | 2026-05-04 | Customer complaint | Corrective | Low | Part | Test | Owner A | 2026-05-01 |  | 2026-05-20 |  | 2026-05-22 |  |  | 7 | 90 | 2026-08-02 | Closed | 18 | Yes | Complete | Yes | 1 | Date before opened
| T-1 | 2026-05-11 | Customer complaint | Corrective | Low | Part | Test | Owner A | [7 empty] | 7 | 90 | 2026-08-09 | D3 Containment | 50 | No | In progress |  | 1 | Duplicate CAPA number
Formulas:
Due = IF(tblVerifyCapas[[#This Row],[Opened]]="","",IF(tblVerifyCapas[[#This Row],[Close within (days)]]="","",tblVerifyCapas[[#This Row],[Opened]]+tblVerifyCapas[[#This Row],[Close within (days)]]))