## Start Here
Cost Savings Tracker
| Read this first: what the workbook does and how to use it. |  |  |  | mfgcalcs.com
Cost Savings Tracker
Keep every cost-reduction project in one register, log the savings finance validates each month, and see realized savings against plan and the year's target.
For: Plant managers, continuous-improvement and lean leads, purchasing managers and plant controllers who report savings.
Version 1.0.0 · updated 15 October 2026
Quick start
| 1. | On Setup, type your plant name, currency, the first month of the savings year, the month you report through and the year's savings target; adjust the categories and which stages count in the plan.
| 2. | On Project Register, add one row per project: category, hard saving or cost avoidance, stage, start month, annual cost before and after, and any one-time or recurring cost.
| 3. | Each month, add one Savings Log row per project with the saving finance validated.
| 4. | Read the Check columns, then open the Dashboard: realized vs plan, the year-end forecast and the gap to target.
What is in this workbook
|  | Start Here | Read this first: what the workbook does and how to use it.
|  | Setup | Plant, currency, the savings year and its target, and the category and stage lists.
|  | Project Register | One row per cost-reduction project: savings, timing, plan, realized to date and forecast.
|  | Savings Log | One row per project per month: the saving realized and who validated it.
|  | Dashboard | Realized savings against plan and target, the year-end forecast and where the savings come from.
|  | Method | How every number is calculated, with assumptions, limits and sources.
|  | Verify | Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference.
Colour key
|  | Input | Yellow cells are yours: type a value or pick from the list. Each one says what it accepts when you click it.
|  | Calculated | Blue cells are formulas. They update as you type; overwrite one and that row stops calculating.
|  | Note | Grey boxes are guidance and labelled example data.
|  | Status words | On target / PASS / OK | Near target / Check | Below target / FAIL
Status is always written in words; the colour only repeats it, so the workbook reads the same in black-and-white print and for colour-blind readers.
Self-check and links
|  | Self-check | PASS | 21 of 21 checks pass
The Verify sheet recomputes this workbook's formulas on fixed test inputs and compares them with an independent reference calculation. PASS means every check agreed when you opened the file.
|  | Run it live | Manufacturing EBITDA Impact Calculator on mfgcalcs.com
|  | Latest version | mfgcalcs.com/templates/cost-savings-tracker
|  | More free templates | mfgcalcs.com/templates
|  | Version | 1.0.0 (updated 15 October 2026)
About the example data
Every number already in this workbook is example data for Brennan Moulded Products, a fictional business invented for this template, so the dashboard and charts show something meaningful on day one. It tracks fourteen projects in the 2026 savings year, reported through September 2026, with 75 monthly savings entries generated from a fixed seed. To clear it: on each working sheet, select the example rows of the table, right-click and choose Delete > Table Rows. The formulas stay, and every new row you type below the table picks them up.
Good to know
| • | Sheets Start Here, Dashboard, Method, Verify are protected without a password so formulas and layout are not overwritten by accident. To change them: Review > Unprotect Sheet.
| • | Setup and the working sheets are not protected, so tables grow as you add rows.
| • | Works in Excel 2016 and later, Microsoft 365, LibreOffice 24 and Google Sheets (File > Import). No macros, no external links, no add-ins.
| • | Money is shown in the currency you type on Setup; no exchange rates are applied.
Free from MFG Calcs - keep this credit when you share it.
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Setup
Cost Savings Tracker
| Plant, currency, the savings year and its target, and the category and stage lists. |  | mfgcalcs.com
Plant and savings year
| Plant or business | Brennan Moulded Products (example)
| Currency label | EUR
| First month of the savings year | 2026-01-01
| Last month of the savings year | 2026-12-01
| Report through (last closed month) | 2026-09-01
| Months a saving counts from its start | 12 | months
| Hard savings target for the year | 260000 | EUR
| Realization target | 90%
Hard saving: a cost that falls in the accounts (the budget can be cut). Cost avoidance: a cost that would have risen and did not; it is tracked but never counted against the target. The target and realization target are yours; nothing here assumes an industry figure.
Lists that feed the dropdowns
Savings categories
| Category | Examples
| Material and procurement | Price, specification, regrind, yield of material
| Labour and productivity | Automation, SMED, overtime, line balancing
| Scrap and quality | Scrap, rework, sorting, warranty
| Energy | Electricity, gas, compressed air, water
| Maintenance | Spares, contractors, breakdown repair
| Logistics and packaging | Freight, packaging, warehousing
Project stages (you decide which count in the plan)
| Stage | Definition | Counts in plan
| Idea | Proposed; not yet approved or resourced | No
| Approved | Approved with an owner, budget and start month | Yes
| In progress | Being implemented; savings may have started | Yes
| Implemented | Change complete; savings running, not yet confirmed | Yes
| Validated | Finance has confirmed the saving in the accounts | Yes

## Project Register
Cost Savings Tracker
| One row per cost-reduction project: savings, timing, plan, realized to date and forecast. | [22 empty] | mfgcalcs.com
Example data for Brennan Moulded Products (fictional). Replace it with your own: select the example rows, right-click, Delete > Table Rows (and the same on the Savings Log). Annual costs are at the same volume before and after, so the difference is the saving.
[8 empty] | EUR/yr | EUR/yr | EUR | EUR/yr |  | EUR/yr |  |  |  | EUR | EUR | EUR |  |  | EUR
| ID | Project | Owner | Category | Type | Stage | Start month | Baseline cost | Cost after | One-time cost | Recurring cost added | Counts in plan | Net annual savings | Payback (months) | Counted from | Counted to | Plan for the year | Plan to date | Realized to date | Realization | Status | Forecast for the year | Check | Notes
| CS-01 | Regrind ratio up to 15% on PP housings | S. Kelly | Material and procurement | Hard saving | Validated | 2025-10-01 | 410000 | 365000 | 6000 |  | Yes | 45000 | 1.6 | 2026-01-01 | 2026-09-01 | 33750 | 33750 | 33370 | 98.87% | On target | 33370 | OK | Carry-over from 2025: counts until September 2026
| CS-02 | ABS resin price renegotiation | M. Walsh | Material and procurement | Hard saving | Validated | 2026-02-01 | 980000 | 921000 |  |  | Yes | 59000 | 0 | 2026-02-01 | 2026-12-01 | 54083.3333 | 39333.3333 | 39870 | 101.4% | On target | 54620 | OK
| CS-03 | Sprue picker robots, presses 7 to 9 | D. Byrne | Labour and productivity | Hard saving | Implemented | 2026-03-01 | 168000 | 112000 | 48000 | 3000 | Yes | 53000 | 10.8679 | 2026-03-01 | 2026-12-01 | 44166.6667 | 30916.6667 | 24180 | 78.21% | Below target | 37430 | OK
| CS-04 | Compressed air leak programme | P. Nolan | Energy | Hard saving | Validated | 2026-01-01 | 96000 | 78000 | 4500 | 1200 | Yes | 16800 | 3.2143 | 2026-01-01 | 2026-12-01 | 16800 | 12600 | 11300 | 89.68% | Near target | 15500 | OK
| CS-05 | LED high-bay lighting | P. Nolan | Energy | Hard saving | Implemented | 2026-04-01 | 42000 | 24000 | 31000 |  | Yes | 18000 | 20.6667 | 2026-04-01 | 2026-12-01 | 13500 | 9000 | 8990 | 99.89% | On target | 13490 | OK
| CS-06 | Door handle scrap reduction (DOE) | A. Doyle | Scrap and quality | Hard saving | In progress | 2026-05-01 | 88000 | 52000 | 9000 |  | Yes | 36000 | 3 | 2026-05-01 | 2026-12-01 | 24000 | 15000 | 8080 | 53.87% | Below target | 17080 | OK | Behind plan: second DOE run in October
| CS-07 | Hot runner conversion, clip mould | A. Doyle | Scrap and quality | Hard saving | In progress | 2026-07-01 | 64000 | 38000 | 26000 | 1500 | Yes | 24500 | 12.7347 | 2026-07-01 | 2026-12-01 | 12250 | 6125 | 3640 | 59.43% | Below target | 9765 | OK
| CS-08 | Returnable packaging, key customer | M. Walsh | Logistics and packaging | Hard saving | Implemented | 2026-03-01 | 75000 | 51000 | 18000 | 2000 | Yes | 22000 | 9.8182 | 2026-03-01 | 2026-12-01 | 18333.3333 | 12833.3333 | 12100 | 94.29% | On target | 17600 | OK
| CS-09 | Chiller preventive maintenance | P. Nolan | Maintenance | Cost avoidance | Validated | 2026-02-01 | 22000 | 0 |  |  | Yes | 22000 | 0 | 2026-02-01 | 2026-12-01 | 20166.6667 | 14666.6667 | 14690 | 100.2% | On target | 20190 | OK | Avoided chiller compressor rebuild (supplier estimate)
| CS-10 | SMED on the 300 t presses | D. Byrne | Labour and productivity | Hard saving | In progress | 2026-06-01 | 95000 | 63000 | 7500 |  | Yes | 32000 | 2.8125 | 2026-06-01 | 2026-12-01 | 18666.6667 | 10666.6667 | 7570 | 70.97% | Below target | 15570 | OK
| CS-11 | Outbound freight consolidation | M. Walsh | Logistics and packaging | Hard saving | Approved | 2026-10-01 | 130000 | 112000 |  |  | Yes | 18000 | 0 | 2026-10-01 | 2026-12-01 | 4500 | 0 | 0 |  |  | 4500 | OK
| CS-12 | Masterbatch let-down optimisation | S. Kelly | Material and procurement | Hard saving | Approved | 2026-11-01 | 58000 | 47000 | 2500 |  | Yes | 11000 | 2.7273 | 2026-11-01 | 2026-12-01 | 1833.3333 | 0 | 0 |  |  | 1833.3333 | OK
| CS-13 | Heat recovery from compressors | P. Nolan | Energy | Hard saving | Idea | 2026-12-01 | 36000 | 14000 | 40000 |  | No | 22000 | 21.8182 | 2026-12-01 | 2026-12-01 | 0 | 0 | 0 |  |  | 0 | OK | Payback under 2 years; needs capital approval
| CS-14 | Carton price increase avoided | M. Walsh | Logistics and packaging | Cost avoidance | Validated | 2026-01-01 | 64000 | 60000 |  |  | Yes | 4000 | 0 | 2026-01-01 | 2026-12-01 | 4000 | 3000 | 2950 | 98.33% | On target | 3950 | OK | Supplier's announced increase withdrawn after tender
Formulas:
Counted from = IF(tblProjects[[#This Row],[ID]]="","",MAX(DATE(YEAR(tblProjects[[#This Row],[Start month]]),MONTH(tblProjects[[#This Row],[Start month]]),1),FYStart))
Counted to = IF(tblProjects[[#This Row],[ID]]="","",IF(CountMonths>0,MIN(FYEnd,EDATE(DATE(YEAR(tblProjects[[#This Row],[Start month]]),MONTH(tblProjects[[#This Row],[Start month]]),1),CountMonths-1)),FYEnd))
Realized to date = IF(tblProjects[[#This Row],[ID]]="","",SUMIFS(tblSavings[Realized savings],tblSavings[Project ID],tblProjects[[#This Row],[ID]],tblSavings[Month],">="&FYStart,tblSavings[Month],"<"&EDATE(ReportMonth,1)))

## Savings Log
Cost Savings Tracker
| One row per project per month: the saving realized and who validated it. | [7 empty] | mfgcalcs.com
Example data for Brennan Moulded Products (fictional). One row per project per month. A month after the report month on Setup is not counted until you move the report month on.
EUR
| Month | Project ID | Realized savings | Validated by | Project | Category | Type | Check | Notes
| 2026-01-01 | CS-01 | 3820 | Finance (R. Quinn) | Regrind ratio up to 15% on PP housings | Material and procurement | Hard saving | OK
| 2026-01-01 | CS-04 | 1340 | Finance (R. Quinn) | Compressed air leak programme | Energy | Hard saving | OK
| 2026-01-01 | CS-14 | 340 | Finance (R. Quinn) | Carton price increase avoided | Logistics and packaging | Cost avoidance | OK
| 2026-02-01 | CS-01 | 3860 | Finance (R. Quinn) | Regrind ratio up to 15% on PP housings | Material and procurement | Hard saving | OK
| 2026-02-01 | CS-02 | 5270 | Finance (R. Quinn) | ABS resin price renegotiation | Material and procurement | Hard saving | OK
| 2026-02-01 | CS-04 | 1250 | Finance (R. Quinn) | Compressed air leak programme | Energy | Hard saving | OK
| 2026-02-01 | CS-09 | 1800 | Finance (R. Quinn) | Chiller preventive maintenance | Maintenance | Cost avoidance | OK
| 2026-02-01 | CS-14 | 320 | Finance (R. Quinn) | Carton price increase avoided | Logistics and packaging | Cost avoidance | OK
| 2026-03-01 | CS-01 | 3870 | Finance (R. Quinn) | Regrind ratio up to 15% on PP housings | Material and procurement | Hard saving | OK
| 2026-03-01 | CS-02 | 4870 | Finance (R. Quinn) | ABS resin price renegotiation | Material and procurement | Hard saving | OK
| 2026-03-01 | CS-03 | 2350 | Finance (R. Quinn) | Sprue picker robots, presses 7 to 9 | Labour and productivity | Hard saving | OK
| 2026-03-01 | CS-04 | 1220 | Finance (R. Quinn) | Compressed air leak programme | Energy | Hard saving | OK
| 2026-03-01 | CS-08 | 1780 | Finance (R. Quinn) | Returnable packaging, key customer | Logistics and packaging | Hard saving | OK
| 2026-03-01 | CS-09 | 1750 | Finance (R. Quinn) | Chiller preventive maintenance | Maintenance | Cost avoidance | OK
| 2026-03-01 | CS-14 | 340 | Finance (R. Quinn) | Carton price increase avoided | Logistics and packaging | Cost avoidance | OK
| 2026-04-01 | CS-01 | 3540 | Finance (R. Quinn) | Regrind ratio up to 15% on PP housings | Material and procurement | Hard saving | OK
| 2026-04-01 | CS-02 | 4800 | Finance (R. Quinn) | ABS resin price renegotiation | Material and procurement | Hard saving | OK
| 2026-04-01 | CS-03 | 3030 | Finance (R. Quinn) | Sprue picker robots, presses 7 to 9 | Labour and productivity | Hard saving | OK
| 2026-04-01 | CS-04 | 1220 | Finance (R. Quinn) | Compressed air leak programme | Energy | Hard saving | OK
| 2026-04-01 | CS-05 | 1510 | Finance (R. Quinn) | LED high-bay lighting | Energy | Hard saving | OK
| 2026-04-01 | CS-08 | 1650 | Finance (R. Quinn) | Returnable packaging, key customer | Logistics and packaging | Hard saving | OK
| 2026-04-01 | CS-09 | 1820 | Finance (R. Quinn) | Chiller preventive maintenance | Maintenance | Cost avoidance | OK
| 2026-04-01 | CS-14 | 320 | Finance (R. Quinn) | Carton price increase avoided | Logistics and packaging | Cost avoidance | OK
| 2026-05-01 | CS-01 | 3660 | Finance (R. Quinn) | Regrind ratio up to 15% on PP housings | Material and procurement | Hard saving | OK
| 2026-05-01 | CS-02 | 4870 | Finance (R. Quinn) | ABS resin price renegotiation | Material and procurement | Hard saving | OK
| 2026-05-01 | CS-03 | 3760 | Finance (R. Quinn) | Sprue picker robots, presses 7 to 9 | Labour and productivity | Hard saving | OK
| 2026-05-01 | CS-04 | 1200 | Finance (R. Quinn) | Compressed air leak programme | Energy | Hard saving | OK
| 2026-05-01 | CS-05 | 1530 | Finance (R. Quinn) | LED high-bay lighting | Energy | Hard saving | OK
| 2026-05-01 | CS-06 | 1580 | Finance (R. Quinn) | Door handle scrap reduction (DOE) | Scrap and quality | Hard saving | OK
| 2026-05-01 | CS-08 | 1630 | Finance (R. Quinn) | Returnable packaging, key customer | Logistics and packaging | Hard saving | OK
| 2026-05-01 | CS-09 | 1860 | Finance (R. Quinn) | Chiller preventive maintenance | Maintenance | Cost avoidance | OK
| 2026-05-01 | CS-14 | 310 | Finance (R. Quinn) | Carton price increase avoided | Logistics and packaging | Cost avoidance | OK
| 2026-06-01 | CS-01 | 3500 | Finance (R. Quinn) | Regrind ratio up to 15% on PP housings | Material and procurement | Hard saving | OK
| 2026-06-01 | CS-02 | 4940 | Finance (R. Quinn) | ABS resin price renegotiation | Material and procurement | Hard saving | OK
| 2026-06-01 | CS-03 | 3980 | Finance (R. Quinn) | Sprue picker robots, presses 7 to 9 | Labour and productivity | Hard saving | OK
| 2026-06-01 | CS-04 | 1260 | Finance (R. Quinn) | Compressed air leak programme | Energy | Hard saving | OK
| 2026-06-01 | CS-05 | 1550 | Finance (R. Quinn) | LED high-bay lighting | Energy | Hard saving | OK
| 2026-06-01 | CS-06 | 1650 | Finance (R. Quinn) | Door handle scrap reduction (DOE) | Scrap and quality | Hard saving | OK
| 2026-06-01 | CS-08 | 1670 | Finance (R. Quinn) | Returnable packaging, key customer | Logistics and packaging | Hard saving | OK
| 2026-06-01 | CS-09 | 1880 | Finance (R. Quinn) | Chiller preventive maintenance | Maintenance | Cost avoidance | OK
| 2026-06-01 | CS-10 | 1310 | Finance (R. Quinn) | SMED on the 300 t presses | Labour and productivity | Hard saving | OK
| 2026-06-01 | CS-14 | 350 | Finance (R. Quinn) | Carton price increase avoided | Logistics and packaging | Cost avoidance | OK
| 2026-07-01 | CS-01 | 3700 | Finance (R. Quinn) | Regrind ratio up to 15% on PP housings | Material and procurement | Hard saving | OK
| 2026-07-01 | CS-02 | 4760 | Finance (R. Quinn) | ABS resin price renegotiation | Material and procurement | Hard saving | OK
| 2026-07-01 | CS-03 | 3700 | Finance (R. Quinn) | Sprue picker robots, presses 7 to 9 | Labour and productivity | Hard saving | OK
| 2026-07-01 | CS-04 | 1220 | Finance (R. Quinn) | Compressed air leak programme | Energy | Hard saving | OK
| 2026-07-01 | CS-05 | 1520 | Finance (R. Quinn) | LED high-bay lighting | Energy | Hard saving | OK
| 2026-07-01 | CS-06 | 1710 | Finance (R. Quinn) | Door handle scrap reduction (DOE) | Scrap and quality | Hard saving | OK
| 2026-07-01 | CS-07 | 890 | Finance (R. Quinn) | Hot runner conversion, clip mould | Scrap and quality | Hard saving | OK
| 2026-07-01 | CS-08 | 1670 | Finance (R. Quinn) | Returnable packaging, key customer | Logistics and packaging | Hard saving | OK
| 2026-07-01 | CS-09 | 1900 | Finance (R. Quinn) | Chiller preventive maintenance | Maintenance | Cost avoidance | OK
| 2026-07-01 | CS-10 | 1700 | Finance (R. Quinn) | SMED on the 300 t presses | Labour and productivity | Hard saving | OK
| 2026-07-01 | CS-14 | 330 | Finance (R. Quinn) | Carton price increase avoided | Logistics and packaging | Cost avoidance | OK
| 2026-08-01 | CS-01 | 3640 | Finance (R. Quinn) | Regrind ratio up to 15% on PP housings | Material and procurement | Hard saving | OK
| 2026-08-01 | CS-02 | 5280 | Finance (R. Quinn) | ABS resin price renegotiation | Material and procurement | Hard saving | OK
| 2026-08-01 | CS-03 | 3670 | Finance (R. Quinn) | Sprue picker robots, presses 7 to 9 | Labour and productivity | Hard saving | OK
| 2026-08-01 | CS-04 | 1350 | Finance (R. Quinn) | Compressed air leak programme | Energy | Hard saving | OK
| 2026-08-01 | CS-05 | 1450 | Finance (R. Quinn) | LED high-bay lighting | Energy | Hard saving | OK
| 2026-08-01 | CS-06 | 1600 | Finance (R. Quinn) | Door handle scrap reduction (DOE) | Scrap and quality | Hard saving | OK
| 2026-08-01 | CS-07 | 1220 | Finance (R. Quinn) | Hot runner conversion, clip mould | Scrap and quality | Hard saving | OK
| 2026-08-01 | CS-08 | 1860 | Finance (R. Quinn) | Returnable packaging, key customer | Logistics and packaging | Hard saving | OK
| 2026-08-01 | CS-09 | 1900 | Finance (R. Quinn) | Chiller preventive maintenance | Maintenance | Cost avoidance | OK
| 2026-08-01 | CS-10 | 2280 | Finance (R. Quinn) | SMED on the 300 t presses | Labour and productivity | Hard saving | OK
| 2026-08-01 | CS-14 | 320 | Finance (R. Quinn) | Carton price increase avoided | Logistics and packaging | Cost avoidance | OK
| 2026-09-01 | CS-01 | 3780 | Pending finance review | Regrind ratio up to 15% on PP housings | Material and procurement | Hard saving | OK
| 2026-09-01 | CS-02 | 5080 | Pending finance review | ABS resin price renegotiation | Material and procurement | Hard saving | OK
| 2026-09-01 | CS-03 | 3690 | Pending finance review | Sprue picker robots, presses 7 to 9 | Labour and productivity | Hard saving | OK
| 2026-09-01 | CS-04 | 1240 | Pending finance review | Compressed air leak programme | Energy | Hard saving | OK
| 2026-09-01 | CS-05 | 1430 | Pending finance review | LED high-bay lighting | Energy | Hard saving | OK
| 2026-09-01 | CS-06 | 1540 | Pending finance review | Door handle scrap reduction (DOE) | Scrap and quality | Hard saving | OK
| 2026-09-01 | CS-07 | 1530 | Pending finance review | Hot runner conversion, clip mould | Scrap and quality | Hard saving | OK
| 2026-09-01 | CS-08 | 1840 | Pending finance review | Returnable packaging, key customer | Logistics and packaging | Hard saving | OK
| 2026-09-01 | CS-09 | 1780 | Pending finance review | Chiller preventive maintenance | Maintenance | Cost avoidance | OK
| 2026-09-01 | CS-10 | 2280 | Pending finance review | SMED on the 300 t presses | Labour and productivity | Hard saving | OK
| 2026-09-01 | CS-14 | 320 | Pending finance review | Carton price increase avoided | Logistics and packaging | Cost avoidance | OK

## Dashboard
Cost Savings Tracker
| Realized savings against plan and target, the year-end forecast and where the savings come from. | [8 empty] | mfgcalcs.com
Brennan Moulded Products (example)
| Savings year from |  | 2026-01-01 |  | Reported through |  | 2026-09-01 |  | Target (EUR) |  | 260000
| HARD SAVINGS TO DATE (EUR) |  | REALIZATION OF PLAN TO DATE |  |  | YEAR-END FORECAST (EUR) |  |  | STILL TO FIND (EUR)
| 149100 |  | 87.59% |  |  | 220758.3333 |  |  | 39241.6667
| 170225 |  | 90% |  |  | 260000 |  |  | Target minus year-end forecast
| Near target |  | Near target |  |  | Below target
| COST AVOIDANCE, YEAR TO DATE (EUR) |  | ANNUAL RUN RATE IN PLAN (EUR) |  |  | ONE-TIME COST IN PLAN (EUR) |  |  | PROJECTS BELOW REALIZATION TARGET
| 17640 |  | 335300 |  |  | 152500 |  |  | 4
| Tracked; not counted against the target |  | Net annual hard savings of projects in plan |  |  | Implementation cost of projects in plan |  |  | See the Status column on the register
Hard savings by category (cost avoidance in the last column)
| Category | Projects | Annual run rate in plan | Plan to date | Realized to date | Realization | Year-end forecast | Cost avoidance to date
| Material and procurement | 3 | 115000 | 73083.3333 | 73240 | 100.2% | 89823.3333 | 0
| Labour and productivity | 2 | 85000 | 41583.3333 | 31750 | 76.35% | 53000 | 0
| Scrap and quality | 2 | 60500 | 21125 | 11720 | 55.48% | 26845 | 0
| Energy | 3 | 34800 | 21600 | 20290 | 93.94% | 28990 | 0
| Maintenance | 1 | 0 | 0 | 0 |  | 0 | 14690
| Logistics and packaging | 3 | 40000 | 12833.3333 | 12100 | 94.29% | 22100 | 2950
Pipeline by stage (all types)
| Stage | Projects | Counts in plan | Net annual savings | One-time cost
| Idea | 1 | No | 22000 | 40000
| Approved | 2 | Yes | 29000 | 2500
| In progress | 3 | Yes | 92500 | 42500
| Implemented | 3 | Yes | 93000 | 97000
| Validated | 5 | Yes | 146800 | 10500
Hard savings by month (cost avoidance shown separately)
| Month | Plan | Realized | Cumulative plan | Cumulative realized | Cost avoidance | Year target (chart)
|  | EUR | EUR | EUR | EUR | EUR | EUR
| 2026-01-01 | 5150 | 5160 | 5150 | 5160 | 340 | 260000
| 2026-02-01 | 10066.6667 | 10380 | 15216.6667 | 15540 | 2120 | 260000
| 2026-03-01 | 16316.6667 | 14090 | 31533.3333 | 29630 | 2090 | 260000
| 2026-04-01 | 17816.6667 | 15750 | 49350 | 45380 | 2140 | 260000
| 2026-05-01 | 20816.6667 | 18230 | 70166.6667 | 63610 | 2170 | 260000
| 2026-06-01 | 23483.3333 | 19860 | 93650 | 83470 | 2230 | 260000
| 2026-07-01 | 25525 | 20870 | 119175 | 104340 | 2230 | 260000
| 2026-08-01 | 25525 | 22350 | 144700 | 126690 | 2220 | 260000
| 2026-09-01 | 25525 | 22410 | 170225 | 149100 | 2100 | 260000
| 2026-10-01 | 23275 | 0 | 193500 |  | 0 | 260000
| 2026-11-01 | 24191.6667 | 0 | 217691.6667 |  | 0 | 260000
| 2026-12-01 | 24191.6667 | 0 | 241883.3333 |  | 0 | 260000
The Dashboard shows the 6 categories and 5 stages of the Setup lists. If you add more, extend the 'By category' and 'Pipeline by stage' blocks (see Method) or they will not appear here.
Formulas:
Annual run rate in plan = IF(B57="","",SUMIFS(tblSavings[Realized savings],tblSavings[Type],"Hard saving",tblSavings[Month],">="&B57,tblSavings[Month],"<"&EDATE(B57,1)))
Implementation cost of projects in plan = IF(B57="","",SUMIFS(tblSavings[Realized savings],tblSavings[Type],"Cost avoidance",tblSavings[Month],">="&B57,tblSavings[Month],"<"&EDATE(B57,1)))

## Method
Cost Savings Tracker
| How every number is calculated, with assumptions, limits and sources. |  | mfgcalcs.com
What this workbook calculates
Each project's saving is the difference between what a cost runs at per year before and after the change, less any running cost the change adds. The plan spreads that net annual saving evenly over the months that count in the savings year; the Savings Log records what was actually realized each month, as validated. Realization compares the two up to the report month, and the forecast adds the plan for the months still to come to what has been realized. Only hard savings count against the target; cost avoidance is shown separately.
Calculations
| Quantity | How it is calculated | Units
| Net annual savings | Baseline cost - cost after - recurring cost added, per year at the same volume (the EBITDA effect of the change with no revenue change). | currency/yr
| Payback | One-time cost / (net annual savings / 12). Blank when the net saving is not positive. | months
| Counted from and to | From: the start month, or the first month of the year if the project started earlier. To: the last month of the year, or the start month + (months a saving counts - 1) if sooner. | month
| Plan for the year | Net annual savings / 12 x the months counted in the year. Zero when the stage does not count in plan (Setup). | currency
| Plan to date | Net annual savings / 12 x the months counted from 'counted from' to the report month (or 'counted to' if sooner). | currency
| Realized to date | Sum of the project's Savings Log entries from the first month of the year to the report month. | currency
| Realization and status | Realized to date / plan to date. On target at or above the realization target; Near target within 10% below it; Below target under that. | %
| Forecast for the year | Realized to date + net annual savings / 12 x the counted months after the report month. | currency
| Dashboard totals | SUMIFS over the register for hard savings only: realized, plan to date, forecast. Realization of plan = realized / plan to date (a ratio of sums). Still to find = MAX(0, target - forecast). | currency, %
| Monthly plan and realized | Plan: SUMIFS of net annual savings / 12 over hard-saving projects in plan whose counted months include the month. Realized: SUMIFS of the Savings Log for the month. Cumulative = running sums from the first month. | currency
Assumptions
| • | Baseline and after costs are at the same volume, so the difference is the saving and not a volume change.
| • | A saving runs evenly through its counted months; ramp-ups show up as realization below plan.
| • | Realized figures are what finance (or you) validated; the workbook does not check them against the accounts.
| • | A project's months count by calendar month: a start on any day of a month counts that whole month.
Limitations
| • | The Dashboard has fixed blocks for 6 categories and 5 stages; longer lists need the blocks extended (a warning appears on the Dashboard).
| • | The forecast assumes the remaining months deliver exactly the plan; it is not a probability. Use the stage list to decide which projects count.
| • | One currency throughout; savings in other currencies must be converted before they are typed.
| • | Savings are not adjusted for volume changes after the baseline was set; re-baseline a project if its volume changes materially.
Agreement with the live calculator
The live Manufacturing EBITDA Impact calculator computes a change's annual EBITDA effect as sales contribution + cash operating savings - added recurring operating cost. For a cost-reduction project with no revenue change that is this workbook's net annual savings (baseline - after - recurring cost), and the build checks the reference implementation against the calculator's engine (20,000 of savings and 5,000 of added cost give 15,000; a project from the Verify sheet gives 27,000). Realization also agrees with the Project Benefit Realization calculator (measured / approved benefit) when the approved benefit is the plan to date. Difference: the calculators look at one project for one period; this workbook spreads each project over the months of the savings year, logs what was realized and adds the forecast.
Open the Manufacturing EBITDA Impact Calculator
Self-check
The Verify sheet holds fixed test inputs. Its formulas are the same formula text as the working sheets, placed against those inputs, and each result is compared with a value computed independently by the template's Python reference implementation when the file was built. If you edit a formula on a working sheet, the Verify sheet still tests the original formula text, so it will not detect your change.
Sources and standards
| • | Common practice in cost-reduction and lean programmes: hard savings vs cost avoidance, finance validation, counting a saving for a fixed number of months from its start (set yours on Setup).
| • | MFG Calcs Manufacturing EBITDA Impact calculator (manufacturing-ebitda-impact) and Project Benefit Realization calculator (project-benefit-realization).
Standards are cited by name so you can look them up; no copyrighted standard text or tables are reproduced. Statistical constants used are public.
Version history
| Version | Change | Date
| 1.0.0 | First release. | 15 October 2026
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Verify
Cost Savings Tracker
| Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference. | [22 empty] | mfgcalcs.com
| Self-check status |  | PASS |  | 21 of 21 checks pass
This sheet recomputes the workbook's own formulas on fixed test inputs and compares each result with a value computed independently by the template's Python reference implementation when the file was built. Every row should read PASS. The test inputs are fixed and do not change when you edit Setup or the working sheets.
Checks
| No. | Check |  |  |  | Expected (reference) | Workbook result | Difference | Tolerance | Result
| 1 | T-1 carry-over: plan for the year (Jan to Sep) |  |  |  | 18000 | 18000 | 0 | 1e-09 | PASS
| 2 | T-1: plan to date |  |  |  | 12000 | 12000 | 0 | 1e-09 | PASS
| 3 | T-1: realized to date (July entry excluded) |  |  |  | 11400 | 11400 | 0 | 1e-09 | PASS
| 4 | T-1: status |  |  |  | On target | On target |  | exact | PASS
| 5 | T-2: net annual savings (= EBITDA impact) |  |  |  | 27000 | 27000 | 0 | 1e-09 | PASS
| 6 | T-2: payback (months) |  |  |  | 8 | 8 | 0 | 1e-09 | PASS
| 7 | T-2: counted from (mid-month start) |  |  |  | 46113 | 46113 | 0 | 1e-09 | PASS
| 8 | T-2: plan to date |  |  |  | 6750 | 6750 | 0 | 1e-09 | PASS
| 9 | T-2: realization |  |  |  | 53.33% | 53.33% | 0 | 1e-09 | PASS
| 10 | T-2: status |  |  |  | Below target | Below target |  | exact | PASS
| 11 | T-2: forecast for the year |  |  |  | 17100 | 17100 | 0 | 1e-09 | PASS
| 12 | T-3 idea: plan for the year |  |  |  | 0 | 0 | 0 | 1e-09 | PASS
| 13 | T-5: Check reports cost after above baseline |  |  |  | Cost after above baseline | Cost after above baseline |  | exact | PASS
| 14 | Log: July entry after the report month |  |  |  | After the report month | After the report month |  | exact | PASS
| 15 | Hard savings realized to date (Dashboard) |  |  |  | 15000 | 15000 | 0 | 1e-09 | PASS
| 16 | Realization of plan to date (Dashboard) |  |  |  | 80% | 80% | 0 | 1e-09 | PASS
| 17 | Year-end forecast, hard savings (Dashboard) |  |  |  | 34500 | 34500 | 0 | 1e-09 | PASS
| 18 | Cost avoidance to date (Dashboard) |  |  |  | 5000 | 5000 | 0 | 1e-09 | PASS
| 19 | May: monthly plan, hard savings |  |  |  | 4250 | 4250 | 0 | 1e-09 | PASS
| 20 | June: cumulative realized |  |  |  | 15000 | 15000 | 0 | 1e-09 | PASS
| 21 | July: cumulative realized is blank after the report month | [6 empty] | exact | PASS
Fixed test inputs
White cells are fixed test inputs; blue cells are the workbook's formulas evaluated on them.
Parameters
| First month of the savings year |  |  | 2026-01-01
| Last month of the savings year |  |  | 2026-12-01
| Report through |  |  | 2026-06-01
| Months a saving counts |  |  | 12
| Realization target |  |  | 90%
| Hard savings target |  |  | 60000
Test table: Projects
[8 empty] | EUR/yr | EUR/yr | EUR | EUR/yr |  | EUR/yr |  |  |  | EUR | EUR | EUR |  |  | EUR
| ID | Project | Owner | Category | Type | Stage | Start month | Baseline cost | Cost after | One-time cost | Recurring cost added | Counts in plan | Net annual savings | Payback (months) | Counted from | Counted to | Plan for the year | Plan to date | Realized to date | Realization | Status | Forecast for the year | Check | Notes
| T-1 | Carry-over | A | Energy | Hard saving | Validated | 2025-10-01 | 120000 | 96000 |  |  | Yes | 24000 | 0 | 2026-01-01 | 2026-09-01 | 18000 | 12000 | 11400 | 95% | On target | 17400 | OK
| T-2 | New this year | B | Energy | Hard saving | In progress | 2026-04-15 | 80000 | 50000 | 18000 | 3000 | Yes | 27000 | 8 | 2026-04-01 | 2026-12-01 | 20250 | 6750 | 3600 | 53.33% | Below target | 17100 | OK
| T-3 | Idea | C | Energy | Hard saving | Idea | 2026-09-01 | 30000 | 20000 |  |  | No | 10000 | 0 | 2026-09-01 | 2026-12-01 | 0 | 0 | 0 |  |  | 0 | OK
| T-4 | Avoided rise | D | Energy | Cost avoidance | Validated | 2026-02-01 | 12000 | 0 |  |  | Yes | 12000 | 0 | 2026-02-01 | 2026-12-01 | 11000 | 5000 | 5000 | 100% | On target | 11000 | OK
| T-5 | Typing error | E | Energy | Hard saving | Idea | 2026-03-01 | 10000 | 11000 |  |  | No | -1000 |  | 2026-03-01 | 2026-12-01 | 0 | 0 | 0 |  |  | 0 | Cost after above baseline
Test table: Savings
EUR
| Month | Project ID | Realized savings | Validated by | Project | Category | Type | Check | Notes
| 2026-01-01 | T-1 | 1900 |  | Carry-over | Energy | Hard saving | OK
| 2026-02-01 | T-1 | 1900 |  | Carry-over | Energy | Hard saving | OK
| 2026-03-01 | T-1 | 1900 |  | Carry-over | Energy | Hard saving | OK
| 2026-04-01 | T-1 | 1900 |  | Carry-over | Energy | Hard saving | OK
| 2026-05-01 | T-1 | 1900 |  | Carry-over | Energy | Hard saving | OK
| 2026-06-01 | T-1 | 1900 |  | Carry-over | Energy | Hard saving | OK
| 2026-04-01 | T-2 | 1200 |  | New this year | Energy | Hard saving | OK
| 2026-05-01 | T-2 | 1200 |  | New this year | Energy | Hard saving | OK
| 2026-06-01 | T-2 | 1200 |  | New this year | Energy | Hard saving | OK
| 2026-02-01 | T-4 | 1000 |  | Avoided rise | Energy | Cost avoidance | OK
| 2026-03-01 | T-4 | 1000 |  | Avoided rise | Energy | Cost avoidance | OK
| 2026-04-01 | T-4 | 1000 |  | Avoided rise | Energy | Cost avoidance | OK
| 2026-05-01 | T-4 | 1000 |  | Avoided rise | Energy | Cost avoidance | OK
| 2026-06-01 | T-4 | 1000 |  | Avoided rise | Energy | Cost avoidance | OK
| 2026-07-01 | T-1 | 2000 |  | Carry-over | Energy | Hard saving | After the report month
Test monthly roll-up (same formulas as the Dashboard)
| Month | Plan | Realized | Cumulative plan | Cumulative realized | Cost avoidance | Year target (chart)
|  | EUR | EUR | EUR | EUR | EUR | EUR
| 2026-01-01 | 2000 | 1900 | 2000 | 1900 | 0 | 60000
| 2026-02-01 | 2000 | 1900 | 4000 | 3800 | 1000 | 60000
| 2026-03-01 | 2000 | 1900 | 6000 | 5700 | 1000 | 60000
| 2026-04-01 | 4250 | 3100 | 10250 | 8800 | 1000 | 60000
| 2026-05-01 | 4250 | 3100 | 14500 | 11900 | 1000 | 60000
| 2026-06-01 | 4250 | 3100 | 18750 | 15000 | 1000 | 60000
| 2026-07-01 | 4250 | 2000 | 23000 |  | 0 | 60000
| 2026-08-01 | 4250 | 0 | 27250 |  | 0 | 60000
| 2026-09-01 | 4250 | 0 | 31500 |  | 0 | 60000
| 2026-10-01 | 2250 | 0 | 33750 |  | 0 | 60000
| 2026-11-01 | 2250 | 0 | 36000 |  | 0 | 60000
| 2026-12-01 | 2250 | 0 | 38250 |  | 0 | 60000
Formulas:
Counted from = IF(tblVerifyProjects[[#This Row],[ID]]="","",MAX(DATE(YEAR(tblVerifyProjects[[#This Row],[Start month]]),MONTH(tblVerifyProjects[[#This Row],[Start month]]),1),E37))
Counted to = IF(tblVerifyProjects[[#This Row],[ID]]="","",IF(E40>0,MIN(E38,EDATE(DATE(YEAR(tblVerifyProjects[[#This Row],[Start month]]),MONTH(tblVerifyProjects[[#This Row],[Start month]]),1),E40-1)),E38))
Realized to date = IF(tblVerifyProjects[[#This Row],[ID]]="","",SUMIFS(tblVerifySavings[Realized savings],tblVerifySavings[Project ID],tblVerifyProjects[[#This Row],[ID]],tblVerifySavings[Month],">="&E37,tblVerifySavings[Month],"<"&EDATE(E39,1)))
Owner = IF(B75="","",SUMIFS(tblVerifySavings[Realized savings],tblVerifySavings[Type],"Hard saving",tblVerifySavings[Month],">="&B75,tblVerifySavings[Month],"<"&EDATE(B75,1)))
Expected (reference) = IF(B75="","",SUMIFS(tblVerifySavings[Realized savings],tblVerifySavings[Type],"Cost avoidance",tblVerifySavings[Month],">="&B75,tblVerifySavings[Month],"<"&EDATE(B75,1)))