## Start Here
Hour-by-Hour Production Board
| Read this first: what the workbook does and how to use it. |  |  |  | mfgcalcs.com
Hour-by-Hour Production Board
Log each line's output every hour against a takt-based target and see the running plan vs actual, the hours that miss and why, by line, day and hour of the shift.
For: Team leaders, cell leaders, shift supervisors and production managers who run a line to takt and review it hour by hour.
Version 1.0.0 · updated 24 October 2026
Quick start
| 1. | On Setup, type your plant name and hourly attainment target, then replace the example lines, shifts, hour slots, products (with their takt times) and miss reasons.
| 2. | Each hour, add one row per line on Hourly Board: the hour of the shift, the product, the minutes available in that hour and the good units made.
| 3. | When an hour misses its target, pick the miss reason and write the countermeasure; the Check column asks for it.
| 4. | Open the Dashboard: filter by line, or set From and To to one day, and read which hours and which reasons lost the most units.
| 5. | To print one shift's board for the line, pick the date, shift and line on Daily Board. A date with no rows prints a blank board to fill in by hand.
What is in this workbook
|  | Start Here | Read this first: what the workbook does and how to use it.
|  | Setup | Plant name, the hourly target, and the line, shift, hour-slot, product (takt time) and miss-reason lists.
|  | Hourly Board | One row per line per hour: the minutes available, the units made, and why an hour missed.
|  | Daily Board | One shift's hour-by-hour board for one line, to print and hang by the line or review at the shift handover.
|  | Dashboard | Hourly attainment against takt, where in the shift the units are lost, and why, for the line and dates you choose.
|  | Method | How every number is calculated, with assumptions, limits and sources.
|  | Verify | Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference.
Colour key
|  | Input | Yellow cells are yours: type a value or pick from the list. Each one says what it accepts when you click it.
|  | Calculated | Blue cells are formulas. They update as you type; overwrite one and that row stops calculating.
|  | Note | Grey boxes are guidance and labelled example data.
|  | Status words | On target / PASS / OK | Near target / Check | Below target / FAIL
Status is always written in words; the colour only repeats it, so the workbook reads the same in black-and-white print and for colour-blind readers.
Self-check and links
|  | Self-check | PASS | 22 of 22 checks pass
The Verify sheet recomputes this workbook's formulas on fixed test inputs and compares them with an independent reference calculation. PASS means every check agreed when you opened the file.
|  | Run it live | Takt Time Calculator on mfgcalcs.com
|  | Latest version | mfgcalcs.com/templates/hour-by-hour-production-board
|  | More free templates | mfgcalcs.com/templates
|  | Version | 1.0.0 (updated 24 October 2026)
About the example data
Every number already in this workbook is example data for Calder Pump Assembly, a fictional business invented for this template, so the dashboard and charts show something meaningful on day one. It covers two assembly cells on two shifts over ten working days (5 to 16 October 2026), generated from a fixed seed. To clear it: on each working sheet, select the example rows of the table, right-click and choose Delete > Table Rows. The formulas stay, and every new row you type below the table picks them up.
Good to know
| • | Sheets Start Here, Daily Board, Dashboard, Method, Verify are protected without a password so formulas and layout are not overwritten by accident. To change them: Review > Unprotect Sheet.
| • | Setup and the working sheets are not protected, so tables grow as you add rows.
| • | Works in Excel 2016 and later, Microsoft 365, LibreOffice 24 and Google Sheets (File > Import). No macros, no external links, no add-ins.
| • | Money is shown in the currency you type on Setup; no exchange rates are applied.
| • | The Daily Board sheet prints without the MFG Calcs band at the top; its page footer keeps a small mfgcalcs.com credit, which you can change in Page Layout > Header & Footer after unprotecting the sheet.
Free from MFG Calcs - keep this credit when you share it.
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Setup
Hour-by-Hour Production Board
| Plant name, the hourly target, and the line, shift, hour-slot, product (takt time) and miss-reason lists. |  | mfgcalcs.com
Plant and target
| Plant name | Calder Pump Assembly (example)
| Hourly attainment target | 100%
The hourly target is set by takt time, not by a benchmark: available seconds in the hour divided by the product's takt, rounded down to whole units. 'Near target' means within 5% below the attainment target.
Lists that feed the dropdowns
Edit, add or remove rows; every dropdown on the Hourly Board reads these lists. Takt time is available time divided by customer demand (use the Takt Time calculator); enter it in seconds per unit.
Lines
| Line | Area | Description
| A1 | Assembly | Pump housing and valve body cell, 4 stations
| A2 | Assembly | Bracket kit and valve body cell, 3 stations
Shifts
| Shift | Starts | Notes
| Early | 6:00 | 06:00 to 14:00, lunch in hour 5
| Late | 14:00 | 14:00 to 22:00, lunch in hour 5
Hour slots
| Hour | Usual minutes | Notes
| 1 | 60 | Start-up and handover
| 2 | 60
| 3 | 50 | 10-minute break
| 4 | 60
| 5 | 30 | 30-minute lunch
| 6 | 60 | First hour after lunch
| 7 | 50 | 10-minute break
| 8 | 50 | 10-minute clean-down
Products and takt times
| Product | Takt time (s) | Notes
| Pump housing PH-40 | 40 | Takt from 630 units a shift
| Valve body VB-12 | 48 | Takt from 525 units a shift
| Bracket kit BK-3 | 30 | Takt from 840 units a shift
Miss reasons
| Reason | Definition
| Start-up | Shift start, handover or first-piece approval
| Material shortage | Parts or packaging not at the cell
| Minor stops | Jams, misfeeds and short stops under 5 minutes
| Machine fault | A station down for repair
| Quality check | Line held for a check, rework or a quality decision
| Changeover | Product change, last good part to first good part
| Operator away | Station unstaffed: training, meeting, absence
| Other | Anything else; say what in the countermeasure

## Hourly Board
Hour-by-Hour Production Board
| One row per line per hour: the minutes available, the units made, and why an hour missed. | [19 empty] | mfgcalcs.com
Example data for Calder Pump Assembly (fictional). Replace it with your own: select the example rows, right-click, Delete > Table Rows. Yellow = you type; blue = calculated; Check names any problem.
| Date | Shift | Line | Hour | Product | Available (min) | Actual (units) | Miss reason | Takt (s) | Target (units) | Gap (units) | Short (units) | Attainment | Hit | Hour status | Cum. target | Cum. actual | Cum. gap | View date | Check | Countermeasure
| 2026-10-05 | Early | A1 | 1 | Pump housing PH-40 | 60 | 79 | Start-up | 40 | 90 | -11 | 11 | 87.78% | 0 | Below target | 90 | 79 | -11 | 2026-10-05 | OK
| 2026-10-05 | Early | A1 | 2 | Pump housing PH-40 | 60 | 91 |  | 40 | 90 | 1 | 0 | 101.1% | 1 | On target | 180 | 170 | -10 | 2026-10-05 | OK
| 2026-10-05 | Early | A1 | 3 | Pump housing PH-40 | 50 | 71 | Minor stops | 40 | 75 | -4 | 4 | 94.67% | 0 | Below target | 255 | 241 | -14 | 2026-10-05 | OK
| 2026-10-05 | Early | A1 | 4 | Pump housing PH-40 | 60 | 88 | Minor stops | 40 | 90 | -2 | 2 | 97.78% | 0 | Near target | 345 | 329 | -16 | 2026-10-05 | OK
| 2026-10-05 | Early | A1 | 5 | Pump housing PH-40 | 30 | 47 |  | 40 | 45 | 2 | 0 | 104.4% | 1 | On target | 390 | 376 | -14 | 2026-10-05 | OK
| 2026-10-05 | Early | A1 | 6 | Pump housing PH-40 | 60 | 87 | Operator away | 40 | 90 | -3 | 3 | 96.67% | 0 | Near target | 480 | 463 | -17 | 2026-10-05 | OK
| 2026-10-05 | Early | A1 | 7 | Pump housing PH-40 | 50 | 73 | Minor stops | 40 | 75 | -2 | 2 | 97.33% | 0 | Near target | 555 | 536 | -19 | 2026-10-05 | OK
| 2026-10-05 | Early | A1 | 8 | Pump housing PH-40 | 50 | 72 | Minor stops | 40 | 75 | -3 | 3 | 96% | 0 | Near target | 630 | 608 | -22 | 2026-10-05 | OK
| 2026-10-05 | Early | A2 | 1 | Bracket kit BK-3 | 60 | 102 | Start-up | 30 | 120 | -18 | 18 | 85% | 0 | Below target | 120 | 102 | -18 | 2026-10-05 | OK | First-piece approval took 15 min
| 2026-10-05 | Early | A2 | 2 | Bracket kit BK-3 | 60 | 124 |  | 30 | 120 | 4 | 0 | 103.3% | 1 | On target | 240 | 226 | -14 | 2026-10-05 | OK
| 2026-10-05 | Early | A2 | 3 | Bracket kit BK-3 | 50 | 44 | Material shortage | 30 | 100 | -56 | 56 | 44% | 0 | Below target | 340 | 270 | -70 | 2026-10-05 | OK | Housings late from goods-in; kanban raised
| 2026-10-05 | Early | A2 | 4 | Bracket kit BK-3 | 60 | 122 |  | 30 | 120 | 2 | 0 | 101.7% | 1 | On target | 460 | 392 | -68 | 2026-10-05 | OK
| 2026-10-05 | Early | A2 | 5 | Bracket kit BK-3 | 30 | 62 |  | 30 | 60 | 2 | 0 | 103.3% | 1 | On target | 520 | 454 | -66 | 2026-10-05 | OK
| 2026-10-05 | Early | A2 | 6 | Bracket kit BK-3 | 60 | 118 | Minor stops | 30 | 120 | -2 | 2 | 98.33% | 0 | Near target | 640 | 572 | -68 | 2026-10-05 | OK
| 2026-10-05 | Early | A2 | 7 | Bracket kit BK-3 | 50 | 103 |  | 30 | 100 | 3 | 0 | 103% | 1 | On target | 740 | 675 | -65 | 2026-10-05 | OK
| 2026-10-05 | Early | A2 | 8 | Bracket kit BK-3 | 50 | 100 |  | 30 | 100 | 0 | 0 | 100% | 1 | On target | 840 | 775 | -65 | 2026-10-05 | OK
| 2026-10-05 | Late | A1 | 1 | Pump housing PH-40 | 60 | 78 | Start-up | 40 | 90 | -12 | 12 | 86.67% | 0 | Below target | 90 | 78 | -12 | 2026-10-05 | OK
| 2026-10-05 | Late | A1 | 2 | Pump housing PH-40 | 60 | 89 | Minor stops | 40 | 90 | -1 | 1 | 98.89% | 0 | Near target | 180 | 167 | -13 | 2026-10-05 | OK
| 2026-10-05 | Late | A1 | 3 | Pump housing PH-40 | 50 | 79 |  | 40 | 75 | 4 | 0 | 105.3% | 1 | On target | 255 | 246 | -9 | 2026-10-05 | OK
| 2026-10-05 | Late | A1 | 4 | Pump housing PH-40 | 60 | 85 | Minor stops | 40 | 90 | -5 | 5 | 94.44% | 0 | Below target | 345 | 331 | -14 | 2026-10-05 | OK
| 2026-10-05 | Late | A1 | 5 | Pump housing PH-40 | 30 | 43 | Quality check | 40 | 45 | -2 | 2 | 95.56% | 0 | Near target | 390 | 374 | -16 | 2026-10-05 | OK
| 2026-10-05 | Late | A1 | 6 | Pump housing PH-40 | 60 | 87 | Quality check | 40 | 90 | -3 | 3 | 96.67% | 0 | Near target | 480 | 461 | -19 | 2026-10-05 | OK
| 2026-10-05 | Late | A1 | 7 | Pump housing PH-40 | 50 | 76 |  | 40 | 75 | 1 | 0 | 101.3% | 1 | On target | 555 | 537 | -18 | 2026-10-05 | OK
| 2026-10-05 | Late | A1 | 8 | Pump housing PH-40 | 50 | 75 |  | 40 | 75 | 0 | 0 | 100% | 1 | On target | 630 | 612 | -18 | 2026-10-05 | OK
| 2026-10-05 | Late | A2 | 1 | Bracket kit BK-3 | 60 | 106 | Start-up | 30 | 120 | -14 | 14 | 88.33% | 0 | Below target | 120 | 106 | -14 | 2026-10-05 | OK
| 2026-10-05 | Late | A2 | 2 | Bracket kit BK-3 | 60 | 53 | Material shortage | 30 | 120 | -67 | 67 | 44.17% | 0 | Below target | 240 | 159 | -81 | 2026-10-05 | OK | Housings late from goods-in; kanban raised
| 2026-10-05 | Late | A2 | 3 | Bracket kit BK-3 | 50 | 105 |  | 30 | 100 | 5 | 0 | 105% | 1 | On target | 340 | 264 | -76 | 2026-10-05 | OK
| 2026-10-05 | Late | A2 | 4 | Bracket kit BK-3 | 60 | 117 | Quality check | 30 | 120 | -3 | 3 | 97.5% | 0 | Near target | 460 | 381 | -79 | 2026-10-05 | OK
| 2026-10-05 | Late | A2 | 5 | Bracket kit BK-3 | 30 | 58 | Minor stops | 30 | 60 | -2 | 2 | 96.67% | 0 | Near target | 520 | 439 | -81 | 2026-10-05 | OK
| 2026-10-05 | Late | A2 | 6 | Bracket kit BK-3 | 60 | 112 | Minor stops | 30 | 120 | -8 | 8 | 93.33% | 0 | Below target | 640 | 551 | -89 | 2026-10-05 | OK
| 2026-10-05 | Late | A2 | 7 | Bracket kit BK-3 | 50 | 105 |  | 30 | 100 | 5 | 0 | 105% | 1 | On target | 740 | 656 | -84 | 2026-10-05 | OK
| 2026-10-05 | Late | A2 | 8 | Bracket kit BK-3 | 50 | 94 | Quality check | 30 | 100 | -6 | 6 | 94% | 0 | Below target | 840 | 750 | -90 | 2026-10-05 | OK
| 2026-10-06 | Early | A1 | 1 | Valve body VB-12 | 60 | 71 | Start-up | 48 | 75 | -4 | 4 | 94.67% | 0 | Below target | 75 | 71 | -4 | 2026-10-06 | OK
| 2026-10-06 | Early | A1 | 2 | Valve body VB-12 | 60 | 73 | Machine fault | 48 | 75 | -2 | 2 | 97.33% | 0 | Near target | 150 | 144 | -6 | 2026-10-06 | OK | Station 3 press reset
| 2026-10-06 | Early | A1 | 3 | Valve body VB-12 | 50 | 65 |  | 48 | 62 | 3 | 0 | 104.8% | 1 | On target | 212 | 209 | -3 | 2026-10-06 | OK
| 2026-10-06 | Early | A1 | 4 | Valve body VB-12 | 60 | 76 |  | 48 | 75 | 1 | 0 | 101.3% | 1 | On target | 287 | 285 | -2 | 2026-10-06 | OK
| 2026-10-06 | Early | A1 | 5 | Valve body VB-12 | 30 | 36 | Quality check | 48 | 37 | -1 | 1 | 97.3% | 0 | Near target | 324 | 321 | -3 | 2026-10-06 | OK
| 2026-10-06 | Early | A1 | 6 | Valve body VB-12 | 60 | 72 | Machine fault | 48 | 75 | -3 | 3 | 96% | 0 | Near target | 399 | 393 | -6 | 2026-10-06 | OK | Station 3 press reset
| 2026-10-06 | Early | A1 | 7 | Valve body VB-12 | 50 | 65 |  | 48 | 62 | 3 | 0 | 104.8% | 1 | On target | 461 | 458 | -3 | 2026-10-06 | OK
| 2026-10-06 | Early | A1 | 8 | Valve body VB-12 | 50 | 63 |  | 48 | 62 | 1 | 0 | 101.6% | 1 | On target | 523 | 521 | -2 | 2026-10-06 | OK
| 2026-10-06 | Early | A2 | 1 | Bracket kit BK-3 | 60 | 102 | Start-up | 30 | 120 | -18 | 18 | 85% | 0 | Below target | 120 | 102 | -18 | 2026-10-06 | OK | First-piece approval took 15 min
| 2026-10-06 | Early | A2 | 2 | Bracket kit BK-3 | 60 | 116 | Machine fault | 30 | 120 | -4 | 4 | 96.67% | 0 | Near target | 240 | 218 | -22 | 2026-10-06 | OK | Station 3 press reset
| 2026-10-06 | Early | A2 | 3 | Bracket kit BK-3 | 50 | 104 |  | 30 | 100 | 4 | 0 | 104% | 1 | On target | 340 | 322 | -18 | 2026-10-06 | OK
| 2026-10-06 | Early | A2 | 4 | Bracket kit BK-3 | 60 | 119 | Minor stops | 30 | 120 | -1 | 1 | 99.17% | 0 | Near target | 460 | 441 | -19 | 2026-10-06 | OK
| 2026-10-06 | Early | A2 | 5 | Bracket kit BK-3 | 30 | 60 |  | 30 | 60 | 0 | 0 | 100% | 1 | On target | 520 | 501 | -19 | 2026-10-06 | OK
| 2026-10-06 | Early | A2 | 6 | Bracket kit BK-3 | 60 | 118 | Operator away | 30 | 120 | -2 | 2 | 98.33% | 0 | Near target | 640 | 619 | -21 | 2026-10-06 | OK
| 2026-10-06 | Early | A2 | 7 | Bracket kit BK-3 | 50 | 105 |  | 30 | 100 | 5 | 0 | 105% | 1 | On target | 740 | 724 | -16 | 2026-10-06 | OK
| 2026-10-06 | Early | A2 | 8 | Bracket kit BK-3 | 50 | 104 |  | 30 | 100 | 4 | 0 | 104% | 1 | On target | 840 | 828 | -12 | 2026-10-06 | OK
| 2026-10-06 | Late | A1 | 1 | Pump housing PH-40 | 60 | 84 | Start-up | 40 | 90 | -6 | 6 | 93.33% | 0 | Below target | 90 | 84 | -6 | 2026-10-06 | OK
| 2026-10-06 | Late | A1 | 2 | Pump housing PH-40 | 60 | 89 | Minor stops | 40 | 90 | -1 | 1 | 98.89% | 0 | Near target | 180 | 173 | -7 | 2026-10-06 | OK
| 2026-10-06 | Late | A1 | 3 | Pump housing PH-40 | 50 | 73 | Minor stops | 40 | 75 | -2 | 2 | 97.33% | 0 | Near target | 255 | 246 | -9 | 2026-10-06 | OK
| 2026-10-06 | Late | A1 | 4 | Pump housing PH-40 | 60 | 90 |  | 40 | 90 | 0 | 0 | 100% | 1 | On target | 345 | 336 | -9 | 2026-10-06 | OK
| 2026-10-06 | Late | A1 | 5 | Pump housing PH-40 | 30 | 46 |  | 40 | 45 | 1 | 0 | 102.2% | 1 | On target | 390 | 382 | -8 | 2026-10-06 | OK
| 2026-10-06 | Late | A1 | 6 | Pump housing PH-40 | 60 | 91 |  | 40 | 90 | 1 | 0 | 101.1% | 1 | On target | 480 | 473 | -7 | 2026-10-06 | OK
| 2026-10-06 | Late | A1 | 7 | Pump housing PH-40 | 50 | 72 | Quality check | 40 | 75 | -3 | 3 | 96% | 0 | Near target | 555 | 545 | -10 | 2026-10-06 | OK
| 2026-10-06 | Late | A1 | 8 | Pump housing PH-40 | 50 | 78 |  | 40 | 75 | 3 | 0 | 104% | 1 | On target | 630 | 623 | -7 | 2026-10-06 | OK
| 2026-10-06 | Late | A2 | 1 | Bracket kit BK-3 | 60 | 110 | Start-up | 30 | 120 | -10 | 10 | 91.67% | 0 | Below target | 120 | 110 | -10 | 2026-10-06 | OK
| 2026-10-06 | Late | A2 | 2 | Bracket kit BK-3 | 60 | 119 | Machine fault | 30 | 120 | -1 | 1 | 99.17% | 0 | Near target | 240 | 229 | -11 | 2026-10-06 | OK | Station 3 press reset
| 2026-10-06 | Late | A2 | 3 | Bracket kit BK-3 | 50 | 94 | Minor stops | 30 | 100 | -6 | 6 | 94% | 0 | Below target | 340 | 323 | -17 | 2026-10-06 | OK
| 2026-10-06 | Late | A2 | 4 | Bracket kit BK-3 | 60 | 114 | Operator away | 30 | 120 | -6 | 6 | 95% | 0 | Near target | 460 | 437 | -23 | 2026-10-06 | OK
| 2026-10-06 | Late | A2 | 5 | Bracket kit BK-3 | 30 | 60 |  | 30 | 60 | 0 | 0 | 100% | 1 | On target | 520 | 497 | -23 | 2026-10-06 | OK
| 2026-10-06 | Late | A2 | 6 | Bracket kit BK-3 | 60 | 44 | Material shortage | 30 | 120 | -76 | 76 | 36.67% | 0 | Below target | 640 | 541 | -99 | 2026-10-06 | OK | Housings late from goods-in; kanban raised
| 2026-10-06 | Late | A2 | 7 | Bracket kit BK-3 | 50 | 95 | Minor stops | 30 | 100 | -5 | 5 | 95% | 0 | Near target | 740 | 636 | -104 | 2026-10-06 | OK
| 2026-10-06 | Late | A2 | 8 | Bracket kit BK-3 | 50 | 99 | Minor stops | 30 | 100 | -1 | 1 | 99% | 0 | Near target | 840 | 735 | -105 | 2026-10-06 | OK
| 2026-10-07 | Early | A1 | 1 | Pump housing PH-40 | 60 | 76 | Start-up | 40 | 90 | -14 | 14 | 84.44% | 0 | Below target | 90 | 76 | -14 | 2026-10-07 | OK | First-piece approval took 15 min
| 2026-10-07 | Early | A1 | 2 | Pump housing PH-40 | 60 | 92 |  | 40 | 90 | 2 | 0 | 102.2% | 1 | On target | 180 | 168 | -12 | 2026-10-07 | OK
| 2026-10-07 | Early | A1 | 3 | Pump housing PH-40 | 50 | 74 | Minor stops | 40 | 75 | -1 | 1 | 98.67% | 0 | Near target | 255 | 242 | -13 | 2026-10-07 | OK
| 2026-10-07 | Early | A1 | 4 | Pump housing PH-40 | 60 | 90 |  | 40 | 90 | 0 | 0 | 100% | 1 | On target | 345 | 332 | -13 | 2026-10-07 | OK
| 2026-10-07 | Early | A1 | 5 | Pump housing PH-40 | 30 | 45 |  | 40 | 45 | 0 | 0 | 100% | 1 | On target | 390 | 377 | -13 | 2026-10-07 | OK
| 2026-10-07 | Early | A1 | 6 | Pump housing PH-40 | 60 | 86 | Minor stops | 40 | 90 | -4 | 4 | 95.56% | 0 | Near target | 480 | 463 | -17 | 2026-10-07 | OK
| 2026-10-07 | Early | A1 | 7 | Pump housing PH-40 | 50 | 76 |  | 40 | 75 | 1 | 0 | 101.3% | 1 | On target | 555 | 539 | -16 | 2026-10-07 | OK
| 2026-10-07 | Early | A1 | 8 | Pump housing PH-40 | 50 | 79 |  | 40 | 75 | 4 | 0 | 105.3% | 1 | On target | 630 | 618 | -12 | 2026-10-07 | OK
| 2026-10-07 | Early | A2 | 1 | Valve body VB-12 | 60 | 68 | Start-up | 48 | 75 | -7 | 7 | 90.67% | 0 | Below target | 75 | 68 | -7 | 2026-10-07 | OK
| 2026-10-07 | Early | A2 | 2 | Valve body VB-12 | 60 | 73 | Minor stops | 48 | 75 | -2 | 2 | 97.33% | 0 | Near target | 150 | 141 | -9 | 2026-10-07 | OK
| 2026-10-07 | Early | A2 | 3 | Valve body VB-12 | 50 | 61 | Operator away | 48 | 62 | -1 | 1 | 98.39% | 0 | Near target | 212 | 202 | -10 | 2026-10-07 | OK
| 2026-10-07 | Early | A2 | 4 | Valve body VB-12 | 60 | 79 |  | 48 | 75 | 4 | 0 | 105.3% | 1 | On target | 287 | 281 | -6 | 2026-10-07 | OK
| 2026-10-07 | Early | A2 | 5 | Valve body VB-12 | 30 | 39 |  | 48 | 37 | 2 | 0 | 105.4% | 1 | On target | 324 | 320 | -4 | 2026-10-07 | OK
| 2026-10-07 | Early | A2 | 6 | Valve body VB-12 | 60 | 73 | Minor stops | 48 | 75 | -2 | 2 | 97.33% | 0 | Near target | 399 | 393 | -6 | 2026-10-07 | OK
| 2026-10-07 | Early | A2 | 7 | Valve body VB-12 | 50 | 25 | Material shortage | 48 | 62 | -37 | 37 | 40.32% | 0 | Below target | 461 | 418 | -43 | 2026-10-07 | OK | Housings late from goods-in; kanban raised
| 2026-10-07 | Early | A2 | 8 | Valve body VB-12 | 50 | 64 |  | 48 | 62 | 2 | 0 | 103.2% | 1 | On target | 523 | 482 | -41 | 2026-10-07 | OK
| 2026-10-07 | Late | A1 | 1 | Pump housing PH-40 | 60 | 75 | Start-up | 40 | 90 | -15 | 15 | 83.33% | 0 | Below target | 90 | 75 | -15 | 2026-10-07 | OK | First-piece approval took 15 min
| 2026-10-07 | Late | A1 | 2 | Pump housing PH-40 | 60 | 91 |  | 40 | 90 | 1 | 0 | 101.1% | 1 | On target | 180 | 166 | -14 | 2026-10-07 | OK
| 2026-10-07 | Late | A1 | 3 | Pump housing PH-40 | 50 | 71 | Machine fault | 40 | 75 | -4 | 4 | 94.67% | 0 | Below target | 255 | 237 | -18 | 2026-10-07 | OK | Station 3 press reset
| 2026-10-07 | Late | A1 | 4 | Pump housing PH-40 | 60 | 87 | Minor stops | 40 | 90 | -3 | 3 | 96.67% | 0 | Near target | 345 | 324 | -21 | 2026-10-07 | OK
| 2026-10-07 | Late | A1 | 5 | Pump housing PH-40 | 30 | 43 | Machine fault | 40 | 45 | -2 | 2 | 95.56% | 0 | Near target | 390 | 367 | -23 | 2026-10-07 | OK | Station 3 press reset
| 2026-10-07 | Late | A1 | 6 | Pump housing PH-40 | 60 | 88 | Machine fault | 40 | 90 | -2 | 2 | 97.78% | 0 | Near target | 480 | 455 | -25 | 2026-10-07 | OK | Station 3 press reset
| 2026-10-07 | Late | A1 | 7 | Pump housing PH-40 | 50 | 73 | Minor stops | 40 | 75 | -2 | 2 | 97.33% | 0 | Near target | 555 | 528 | -27 | 2026-10-07 | OK
| 2026-10-07 | Late | A1 | 8 | Pump housing PH-40 | 50 | 75 |  | 40 | 75 | 0 | 0 | 100% | 1 | On target | 630 | 603 | -27 | 2026-10-07 | OK
| 2026-10-07 | Late | A2 | 1 | Valve body VB-12 | 60 | 60 | Start-up | 48 | 75 | -15 | 15 | 80% | 0 | Below target | 75 | 60 | -15 | 2026-10-07 | OK | First-piece approval took 15 min
| 2026-10-07 | Late | A2 | 2 | Valve body VB-12 | 60 | 79 |  | 48 | 75 | 4 | 0 | 105.3% | 1 | On target | 150 | 139 | -11 | 2026-10-07 | OK
| 2026-10-07 | Late | A2 | 3 | Valve body VB-12 | 50 | 62 |  | 48 | 62 | 0 | 0 | 100% | 1 | On target | 212 | 201 | -11 | 2026-10-07 | OK
| 2026-10-07 | Late | A2 | 4 | Valve body VB-12 | 60 | 72 | Minor stops | 48 | 75 | -3 | 3 | 96% | 0 | Near target | 287 | 273 | -14 | 2026-10-07 | OK
| 2026-10-07 | Late | A2 | 5 | Valve body VB-12 | 30 | 37 |  | 48 | 37 | 0 | 0 | 100% | 1 | On target | 324 | 310 | -14 | 2026-10-07 | OK
| 2026-10-07 | Late | A2 | 6 | Valve body VB-12 | 60 | 76 |  | 48 | 75 | 1 | 0 | 101.3% | 1 | On target | 399 | 386 | -13 | 2026-10-07 | OK
| 2026-10-07 | Late | A2 | 7 | Valve body VB-12 | 50 | 61 | Quality check | 48 | 62 | -1 | 1 | 98.39% | 0 | Near target | 461 | 447 | -14 | 2026-10-07 | OK
| 2026-10-07 | Late | A2 | 8 | Valve body VB-12 | 50 | 63 |  | 48 | 62 | 1 | 0 | 101.6% | 1 | On target | 523 | 510 | -13 | 2026-10-07 | OK
| 2026-10-08 | Early | A1 | 1 | Valve body VB-12 | 60 | 69 | Start-up | 48 | 75 | -6 | 6 | 92% | 0 | Below target | 75 | 69 | -6 | 2026-10-08 | OK
| 2026-10-08 | Early | A1 | 2 | Valve body VB-12 | 60 | 78 |  | 48 | 75 | 3 | 0 | 104% | 1 | On target | 150 | 147 | -3 | 2026-10-08 | OK
| 2026-10-08 | Early | A1 | 3 | Valve body VB-12 | 50 | 64 |  | 48 | 62 | 2 | 0 | 103.2% | 1 | On target | 212 | 211 | -1 | 2026-10-08 | OK
| 2026-10-08 | Early | A1 | 4 | Valve body VB-12 | 60 | 72 | Minor stops | 48 | 75 | -3 | 3 | 96% | 0 | Near target | 287 | 283 | -4 | 2026-10-08 | OK
| 2026-10-08 | Early | A1 | 5 | Valve body VB-12 | 30 | 36 | Machine fault | 48 | 37 | -1 | 1 | 97.3% | 0 | Near target | 324 | 319 | -5 | 2026-10-08 | OK | Station 3 press reset
| 2026-10-08 | Early | A1 | 6 | Valve body VB-12 | 60 | 73 | Minor stops | 48 | 75 | -2 | 2 | 97.33% | 0 | Near target | 399 | 392 | -7 | 2026-10-08 | OK
| 2026-10-08 | Early | A1 | 7 | Valve body VB-12 | 50 | 63 |  | 48 | 62 | 1 | 0 | 101.6% | 1 | On target | 461 | 455 | -6 | 2026-10-08 | OK
| 2026-10-08 | Early | A1 | 8 | Valve body VB-12 | 50 | 60 | Minor stops | 48 | 62 | -2 | 2 | 96.77% | 0 | Near target | 523 | 515 | -8 | 2026-10-08 | OK
| 2026-10-08 | Early | A2 | 1 | Bracket kit BK-3 | 60 | 113 | Start-up | 30 | 120 | -7 | 7 | 94.17% | 0 | Below target | 120 | 113 | -7 | 2026-10-08 | OK
| 2026-10-08 | Early | A2 | 2 | Bracket kit BK-3 | 60 | 118 | Quality check | 30 | 120 | -2 | 2 | 98.33% | 0 | Near target | 240 | 231 | -9 | 2026-10-08 | OK
| 2026-10-08 | Early | A2 | 3 | Bracket kit BK-3 | 50 | 105 |  | 30 | 100 | 5 | 0 | 105% | 1 | On target | 340 | 336 | -4 | 2026-10-08 | OK
| 2026-10-08 | Early | A2 | 4 | Bracket kit BK-3 | 60 | 124 |  | 30 | 120 | 4 | 0 | 103.3% | 1 | On target | 460 | 460 | 0 | 2026-10-08 | OK
| 2026-10-08 | Early | A2 | 5 | Bracket kit BK-3 | 30 | 58 | Other | 30 | 60 | -2 | 2 | 96.67% | 0 | Near target | 520 | 518 | -2 | 2026-10-08 | OK
| 2026-10-08 | Early | A2 | 6 | Bracket kit BK-3 | 60 | 120 |  | 30 | 120 | 0 | 0 | 100% | 1 | On target | 640 | 638 | -2 | 2026-10-08 | OK
| 2026-10-08 | Early | A2 | 7 | Bracket kit BK-3 | 50 | 97 | Minor stops | 30 | 100 | -3 | 3 | 97% | 0 | Near target | 740 | 735 | -5 | 2026-10-08 | OK
| 2026-10-08 | Early | A2 | 8 | Bracket kit BK-3 | 50 | 95 | Minor stops | 30 | 100 | -5 | 5 | 95% | 0 | Near target | 840 | 830 | -10 | 2026-10-08 | OK
| 2026-10-08 | Late | A1 | 1 | Valve body VB-12 | 60 | 64 | Start-up | 48 | 75 | -11 | 11 | 85.33% | 0 | Below target | 75 | 64 | -11 | 2026-10-08 | OK | First-piece approval took 15 min
| 2026-10-08 | Late | A1 | 2 | Valve body VB-12 | 60 | 76 |  | 48 | 75 | 1 | 0 | 101.3% | 1 | On target | 150 | 140 | -10 | 2026-10-08 | OK
| 2026-10-08 | Late | A1 | 3 | Valve body VB-12 | 50 | 65 |  | 48 | 62 | 3 | 0 | 104.8% | 1 | On target | 212 | 205 | -7 | 2026-10-08 | OK
| 2026-10-08 | Late | A1 | 4 | Valve body VB-12 | 60 | 75 |  | 48 | 75 | 0 | 0 | 100% | 1 | On target | 287 | 280 | -7 | 2026-10-08 | OK
| 2026-10-08 | Late | A1 | 5 | Valve body VB-12 | 30 | 36 | Minor stops | 48 | 37 | -1 | 1 | 97.3% | 0 | Near target | 324 | 316 | -8 | 2026-10-08 | OK
| 2026-10-08 | Late | A1 | 6 | Valve body VB-12 | 60 | 71 | Operator away | 48 | 75 | -4 | 4 | 94.67% | 0 | Below target | 399 | 387 | -12 | 2026-10-08 | OK
| 2026-10-08 | Late | A1 | 7 | Valve body VB-12 | 50 | 64 |  | 48 | 62 | 2 | 0 | 103.2% | 1 | On target | 461 | 451 | -10 | 2026-10-08 | OK
| 2026-10-08 | Late | A1 | 8 | Valve body VB-12 | 50 | 63 |  | 48 | 62 | 1 | 0 | 101.6% | 1 | On target | 523 | 514 | -9 | 2026-10-08 | OK
| 2026-10-08 | Late | A2 | 1 | Bracket kit BK-3 | 60 | 102 | Start-up | 30 | 120 | -18 | 18 | 85% | 0 | Below target | 120 | 102 | -18 | 2026-10-08 | OK | First-piece approval took 15 min
| 2026-10-08 | Late | A2 | 2 | Bracket kit BK-3 | 60 | 114 | Quality check | 30 | 120 | -6 | 6 | 95% | 0 | Near target | 240 | 216 | -24 | 2026-10-08 | OK
| 2026-10-08 | Late | A2 | 3 | Bracket kit BK-3 | 50 | 52 | Material shortage | 30 | 100 | -48 | 48 | 52% | 0 | Below target | 340 | 268 | -72 | 2026-10-08 | OK | Housings late from goods-in; kanban raised
| 2026-10-08 | Late | A2 | 4 | Bracket kit BK-3 | 60 | 119 | Minor stops | 30 | 120 | -1 | 1 | 99.17% | 0 | Near target | 460 | 387 | -73 | 2026-10-08 | OK
| 2026-10-08 | Late | A2 | 5 | Bracket kit BK-3 | 30 | 60 |  | 30 | 60 | 0 | 0 | 100% | 1 | On target | 520 | 447 | -73 | 2026-10-08 | OK
| 2026-10-08 | Late | A2 | 6 | Bracket kit BK-3 | 60 | 118 | Quality check | 30 | 120 | -2 | 2 | 98.33% | 0 | Near target | 640 | 565 | -75 | 2026-10-08 | OK
| 2026-10-08 | Late | A2 | 7 | Bracket kit BK-3 | 50 | 102 |  | 30 | 100 | 2 | 0 | 102% | 1 | On target | 740 | 667 | -73 | 2026-10-08 | OK
| 2026-10-08 | Late | A2 | 8 | Bracket kit BK-3 | 50 | 96 | Machine fault | 30 | 100 | -4 | 4 | 96% | 0 | Near target | 840 | 763 | -77 | 2026-10-08 | OK | Station 3 press reset
| 2026-10-09 | Early | A1 | 1 | Pump housing PH-40 | 60 | 77 | Start-up | 40 | 90 | -13 | 13 | 85.56% | 0 | Below target | 90 | 77 | -13 | 2026-10-09 | OK | First-piece approval took 15 min
| 2026-10-09 | Early | A1 | 2 | Pump housing PH-40 | 60 | 90 |  | 40 | 90 | 0 | 0 | 100% | 1 | On target | 180 | 167 | -13 | 2026-10-09 | OK
| 2026-10-09 | Early | A1 | 3 | Pump housing PH-40 | 50 | 73 | Minor stops | 40 | 75 | -2 | 2 | 97.33% | 0 | Near target | 255 | 240 | -15 | 2026-10-09 | OK
| 2026-10-09 | Early | A1 | 4 | Pump housing PH-40 | 60 | 93 |  | 40 | 90 | 3 | 0 | 103.3% | 1 | On target | 345 | 333 | -12 | 2026-10-09 | OK
| 2026-10-09 | Early | A1 | 5 | Pump housing PH-40 | 30 | 46 |  | 40 | 45 | 1 | 0 | 102.2% | 1 | On target | 390 | 379 | -11 | 2026-10-09 | OK
| 2026-10-09 | Early | A1 | 6 | Pump housing PH-40 | 60 | 89 | Minor stops | 40 | 90 | -1 | 1 | 98.89% | 0 | Near target | 480 | 468 | -12 | 2026-10-09 | OK
| 2026-10-09 | Early | A1 | 7 | Pump housing PH-40 | 50 | 74 | Minor stops | 40 | 75 | -1 | 1 | 98.67% | 0 | Near target | 555 | 542 | -13 | 2026-10-09 | OK
| 2026-10-09 | Early | A1 | 8 | Pump housing PH-40 | 50 | 79 |  | 40 | 75 | 4 | 0 | 105.3% | 1 | On target | 630 | 621 | -9 | 2026-10-09 | OK
| 2026-10-09 | Early | A2 | 1 | Valve body VB-12 | 60 | 67 | Start-up | 48 | 75 | -8 | 8 | 89.33% | 0 | Below target | 75 | 67 | -8 | 2026-10-09 | OK
| 2026-10-09 | Early | A2 | 2 | Valve body VB-12 | 60 | 79 |  | 48 | 75 | 4 | 0 | 105.3% | 1 | On target | 150 | 146 | -4 | 2026-10-09 | OK
| 2026-10-09 | Early | A2 | 3 | Valve body VB-12 | 50 | 63 |  | 48 | 62 | 1 | 0 | 101.6% | 1 | On target | 212 | 209 | -3 | 2026-10-09 | OK
| 2026-10-09 | Early | A2 | 4 | Valve body VB-12 | 60 | 33 | Material shortage | 48 | 75 | -42 | 42 | 44% | 0 | Below target | 287 | 242 | -45 | 2026-10-09 | OK | Housings late from goods-in; kanban raised
| 2026-10-09 | Early | A2 | 5 | Valve body VB-12 | 30 | 35 | Minor stops | 48 | 37 | -2 | 2 | 94.59% | 0 | Below target | 324 | 277 | -47 | 2026-10-09 | OK
| 2026-10-09 | Early | A2 | 6 | Valve body VB-12 | 60 | 76 |  | 48 | 75 | 1 | 0 | 101.3% | 1 | On target | 399 | 353 | -46 | 2026-10-09 | OK
| 2026-10-09 | Early | A2 | 7 | Valve body VB-12 | 50 | 59 | Quality check | 48 | 62 | -3 | 3 | 95.16% | 0 | Near target | 461 | 412 | -49 | 2026-10-09 | OK
| 2026-10-09 | Early | A2 | 8 | Valve body VB-12 | 50 | 59 | Minor stops | 48 | 62 | -3 | 3 | 95.16% | 0 | Near target | 523 | 471 | -52 | 2026-10-09 | OK
| 2026-10-09 | Late | A1 | 1 | Pump housing PH-40 | 60 | 78 | Start-up | 40 | 90 | -12 | 12 | 86.67% | 0 | Below target | 90 | 78 | -12 | 2026-10-09 | OK
| 2026-10-09 | Late | A1 | 2 | Pump housing PH-40 | 60 | 92 |  | 40 | 90 | 2 | 0 | 102.2% | 1 | On target | 180 | 170 | -10 | 2026-10-09 | OK
| 2026-10-09 | Late | A1 | 3 | Pump housing PH-40 | 50 | 75 |  | 40 | 75 | 0 | 0 | 100% | 1 | On target | 255 | 245 | -10 | 2026-10-09 | OK
| 2026-10-09 | Late | A1 | 4 | Pump housing PH-40 | 60 | 91 |  | 40 | 90 | 1 | 0 | 101.1% | 1 | On target | 345 | 336 | -9 | 2026-10-09 | OK
| 2026-10-09 | Late | A1 | 5 | Pump housing PH-40 | 30 | 47 |  | 40 | 45 | 2 | 0 | 104.4% | 1 | On target | 390 | 383 | -7 | 2026-10-09 | OK
| 2026-10-09 | Late | A1 | 6 | Pump housing PH-40 | 60 | 83 | Quality check | 40 | 90 | -7 | 7 | 92.22% | 0 | Below target | 480 | 466 | -14 | 2026-10-09 | OK
| 2026-10-09 | Late | A1 | 7 | Pump housing PH-40 | 50 | 74 | Minor stops | 40 | 75 | -1 | 1 | 98.67% | 0 | Near target | 555 | 540 | -15 | 2026-10-09 | OK
| 2026-10-09 | Late | A1 | 8 | Pump housing PH-40 | 50 | 74 | Minor stops | 40 | 75 | -1 | 1 | 98.67% | 0 | Near target | 630 | 614 | -16 | 2026-10-09 | OK
| 2026-10-09 | Late | A2 | 1 | Bracket kit BK-3 | 60 | 113 | Start-up | 30 | 120 | -7 | 7 | 94.17% | 0 | Below target | 120 | 113 | -7 | 2026-10-09 | OK
| 2026-10-09 | Late | A2 | 2 | Bracket kit BK-3 | 60 | 126 |  | 30 | 120 | 6 | 0 | 105% | 1 | On target | 240 | 239 | -1 | 2026-10-09 | OK
| 2026-10-09 | Late | A2 | 3 | Bracket kit BK-3 | 50 | 58 | Material shortage | 30 | 100 | -42 | 42 | 58% | 0 | Below target | 340 | 297 | -43 | 2026-10-09 | OK | Housings late from goods-in; kanban raised
| 2026-10-09 | Late | A2 | 4 | Bracket kit BK-3 | 60 | 118 | Minor stops | 30 | 120 | -2 | 2 | 98.33% | 0 | Near target | 460 | 415 | -45 | 2026-10-09 | OK
| 2026-10-09 | Late | A2 | 5 | Bracket kit BK-3 | 30 | 60 |  | 30 | 60 | 0 | 0 | 100% | 1 | On target | 520 | 475 | -45 | 2026-10-09 | OK
| 2026-10-09 | Late | A2 | 6 | Bracket kit BK-3 | 60 | 117 | Minor stops | 30 | 120 | -3 | 3 | 97.5% | 0 | Near target | 640 | 592 | -48 | 2026-10-09 | OK
| 2026-10-09 | Late | A2 | 7 | Bracket kit BK-3 | 50 | 106 |  | 30 | 100 | 6 | 0 | 106% | 1 | On target | 740 | 698 | -42 | 2026-10-09 | OK
| 2026-10-09 | Late | A2 | 8 | Bracket kit BK-3 | 50 | 98 | Minor stops | 30 | 100 | -2 | 2 | 98% | 0 | Near target | 840 | 796 | -44 | 2026-10-09 | OK
| 2026-10-12 | Early | A1 | 1 | Pump housing PH-40 | 60 | 75 | Start-up | 40 | 90 | -15 | 15 | 83.33% | 0 | Below target | 90 | 75 | -15 | 2026-10-12 | OK | First-piece approval took 15 min
| 2026-10-12 | Early | A1 | 2 | Pump housing PH-40 | 60 | 87 | Quality check | 40 | 90 | -3 | 3 | 96.67% | 0 | Near target | 180 | 162 | -18 | 2026-10-12 | OK
| 2026-10-12 | Early | A1 | 3 | Pump housing PH-40 | 50 | 77 |  | 40 | 75 | 2 | 0 | 102.7% | 1 | On target | 255 | 239 | -16 | 2026-10-12 | OK
| 2026-10-12 | Early | A1 | 4 | Pump housing PH-40 | 60 | 92 |  | 40 | 90 | 2 | 0 | 102.2% | 1 | On target | 345 | 331 | -14 | 2026-10-12 | OK
| 2026-10-12 | Early | A1 | 5 | Pump housing PH-40 | 30 | 43 | Minor stops | 40 | 45 | -2 | 2 | 95.56% | 0 | Near target | 390 | 374 | -16 | 2026-10-12 | OK
| 2026-10-12 | Early | A1 | 6 | Pump housing PH-40 | 60 | 81 | Machine fault | 40 | 90 | -9 | 9 | 90% | 0 | Below target | 480 | 455 | -25 | 2026-10-12 | OK | Station 3 press reset
| 2026-10-12 | Early | A1 | 7 | Pump housing PH-40 | 50 | 71 | Minor stops | 40 | 75 | -4 | 4 | 94.67% | 0 | Below target | 555 | 526 | -29 | 2026-10-12 | OK
| 2026-10-12 | Early | A1 | 8 | Pump housing PH-40 | 50 | 76 |  | 40 | 75 | 1 | 0 | 101.3% | 1 | On target | 630 | 602 | -28 | 2026-10-12 | OK
| 2026-10-12 | Early | A2 | 1 | Bracket kit BK-3 | 60 | 98 | Start-up | 30 | 120 | -22 | 22 | 81.67% | 0 | Below target | 120 | 98 | -22 | 2026-10-12 | OK | First-piece approval took 15 min
| 2026-10-12 | Early | A2 | 2 | Bracket kit BK-3 | 60 | 115 | Machine fault | 30 | 120 | -5 | 5 | 95.83% | 0 | Near target | 240 | 213 | -27 | 2026-10-12 | OK | Station 3 press reset
| 2026-10-12 | Early | A2 | 3 | Bracket kit BK-3 | 50 | 103 |  | 30 | 100 | 3 | 0 | 103% | 1 | On target | 340 | 316 | -24 | 2026-10-12 | OK
| 2026-10-12 | Early | A2 | 4 | Bracket kit BK-3 | 60 | 115 | Other | 30 | 120 | -5 | 5 | 95.83% | 0 | Near target | 460 | 431 | -29 | 2026-10-12 | OK
| 2026-10-12 | Early | A2 | 5 | Bracket kit BK-3 | 30 | 62 |  | 30 | 60 | 2 | 0 | 103.3% | 1 | On target | 520 | 493 | -27 | 2026-10-12 | OK
| 2026-10-12 | Early | A2 | 6 | Bracket kit BK-3 | 60 | 119 | Minor stops | 30 | 120 | -1 | 1 | 99.17% | 0 | Near target | 640 | 612 | -28 | 2026-10-12 | OK
| 2026-10-12 | Early | A2 | 7 | Bracket kit BK-3 | 50 | 104 |  | 30 | 100 | 4 | 0 | 104% | 1 | On target | 740 | 716 | -24 | 2026-10-12 | OK
| 2026-10-12 | Early | A2 | 8 | Bracket kit BK-3 | 50 | 104 |  | 30 | 100 | 4 | 0 | 104% | 1 | On target | 840 | 820 | -20 | 2026-10-12 | OK
| 2026-10-12 | Late | A1 | 1 | Pump housing PH-40 | 60 | 83 | Start-up | 40 | 90 | -7 | 7 | 92.22% | 0 | Below target | 90 | 83 | -7 | 2026-10-12 | OK
| 2026-10-12 | Late | A1 | 2 | Pump housing PH-40 | 60 | 87 | Minor stops | 40 | 90 | -3 | 3 | 96.67% | 0 | Near target | 180 | 170 | -10 | 2026-10-12 | OK
| 2026-10-12 | Late | A1 | 3 | Pump housing PH-40 | 50 | 79 |  | 40 | 75 | 4 | 0 | 105.3% | 1 | On target | 255 | 249 | -6 | 2026-10-12 | OK
| 2026-10-12 | Late | A1 | 4 | Pump housing PH-40 | 60 | 89 | Quality check | 40 | 90 | -1 | 1 | 98.89% | 0 | Near target | 345 | 338 | -7 | 2026-10-12 | OK
| 2026-10-12 | Late | A1 | 5 | Pump housing PH-40 | 30 | 45 |  | 40 | 45 | 0 | 0 | 100% | 1 | On target | 390 | 383 | -7 | 2026-10-12 | OK
| 2026-10-12 | Late | A1 | 6 | Pump housing PH-40 | 60 | 88 | Machine fault | 40 | 90 | -2 | 2 | 97.78% | 0 | Near target | 480 | 471 | -9 | 2026-10-12 | OK | Station 3 press reset
| 2026-10-12 | Late | A1 | 7 | Pump housing PH-40 | 50 | 78 |  | 40 | 75 | 3 | 0 | 104% | 1 | On target | 555 | 549 | -6 | 2026-10-12 | OK
| 2026-10-12 | Late | A1 | 8 | Pump housing PH-40 | 50 | 77 |  | 40 | 75 | 2 | 0 | 102.7% | 1 | On target | 630 | 626 | -4 | 2026-10-12 | OK
| 2026-10-12 | Late | A2 | 1 | Bracket kit BK-3 | 60 | 101 | Start-up | 30 | 120 | -19 | 19 | 84.17% | 0 | Below target | 120 | 101 | -19 | 2026-10-12 | OK | First-piece approval took 15 min
| 2026-10-12 | Late | A2 | 2 | Bracket kit BK-3 | 60 | 125 |  | 30 | 120 | 5 | 0 | 104.2% | 1 | On target | 240 | 226 | -14 | 2026-10-12 | OK
| 2026-10-12 | Late | A2 | 3 | Bracket kit BK-3 | 50 | 95 | Machine fault | 30 | 100 | -5 | 5 | 95% | 0 | Near target | 340 | 321 | -19 | 2026-10-12 | OK | Station 3 press reset
| 2026-10-12 | Late | A2 | 4 | Bracket kit BK-3 | 60 | 118 | Quality check | 30 | 120 | -2 | 2 | 98.33% | 0 | Near target | 460 | 439 | -21 | 2026-10-12 | OK
| 2026-10-12 | Late | A2 | 5 | Bracket kit BK-3 | 30 | 63 |  | 30 | 60 | 3 | 0 | 105% | 1 | On target | 520 | 502 | -18 | 2026-10-12 | OK
| 2026-10-12 | Late | A2 | 6 | Bracket kit BK-3 | 60 | 111 | Other | 30 | 120 | -9 | 9 | 92.5% | 0 | Below target | 640 | 613 | -27 | 2026-10-12 | OK
| 2026-10-12 | Late | A2 | 7 | Bracket kit BK-3 | 50 | 104 |  | 30 | 100 | 4 | 0 | 104% | 1 | On target | 740 | 717 | -23 | 2026-10-12 | OK
| 2026-10-12 | Late | A2 | 8 | Bracket kit BK-3 | 50 | 102 |  | 30 | 100 | 2 | 0 | 102% | 1 | On target | 840 | 819 | -21 | 2026-10-12 | OK
| 2026-10-13 | Early | A1 | 1 | Pump housing PH-40 | 60 | 82 | Start-up | 40 | 90 | -8 | 8 | 91.11% | 0 | Below target | 90 | 82 | -8 | 2026-10-13 | OK
| 2026-10-13 | Early | A1 | 2 | Pump housing PH-40 | 60 | 85 | Minor stops | 40 | 90 | -5 | 5 | 94.44% | 0 | Below target | 180 | 167 | -13 | 2026-10-13 | OK
| 2026-10-13 | Early | A1 | 3 | Pump housing PH-40 | 50 | 73 | Minor stops | 40 | 75 | -2 | 2 | 97.33% | 0 | Near target | 255 | 240 | -15 | 2026-10-13 | OK
| 2026-10-13 | Early | A1 | 4 | Pump housing PH-40 | 60 | 90 |  | 40 | 90 | 0 | 0 | 100% | 1 | On target | 345 | 330 | -15 | 2026-10-13 | OK
| 2026-10-13 | Early | A1 | 5 | Pump housing PH-40 | 30 | 44 | Quality check | 40 | 45 | -1 | 1 | 97.78% | 0 | Near target | 390 | 374 | -16 | 2026-10-13 | OK
| 2026-10-13 | Early | A1 | 6 | Pump housing PH-40 | 60 | 81 | Minor stops | 40 | 90 | -9 | 9 | 90% | 0 | Below target | 480 | 455 | -25 | 2026-10-13 | OK
| 2026-10-13 | Early | A1 | 7 | Pump housing PH-40 | 50 | 76 |  | 40 | 75 | 1 | 0 | 101.3% | 1 | On target | 555 | 531 | -24 | 2026-10-13 | OK
| 2026-10-13 | Early | A1 | 8 | Pump housing PH-40 | 50 | 73 | Minor stops | 40 | 75 | -2 | 2 | 97.33% | 0 | Near target | 630 | 604 | -26 | 2026-10-13 | OK
| 2026-10-13 | Early | A2 | 1 | Bracket kit BK-3 | 60 | 110 | Start-up | 30 | 120 | -10 | 10 | 91.67% | 0 | Below target | 120 | 110 | -10 | 2026-10-13 | OK
| 2026-10-13 | Early | A2 | 2 | Bracket kit BK-3 | 60 | 120 |  | 30 | 120 | 0 | 0 | 100% | 1 | On target | 240 | 230 | -10 | 2026-10-13 | OK
| 2026-10-13 | Early | A2 | 3 | Bracket kit BK-3 | 50 | 53 | Material shortage | 30 | 100 | -47 | 47 | 53% | 0 | Below target | 340 | 283 | -57 | 2026-10-13 | OK | Housings late from goods-in; kanban raised
| 2026-10-13 | Early | A2 | 4 | Bracket kit BK-3 | 60 | 125 |  | 30 | 120 | 5 | 0 | 104.2% | 1 | On target | 460 | 408 | -52 | 2026-10-13 | OK
| 2026-10-13 | Early | A2 | 5 | Bracket kit BK-3 | 30 | 61 |  | 30 | 60 | 1 | 0 | 101.7% | 1 | On target | 520 | 469 | -51 | 2026-10-13 | OK
| 2026-10-13 | Early | A2 | 6 | Bracket kit BK-3 | 60 | 117 | Minor stops | 30 | 120 | -3 | 3 | 97.5% | 0 | Near target | 640 | 586 | -54 | 2026-10-13 | OK
| 2026-10-13 | Early | A2 | 7 | Bracket kit BK-3 | 50 | 101 |  | 30 | 100 | 1 | 0 | 101% | 1 | On target | 740 | 687 | -53 | 2026-10-13 | OK
| 2026-10-13 | Early | A2 | 8 | Bracket kit BK-3 | 50 | 99 | Minor stops | 30 | 100 | -1 | 1 | 99% | 0 | Near target | 840 | 786 | -54 | 2026-10-13 | OK
| 2026-10-13 | Late | A1 | 1 | Pump housing PH-40 | 60 | 72 | Start-up | 40 | 90 | -18 | 18 | 80% | 0 | Below target | 90 | 72 | -18 | 2026-10-13 | OK | First-piece approval took 15 min
| 2026-10-13 | Late | A1 | 2 | Pump housing PH-40 | 60 | 85 | Minor stops | 40 | 90 | -5 | 5 | 94.44% | 0 | Below target | 180 | 157 | -23 | 2026-10-13 | OK
| 2026-10-13 | Late | A1 | 3 | Pump housing PH-40 | 50 | 77 |  | 40 | 75 | 2 | 0 | 102.7% | 1 | On target | 255 | 234 | -21 | 2026-10-13 | OK
| 2026-10-13 | Late | A1 | 4 | Pump housing PH-40 | 60 | 89 | Quality check | 40 | 90 | -1 | 1 | 98.89% | 0 | Near target | 345 | 323 | -22 | 2026-10-13 | OK
| 2026-10-13 | Late | A1 | 5 | Pump housing PH-40 | 30 | 43 | Minor stops | 40 | 45 | -2 | 2 | 95.56% | 0 | Near target | 390 | 366 | -24 | 2026-10-13 | OK
| 2026-10-13 | Late | A1 | 6 | Pump housing PH-40 | 60 | 83 | Quality check | 40 | 90 | -7 | 7 | 92.22% | 0 | Below target | 480 | 449 | -31 | 2026-10-13 | OK
| 2026-10-13 | Late | A1 | 7 | Pump housing PH-40 | 50 | 73 | Minor stops | 40 | 75 | -2 | 2 | 97.33% | 0 | Near target | 555 | 522 | -33 | 2026-10-13 | OK
| 2026-10-13 | Late | A1 | 8 | Pump housing PH-40 | 50 | 72 | Quality check | 40 | 75 | -3 | 3 | 96% | 0 | Near target | 630 | 594 | -36 | 2026-10-13 | OK
| 2026-10-13 | Late | A2 | 1 | Bracket kit BK-3 | 60 | 115 | Start-up | 30 | 120 | -5 | 5 | 95.83% | 0 | Near target | 120 | 115 | -5 | 2026-10-13 | OK
| 2026-10-13 | Late | A2 | 2 | Bracket kit BK-3 | 60 | 116 | Minor stops | 30 | 120 | -4 | 4 | 96.67% | 0 | Near target | 240 | 231 | -9 | 2026-10-13 | OK
| 2026-10-13 | Late | A2 | 3 | Bracket kit BK-3 | 50 | 58 | Material shortage | 30 | 100 | -42 | 42 | 58% | 0 | Below target | 340 | 289 | -51 | 2026-10-13 | OK | Housings late from goods-in; kanban raised
| 2026-10-13 | Late | A2 | 4 | Bracket kit BK-3 | 60 | 125 |  | 30 | 120 | 5 | 0 | 104.2% | 1 | On target | 460 | 414 | -46 | 2026-10-13 | OK
| 2026-10-13 | Late | A2 | 5 | Bracket kit BK-3 | 30 | 62 |  | 30 | 60 | 2 | 0 | 103.3% | 1 | On target | 520 | 476 | -44 | 2026-10-13 | OK
| 2026-10-13 | Late | A2 | 6 | Bracket kit BK-3 | 60 | 113 | Minor stops | 30 | 120 | -7 | 7 | 94.17% | 0 | Below target | 640 | 589 | -51 | 2026-10-13 | OK
| 2026-10-13 | Late | A2 | 7 | Bracket kit BK-3 | 50 | 97 | Other | 30 | 100 | -3 | 3 | 97% | 0 | Near target | 740 | 686 | -54 | 2026-10-13 | OK
| 2026-10-13 | Late | A2 | 8 | Bracket kit BK-3 | 50 | 96 | Minor stops | 30 | 100 | -4 | 4 | 96% | 0 | Near target | 840 | 782 | -58 | 2026-10-13 | OK
| 2026-10-14 | Early | A1 | 1 | Valve body VB-12 | 60 | 66 | Start-up | 48 | 75 | -9 | 9 | 88% | 0 | Below target | 75 | 66 | -9 | 2026-10-14 | OK
| 2026-10-14 | Early | A1 | 2 | Valve body VB-12 | 60 | 79 |  | 48 | 75 | 4 | 0 | 105.3% | 1 | On target | 150 | 145 | -5 | 2026-10-14 | OK
| 2026-10-14 | Early | A1 | 3 | Valve body VB-12 | 50 | 61 | Minor stops | 48 | 62 | -1 | 1 | 98.39% | 0 | Near target | 212 | 206 | -6 | 2026-10-14 | OK
| 2026-10-14 | Early | A1 | 4 | Valve body VB-12 | 60 | 76 |  | 48 | 75 | 1 | 0 | 101.3% | 1 | On target | 287 | 282 | -5 | 2026-10-14 | OK
| 2026-10-14 | Early | A1 | 5 | Valve body VB-12 | 30 | 37 |  | 48 | 37 | 0 | 0 | 100% | 1 | On target | 324 | 319 | -5 | 2026-10-14 | OK
| 2026-10-14 | Early | A1 | 6 | Valve body VB-12 | 60 | 70 | Minor stops | 48 | 75 | -5 | 5 | 93.33% | 0 | Below target | 399 | 389 | -10 | 2026-10-14 | OK
| 2026-10-14 | Early | A1 | 7 | Valve body VB-12 | 50 | 61 | Machine fault | 48 | 62 | -1 | 1 | 98.39% | 0 | Near target | 461 | 450 | -11 | 2026-10-14 | OK | Station 3 press reset
| 2026-10-14 | Early | A1 | 8 | Valve body VB-12 | 50 | 64 |  | 48 | 62 | 2 | 0 | 103.2% | 1 | On target | 523 | 514 | -9 | 2026-10-14 | OK
| 2026-10-14 | Early | A2 | 1 | Bracket kit BK-3 | 60 | 102 | Start-up | 30 | 120 | -18 | 18 | 85% | 0 | Below target | 120 | 102 | -18 | 2026-10-14 | OK | First-piece approval took 15 min
| 2026-10-14 | Early | A2 | 2 | Bracket kit BK-3 | 60 | 117 | Operator away | 30 | 120 | -3 | 3 | 97.5% | 0 | Near target | 240 | 219 | -21 | 2026-10-14 | OK
| 2026-10-14 | Early | A2 | 3 | Bracket kit BK-3 | 50 | 101 |  | 30 | 100 | 1 | 0 | 101% | 1 | On target | 340 | 320 | -20 | 2026-10-14 | OK
| 2026-10-14 | Early | A2 | 4 | Bracket kit BK-3 | 60 | 122 |  | 30 | 120 | 2 | 0 | 101.7% | 1 | On target | 460 | 442 | -18 | 2026-10-14 | OK
| 2026-10-14 | Early | A2 | 5 | Bracket kit BK-3 | 30 | 63 |  | 30 | 60 | 3 | 0 | 105% | 1 | On target | 520 | 505 | -15 | 2026-10-14 | OK
| 2026-10-14 | Early | A2 | 6 | Bracket kit BK-3 | 60 | 106 | Operator away | 30 | 120 | -14 | 14 | 88.33% | 0 | Below target | 640 | 611 | -29 | 2026-10-14 | OK
| 2026-10-14 | Early | A2 | 7 | Bracket kit BK-3 | 50 | 95 | Minor stops | 30 | 100 | -5 | 5 | 95% | 0 | Near target | 740 | 706 | -34 | 2026-10-14 | OK
| 2026-10-14 | Early | A2 | 8 | Bracket kit BK-3 | 50 | 95 | Minor stops | 30 | 100 | -5 | 5 | 95% | 0 | Near target | 840 | 801 | -39 | 2026-10-14 | OK
| 2026-10-14 | Late | A1 | 1 | Valve body VB-12 | 60 | 66 | Start-up | 48 | 75 | -9 | 9 | 88% | 0 | Below target | 75 | 66 | -9 | 2026-10-14 | OK
| 2026-10-14 | Late | A1 | 2 | Valve body VB-12 | 60 | 74 | Minor stops | 48 | 75 | -1 | 1 | 98.67% | 0 | Near target | 150 | 140 | -10 | 2026-10-14 | OK
| 2026-10-14 | Late | A1 | 3 | Valve body VB-12 | 50 | 59 | Minor stops | 48 | 62 | -3 | 3 | 95.16% | 0 | Near target | 212 | 199 | -13 | 2026-10-14 | OK
| 2026-10-14 | Late | A1 | 4 | Valve body VB-12 | 60 | 71 | Quality check | 48 | 75 | -4 | 4 | 94.67% | 0 | Below target | 287 | 270 | -17 | 2026-10-14 | OK
| 2026-10-14 | Late | A1 | 5 | Valve body VB-12 | 30 | 37 |  | 48 | 37 | 0 | 0 | 100% | 1 | On target | 324 | 307 | -17 | 2026-10-14 | OK
| 2026-10-14 | Late | A1 | 6 | Valve body VB-12 | 60 | 73 | Operator away | 48 | 75 | -2 | 2 | 97.33% | 0 | Near target | 399 | 380 | -19 | 2026-10-14 | OK
| 2026-10-14 | Late | A1 | 7 | Valve body VB-12 | 50 | 59 | Machine fault | 48 | 62 | -3 | 3 | 95.16% | 0 | Near target | 461 | 439 | -22 | 2026-10-14 | OK | Station 3 press reset
| 2026-10-14 | Late | A1 | 8 | Valve body VB-12 | 50 | 59 | Minor stops | 48 | 62 | -3 | 3 | 95.16% | 0 | Near target | 523 | 498 | -25 | 2026-10-14 | OK
| 2026-10-14 | Late | A2 | 1 | Bracket kit BK-3 | 60 | 101 | Start-up | 30 | 120 | -19 | 19 | 84.17% | 0 | Below target | 120 | 101 | -19 | 2026-10-14 | OK | First-piece approval took 15 min
| 2026-10-14 | Late | A2 | 2 | Bracket kit BK-3 | 60 | 125 |  | 30 | 120 | 5 | 0 | 104.2% | 1 | On target | 240 | 226 | -14 | 2026-10-14 | OK
| 2026-10-14 | Late | A2 | 3 | Bracket kit BK-3 | 50 | 101 |  | 30 | 100 | 1 | 0 | 101% | 1 | On target | 340 | 327 | -13 | 2026-10-14 | OK
| 2026-10-14 | Late | A2 | 4 | Bracket kit BK-3 | 60 | 114 | Operator away | 30 | 120 | -6 | 6 | 95% | 0 | Near target | 460 | 441 | -19 | 2026-10-14 | OK
| 2026-10-14 | Late | A2 | 5 | Bracket kit BK-3 | 30 | 60 |  | 30 | 60 | 0 | 0 | 100% | 1 | On target | 520 | 501 | -19 | 2026-10-14 | OK
| 2026-10-14 | Late | A2 | 6 | Bracket kit BK-3 | 60 | 113 | Minor stops | 30 | 120 | -7 | 7 | 94.17% | 0 | Below target | 640 | 614 | -26 | 2026-10-14 | OK
| 2026-10-14 | Late | A2 | 7 | Bracket kit BK-3 | 50 | 106 |  | 30 | 100 | 6 | 0 | 106% | 1 | On target | 740 | 720 | -20 | 2026-10-14 | OK
| 2026-10-14 | Late | A2 | 8 | Bracket kit BK-3 | 50 | 94 | Minor stops | 30 | 100 | -6 | 6 | 94% | 0 | Below target | 840 | 814 | -26 | 2026-10-14 | OK
| 2026-10-15 | Early | A1 | 1 | Valve body VB-12 | 60 | 65 | Start-up | 48 | 75 | -10 | 10 | 86.67% | 0 | Below target | 75 | 65 | -10 | 2026-10-15 | OK
| 2026-10-15 | Early | A1 | 2 | Valve body VB-12 | 60 | 78 |  | 48 | 75 | 3 | 0 | 104% | 1 | On target | 150 | 143 | -7 | 2026-10-15 | OK
| 2026-10-15 | Early | A1 | 3 | Valve body VB-12 | 50 | 64 |  | 48 | 62 | 2 | 0 | 103.2% | 1 | On target | 212 | 207 | -5 | 2026-10-15 | OK
| 2026-10-15 | Early | A1 | 4 | Valve body VB-12 | 60 | 76 |  | 48 | 75 | 1 | 0 | 101.3% | 1 | On target | 287 | 283 | -4 | 2026-10-15 | OK
| 2026-10-15 | Early | A1 | 5 | Valve body VB-12 | 30 | 35 | Operator away | 48 | 37 | -2 | 2 | 94.59% | 0 | Below target | 324 | 318 | -6 | 2026-10-15 | OK
| 2026-10-15 | Early | A1 | 6 | Valve body VB-12 | 60 | 77 |  | 48 | 75 | 2 | 0 | 102.7% | 1 | On target | 399 | 395 | -4 | 2026-10-15 | OK
| 2026-10-15 | Early | A1 | 7 | Valve body VB-12 | 50 | 62 |  | 48 | 62 | 0 | 0 | 100% | 1 | On target | 461 | 457 | -4 | 2026-10-15 | OK
| 2026-10-15 | Early | A1 | 8 | Valve body VB-12 | 50 | 62 |  | 48 | 62 | 0 | 0 | 100% | 1 | On target | 523 | 519 | -4 | 2026-10-15 | OK
| 2026-10-15 | Early | A2 | 1 | Bracket kit BK-3 | 60 | 114 | Start-up | 30 | 120 | -6 | 6 | 95% | 0 | Near target | 120 | 114 | -6 | 2026-10-15 | OK
| 2026-10-15 | Early | A2 | 2 | Bracket kit BK-3 | 60 | 118 | Other | 30 | 120 | -2 | 2 | 98.33% | 0 | Near target | 240 | 232 | -8 | 2026-10-15 | OK
| 2026-10-15 | Early | A2 | 3 | Bracket kit BK-3 | 50 | 97 | Minor stops | 30 | 100 | -3 | 3 | 97% | 0 | Near target | 340 | 329 | -11 | 2026-10-15 | OK
| 2026-10-15 | Early | A2 | 4 | Bracket kit BK-3 | 60 | 127 |  | 30 | 120 | 7 | 0 | 105.8% | 1 | On target | 460 | 456 | -4 | 2026-10-15 | OK
| 2026-10-15 | Early | A2 | 5 | Bracket kit BK-3 | 30 | 60 |  | 30 | 60 | 0 | 0 | 100% | 1 | On target | 520 | 516 | -4 | 2026-10-15 | OK
| 2026-10-15 | Early | A2 | 6 | Bracket kit BK-3 | 60 | 105 | Operator away | 30 | 120 | -15 | 15 | 87.5% | 0 | Below target | 640 | 621 | -19 | 2026-10-15 | OK
| 2026-10-15 | Early | A2 | 7 | Bracket kit BK-3 | 50 | 99 | Machine fault | 30 | 100 | -1 | 1 | 99% | 0 | Near target | 740 | 720 | -20 | 2026-10-15 | OK | Station 3 press reset
| 2026-10-15 | Early | A2 | 8 | Bracket kit BK-3 | 50 | 104 |  | 30 | 100 | 4 | 0 | 104% | 1 | On target | 840 | 824 | -16 | 2026-10-15 | OK
| 2026-10-15 | Late | A1 | 1 | Pump housing PH-40 | 60 | 78 | Start-up | 40 | 90 | -12 | 12 | 86.67% | 0 | Below target | 90 | 78 | -12 | 2026-10-15 | OK
| 2026-10-15 | Late | A1 | 2 | Pump housing PH-40 | 60 | 93 |  | 40 | 90 | 3 | 0 | 103.3% | 1 | On target | 180 | 171 | -9 | 2026-10-15 | OK
| 2026-10-15 | Late | A1 | 3 | Pump housing PH-40 | 50 | 74 | Quality check | 40 | 75 | -1 | 1 | 98.67% | 0 | Near target | 255 | 245 | -10 | 2026-10-15 | OK
| 2026-10-15 | Late | A1 | 4 | Pump housing PH-40 | 60 | 85 | Minor stops | 40 | 90 | -5 | 5 | 94.44% | 0 | Below target | 345 | 330 | -15 | 2026-10-15 | OK
| 2026-10-15 | Late | A1 | 5 | Pump housing PH-40 | 30 | 47 |  | 40 | 45 | 2 | 0 | 104.4% | 1 | On target | 390 | 377 | -13 | 2026-10-15 | OK
| 2026-10-15 | Late | A1 | 6 | Pump housing PH-40 | 60 | 81 | Minor stops | 40 | 90 | -9 | 9 | 90% | 0 | Below target | 480 | 458 | -22 | 2026-10-15 | OK
| 2026-10-15 | Late | A1 | 7 | Pump housing PH-40 | 50 | 73 | Minor stops | 40 | 75 | -2 | 2 | 97.33% | 0 | Near target | 555 | 531 | -24 | 2026-10-15 | OK
| 2026-10-15 | Late | A1 | 8 | Pump housing PH-40 | 50 | 73 | Machine fault | 40 | 75 | -2 | 2 | 97.33% | 0 | Near target | 630 | 604 | -26 | 2026-10-15 | OK | Station 3 press reset
| 2026-10-15 | Late | A2 | 1 | Valve body VB-12 | 60 | 59 | Start-up | 48 | 75 | -16 | 16 | 78.67% | 0 | Below target | 75 | 59 | -16 | 2026-10-15 | OK | First-piece approval took 15 min
| 2026-10-15 | Late | A2 | 2 | Valve body VB-12 | 60 | 73 | Operator away | 48 | 75 | -2 | 2 | 97.33% | 0 | Near target | 150 | 132 | -18 | 2026-10-15 | OK
| 2026-10-15 | Late | A2 | 3 | Valve body VB-12 | 50 | 60 | Other | 48 | 62 | -2 | 2 | 96.77% | 0 | Near target | 212 | 192 | -20 | 2026-10-15 | OK
| 2026-10-15 | Late | A2 | 4 | Valve body VB-12 | 60 | 35 | Material shortage | 48 | 75 | -40 | 40 | 46.67% | 0 | Below target | 287 | 227 | -60 | 2026-10-15 | OK | Housings late from goods-in; kanban raised
| 2026-10-15 | Late | A2 | 5 | Valve body VB-12 | 30 | 39 |  | 48 | 37 | 2 | 0 | 105.4% | 1 | On target | 324 | 266 | -58 | 2026-10-15 | OK
| 2026-10-15 | Late | A2 | 6 | Valve body VB-12 | 60 | 70 | Operator away | 48 | 75 | -5 | 5 | 93.33% | 0 | Below target | 399 | 336 | -63 | 2026-10-15 | OK
| 2026-10-15 | Late | A2 | 7 | Valve body VB-12 | 50 | 62 |  | 48 | 62 | 0 | 0 | 100% | 1 | On target | 461 | 398 | -63 | 2026-10-15 | OK
| 2026-10-15 | Late | A2 | 8 | Valve body VB-12 | 50 | 65 |  | 48 | 62 | 3 | 0 | 104.8% | 1 | On target | 523 | 463 | -60 | 2026-10-15 | OK
| 2026-10-16 | Early | A1 | 1 | Valve body VB-12 | 60 | 65 | Start-up | 48 | 75 | -10 | 10 | 86.67% | 0 | Below target | 75 | 65 | -10 | 2026-10-16 | OK
| 2026-10-16 | Early | A1 | 2 | Valve body VB-12 | 60 | 75 |  | 48 | 75 | 0 | 0 | 100% | 1 | On target | 150 | 140 | -10 | 2026-10-16 | OK
| 2026-10-16 | Early | A1 | 3 | Valve body VB-12 | 50 | 61 | Quality check | 48 | 62 | -1 | 1 | 98.39% | 0 | Near target | 212 | 201 | -11 | 2026-10-16 | OK
| 2026-10-16 | Early | A1 | 4 | Valve body VB-12 | 60 | 74 | Quality check | 48 | 75 | -1 | 1 | 98.67% | 0 | Near target | 287 | 275 | -12 | 2026-10-16 | OK
| 2026-10-16 | Early | A1 | 5 | Valve body VB-12 | 30 | 37 |  | 48 | 37 | 0 | 0 | 100% | 1 | On target | 324 | 312 | -12 | 2026-10-16 | OK
| 2026-10-16 | Early | A1 | 6 | Valve body VB-12 | 60 | 69 | Minor stops | 48 | 75 | -6 | 6 | 92% | 0 | Below target | 399 | 381 | -18 | 2026-10-16 | OK
| 2026-10-16 | Early | A1 | 7 | Valve body VB-12 | 50 | 62 |  | 48 | 62 | 0 | 0 | 100% | 1 | On target | 461 | 443 | -18 | 2026-10-16 | OK
| 2026-10-16 | Early | A1 | 8 | Valve body VB-12 | 50 | 62 |  | 48 | 62 | 0 | 0 | 100% | 1 | On target | 523 | 505 | -18 | 2026-10-16 | OK
| 2026-10-16 | Early | A2 | 1 | Bracket kit BK-3 | 60 | 104 | Start-up | 30 | 120 | -16 | 16 | 86.67% | 0 | Below target | 120 | 104 | -16 | 2026-10-16 | OK
| 2026-10-16 | Early | A2 | 2 | Bracket kit BK-3 | 60 | 127 |  | 30 | 120 | 7 | 0 | 105.8% | 1 | On target | 240 | 231 | -9 | 2026-10-16 | OK
| 2026-10-16 | Early | A2 | 3 | Bracket kit BK-3 | 50 | 51 | Material shortage | 30 | 100 | -49 | 49 | 51% | 0 | Below target | 340 | 282 | -58 | 2026-10-16 | OK | Housings late from goods-in; kanban raised
| 2026-10-16 | Early | A2 | 4 | Bracket kit BK-3 | 60 | 125 |  | 30 | 120 | 5 | 0 | 104.2% | 1 | On target | 460 | 407 | -53 | 2026-10-16 | OK
| 2026-10-16 | Early | A2 | 5 | Bracket kit BK-3 | 30 | 61 |  | 30 | 60 | 1 | 0 | 101.7% | 1 | On target | 520 | 468 | -52 | 2026-10-16 | OK
| 2026-10-16 | Early | A2 | 6 | Bracket kit BK-3 | 60 | 114 | Minor stops | 30 | 120 | -6 | 6 | 95% | 0 | Near target | 640 | 582 | -58 | 2026-10-16 | OK
| 2026-10-16 | Early | A2 | 7 | Bracket kit BK-3 | 50 | 102 |  | 30 | 100 | 2 | 0 | 102% | 1 | On target | 740 | 684 | -56 | 2026-10-16 | OK
| 2026-10-16 | Early | A2 | 8 | Bracket kit BK-3 | 50 | 103 |  | 30 | 100 | 3 | 0 | 103% | 1 | On target | 840 | 787 | -53 | 2026-10-16 | OK
| 2026-10-16 | Late | A1 | 1 | Valve body VB-12 | 60 | 66 | Start-up | 48 | 75 | -9 | 9 | 88% | 0 | Below target | 75 | 66 | -9 | 2026-10-16 | OK
| 2026-10-16 | Late | A1 | 2 | Valve body VB-12 | 60 | 77 |  | 48 | 75 | 2 | 0 | 102.7% | 1 | On target | 150 | 143 | -7 | 2026-10-16 | OK
| 2026-10-16 | Late | A1 | 3 | Valve body VB-12 | 50 | 64 |  | 48 | 62 | 2 | 0 | 103.2% | 1 | On target | 212 | 207 | -5 | 2026-10-16 | OK
| 2026-10-16 | Late | A1 | 4 | Valve body VB-12 | 60 | 72 | Quality check | 48 | 75 | -3 | 3 | 96% | 0 | Near target | 287 | 279 | -8 | 2026-10-16 | OK
| 2026-10-16 | Late | A1 | 5 | Valve body VB-12 | 30 | 35 | Minor stops | 48 | 37 | -2 | 2 | 94.59% | 0 | Below target | 324 | 314 | -10 | 2026-10-16 | OK
| 2026-10-16 | Late | A1 | 6 | Valve body VB-12 | 60 | 69 | Quality check | 48 | 75 | -6 | 6 | 92% | 0 | Below target | 399 | 383 | -16 | 2026-10-16 | OK
| 2026-10-16 | Late | A1 | 7 | Valve body VB-12 | 50 | 61 | Quality check | 48 | 62 | -1 | 1 | 98.39% | 0 | Near target | 461 | 444 | -17 | 2026-10-16 | OK
| 2026-10-16 | Late | A1 | 8 | Valve body VB-12 | 50 | 63 |  | 48 | 62 | 1 | 0 | 101.6% | 1 | On target | 523 | 507 | -16 | 2026-10-16 | OK
| 2026-10-16 | Late | A2 | 1 | Bracket kit BK-3 | 60 | 105 | Start-up | 30 | 120 | -15 | 15 | 87.5% | 0 | Below target | 120 | 105 | -15 | 2026-10-16 | OK
| 2026-10-16 | Late | A2 | 2 | Bracket kit BK-3 | 60 | 118 | Minor stops | 30 | 120 | -2 | 2 | 98.33% | 0 | Near target | 240 | 223 | -17 | 2026-10-16 | OK
| 2026-10-16 | Late | A2 | 3 | Bracket kit BK-3 | 50 | 106 |  | 30 | 100 | 6 | 0 | 106% | 1 | On target | 340 | 329 | -11 | 2026-10-16 | OK
| 2026-10-16 | Late | A2 | 4 | Bracket kit BK-3 | 60 | 121 |  | 30 | 120 | 1 | 0 | 100.8% | 1 | On target | 460 | 450 | -10 | 2026-10-16 | OK
| 2026-10-16 | Late | A2 | 5 | Bracket kit BK-3 | 30 | 60 |  | 30 | 60 | 0 | 0 | 100% | 1 | On target | 520 | 510 | -10 | 2026-10-16 | OK
| 2026-10-16 | Late | A2 | 6 | Bracket kit BK-3 | 60 | 111 | Quality check | 30 | 120 | -9 | 9 | 92.5% | 0 | Below target | 640 | 621 | -19 | 2026-10-16 | OK
| 2026-10-16 | Late | A2 | 7 | Bracket kit BK-3 | 50 | 97 | Other | 30 | 100 | -3 | 3 | 97% | 0 | Near target | 740 | 718 | -22 | 2026-10-16 | OK
| 2026-10-16 | Late | A2 | 8 | Bracket kit BK-3 | 50 | 103 |  | 30 | 100 | 3 | 0 | 103% | 1 | On target | 840 | 821 | -19 | 2026-10-16 | OK
Formulas:
View date = IF(tblBoard[[#This Row],[Date]]="","",IF(AND(tblBoard[[#This Row],[Date]]>=FFrom,tblBoard[[#This Row],[Date]]<=FTo,OR(DashLine="",tblBoard[[#This Row],[Line]]=DashLine)),tblBoard[[#This Row],[Date]],""))

## Daily Board
Hour-by-Hour Production Board
| One shift's hour-by-hour board for one line, to print and hang by the line or review at the shift handover. | [12 empty] | mfgcalcs.com
| HOUR-BY-HOUR PRODUCTION BOARD | [10 empty] | Calder Pump Assembly (example)
| Date |  | 2026-10-16 |  |  | Shift |  | Early |  |  |  | Line | A2
8 hours logged. Target per hour = available minutes x 60 / takt, rounded down; running totals from hour 1.
| SHIFT ATTAINMENT |  |  |  | UNITS MADE |  |  |  |  | HOURS ON TARGET |  |  | UNITS SHORT
| 93.69% |  |  |  | 787 |  |  |  |  | 62.5% |  |  | 71
| 100% |  |  |  | Target at takt: 840 |  |  |  |  | 5 of 8 hours |  |  | Sum of each missed hour's shortfall
Below target
Hour by hour
| Hour | Starts | Product | Available (min) | Target | Actual | Gap | Cum. target | Cum. actual | Cum. gap | Attainment | Miss reason | Countermeasure
| 1 | 6:00 | Bracket kit BK-3 | 60 | 120 | 104 | -16 | 120 | 104 | -16 | 86.67% | Start-up
| 2 | 7:00 | Bracket kit BK-3 | 60 | 120 | 127 | 7 | 240 | 231 | -9 | 105.8%
| 3 | 8:00 | Bracket kit BK-3 | 50 | 100 | 51 | -49 | 340 | 282 | -58 | 51% | Material shortage | Housings late from goods-in; kanban raised
| 4 | 9:00 | Bracket kit BK-3 | 60 | 120 | 125 | 5 | 460 | 407 | -53 | 104.2%
| 5 | 10:00 | Bracket kit BK-3 | 30 | 60 | 61 | 1 | 520 | 468 | -52 | 101.7%
| 6 | 11:00 | Bracket kit BK-3 | 60 | 120 | 114 | -6 | 640 | 582 | -58 | 95% | Minor stops
| 7 | 12:00 | Bracket kit BK-3 | 50 | 100 | 102 | 2 | 740 | 684 | -56 | 102%
| 8 | 13:00 | Bracket kit BK-3 | 50 | 100 | 103 | 3 | 840 | 787 | -53 | 103%
Team leader (name, signature)
Shift supervisor (name, signature)
Handover to the next shift

## Dashboard
Hour-by-Hour Production Board
| Hourly attainment against takt, where in the shift the units are lost, and why, for the line and dates you choose. | [7 empty] | mfgcalcs.com
| Line |  |  |  | From |  |  | To
Calder Pump Assembly (example): 320 line-hours in view. Leave the filters blank to include everything; dates are inclusive.
| ATTAINMENT |  | HOURS ON TARGET |  |  | UNITS SHORT |  | WEAKEST HOUR OF THE SHIFT
| 95.61% |  | 41.56% |  |  | 1474 |  | Hour 1
| 100% |  | Share of logged hours that reached the target |  |  | Sum of each missed hour's shortfall |  | Lowest attainment, see the hour chart
Near target
| UNITS MADE |  | UNITS AT TAKT |  |  | HOURS LOGGED |  | BIGGEST MISS REASON
| 26079 |  | 27276 |  |  | 320 |  | Material shortage
| Good units in view |  | Sum of the hourly targets |  |  | Line-hours with a target |  | Ranked by units short, see the Pareto
By hour of the shift
| Hour of shift | Target (units) | Actual (units) | Short (units) | Attainment | Hours on target | Attainment target
| 1 | 3900 | 3421 | 479 | 87.72% | 0% | 100%
| 2 | 3900 | 3836 | 121 | 98.36% | 50% | 100%
| 3 | 3244 | 2972 | 322 | 91.62% | 47.5% | 100%
| 4 | 3900 | 3805 | 139 | 97.56% | 47.5% | 100%
| 5 | 1944 | 1948 | 22 | 100.2% | 67.5% | 100%
| 6 | 3900 | 3650 | 255 | 93.59% | 12.5% | 100%
| 7 | 3244 | 3211 | 83 | 98.98% | 50% | 100%
| 8 | 3244 | 3236 | 53 | 99.75% | 57.5% | 100%
Daily summary (last 10 production days in view)
| Date | Target (units) | Actual (units) | Short (units) | Attainment | Attainment target
| 2026-10-05 | 2940 | 2745 | 224 | 93.37% | 100%
| 2026-10-06 | 2833 | 2707 | 152 | 95.55% | 100%
| 2026-10-07 | 2306 | 2213 | 115 | 95.97% | 100%
| 2026-10-08 | 2726 | 2622 | 128 | 96.18% | 100%
| 2026-10-09 | 2623 | 2502 | 152 | 95.39% | 100%
| 2026-10-12 | 2940 | 2867 | 114 | 97.52% | 100%
| 2026-10-13 | 2940 | 2766 | 191 | 94.08% | 100%
| 2026-10-14 | 2726 | 2627 | 124 | 96.37% | 100%
| 2026-10-15 | 2516 | 2410 | 135 | 95.79% | 100%
| 2026-10-16 | 2726 | 2620 | 139 | 96.11% | 100%
| By line |  |  |  |  | Units short by miss reason (Pareto)
| Line | Target | Actual | Attain. | Hrs on tgt | Rank | Miss reason | Units short | Share | Cumulative | Helper: Miss reason (list order) | Helper: value (-1 = unused slot) | Helper: rank, ties by list order
| A1 | 11744 | 11422 | 97.26% | 41.25% |  |  | units | % | %
| A2 | 15532 | 14657 | 94.37% | 41.88% | 1 | Material shortage | 546 | 37.04% | 37.04% | Start-up | 479 | 2
[6 empty] | 2 | Start-up | 479 | 32.5% | 69.54% | Material shortage | 546 | 1
[6 empty] | 3 | Minor stops | 224 | 15.2% | 84.74% | Minor stops | 224 | 3
[6 empty] | 4 | Quality check | 83 | 5.631% | 90.37% | Machine fault | 51 | 6
[6 empty] | 5 | Operator away | 65 | 4.41% | 94.78% | Quality check | 83 | 4
[6 empty] | 6 | Machine fault | 51 | 3.46% | 98.24% | Changeover | 0 | 8
[6 empty] | 7 | Other | 26 | 1.764% | 100% | Operator away | 65 | 5
[6 empty] | 8 | Changeover | 0 | 0% | 100% | Other | 26 | 7
[7 empty] | Total | 1474
The Dashboard shows the 2 lines, 8 hour slots and 8 miss reasons of the Setup lists. If you add more, extend the 'By line', 'By hour of the shift' and Pareto blocks (see Method) or they will not appear here.
Formulas:
Line = IF(B65="","",IFERROR(LARGE(tblBoard[View date],COUNTIF(tblBoard[View date],">="&B65)+1),""))
Line = IF(COUNT(tblBoard[View date])=0,"",MAX(tblBoard[View date]))

## Method
Hour-by-Hour Production Board
| How every number is calculated, with assumptions, limits and sources. |  | mfgcalcs.com
What this workbook calculates
One row per line per hour holds the minutes the line was planned to run in that hour and the good units it made. The product's takt time turns the minutes into the hour's target, so every hour is judged against the pace customer demand requires, not against a rate someone typed. Running totals show how far ahead or behind the shift is, and the miss reason on every short hour feeds the Pareto. Every roll-up adds the quantities first and divides last, so a 30-minute lunch hour weighs half as much as a full hour.
Calculations
| Quantity | How it is calculated | Units
| Takt time | Looked up from the Products list on Setup by product (INDEX/MATCH): available time / customer demand, in seconds per unit. | s/unit
| Target | INT(available minutes x 60 / takt): the whole units the hour should make at takt. | units
| Gap | Actual - target. Negative is units short. | units
| Short | MAX(0, target - actual): the hour's shortfall, never negative. | units
| Attainment | Actual / target. Over several rows: sum of actual / sum of target. | %
| Hit | 1 when actual >= target x the hourly attainment target on Setup, else 0. Hours on target = sum of hits / hours with a target. | -
| Hour status | On target at or above the attainment target, Near target within 5% below it, Below target otherwise. | -
| Cumulative target and actual | SUMIFS of target and actual over the rows with the same date, shift and line and an hour up to this row's hour. | units
| Pareto | Units short summed by miss reason, ranked by COUNTIF ranks with share and cumulative share. Hidden helper columns AO:AQ hold the unsorted values and ranks. | units, %
| Dashboard roll-ups | SUMIFS over the Hourly Board restricted to rows whose View date is filled in (inside the line and date filters). | -
| Daily Board | For the date, shift and line chosen on that sheet: SUMIFS of minutes, target and actual per hour and up to each hour; product, miss reason and countermeasure by INDEX at the matching row (SUMPRODUCT finds its position). Starts = the shift's start time on Setup + (hour - 1) / 24. | units, %
Assumptions
| • | One product per line per hour. If a line changes product inside an hour, split the hour into two rows with their own minutes; the Check column will flag the duplicate hour, which you can then read as intended.
| • | Actual counts good units completed in the hour; scrap and rework are not counted.
| • | Available minutes are planned running time: breaks, meetings and planned clean-down come off, unplanned stops do not.
| • | Takt time is set per product. If demand changes, update the takt on Setup; past rows keep the targets they were logged against only if you copy them as values first.
Limitations
| • | The target is rounded down to whole units, so a 50-minute hour at a 48-second takt is 62 units, not 62.5.
| • | Only one miss reason per hour, so the Pareto attributes each hour's whole shortfall to one reason.
| • | When an hour is split into two rows, the Daily Board adds their minutes and units but shows the product, reason and countermeasure of the later row.
| • | The Dashboard has fixed blocks for the number of lines, hour slots and reasons in the example lists; longer lists need the blocks extended (a warning appears on the Dashboard).
| • | The daily block shows the last 10 production days inside the filters.
Agreement with the live calculator
Takt time here is the live Takt Time calculator's number: available time x 60 / customer demand. For the calculator's example (a 480-minute shift with 45 minutes of breaks and planned stops and 950 units of demand) takt is 27.47 seconds and the required rate is 131.0 units an hour, so a full 60-minute hour on this board has a target of 131 units; both numbers are checked against the calculator's engine on every build. The calculator gives the pace; this workbook holds each hour to it and keeps the record.
Open the Takt Time Calculator
Self-check
The Verify sheet holds fixed test inputs. Its formulas are the same formula text as the working sheets, placed against those inputs, and each result is compared with a value computed independently by the template's Python reference implementation when the file was built. If you edit a formula on a working sheet, the Verify sheet still tests the original formula text, so it will not detect your change.
Sources and standards
| • | Lean Enterprise Institute, Lean Lexicon, 5th edition, 2014 (takt time; production analysis board).
| • | Rother, M. and Shook, J., Learning to See, Lean Enterprise Institute, 1999 (takt time from available time and customer demand).
| • | MFG Calcs Takt Time calculator (takt-time): available time x 60 / customer demand.
Standards are cited by name so you can look them up; no copyrighted standard text or tables are reproduced. Statistical constants used are public.
Version history
| Version | Change | Date
| 1.0.0 | First release. | 24 October 2026
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Verify
Hour-by-Hour Production Board
| Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference. | [19 empty] | mfgcalcs.com
| Self-check status |  | PASS |  | 22 of 22 checks pass
This sheet recomputes the workbook's own formulas on fixed test inputs and compares each result with a value computed independently by the template's Python reference implementation when the file was built. Every row should read PASS. The test inputs are fixed and do not change when you edit Setup or the working sheets.
Checks
| No. | Check |  |  |  | Expected (reference) | Workbook result | Difference | Tolerance | Result
| 1 | Row 1 (calculator example, short hour): target |  |  |  | 131 | 131 | 0 | 1e-09 | PASS
| 2 | Row 1 (calculator example, short hour): gap |  |  |  | -6 | -6 | 0 | 1e-09 | PASS
| 3 | Row 1 (calculator example, short hour): attainment |  |  |  | 95.42% | 95.42% | 0 | 1e-09 | PASS
| 4 | Row 2 (50-minute hour, above target): target |  |  |  | 109 | 109 | 0 | 1e-09 | PASS
| 5 | Row 2 (50-minute hour, above target): gap |  |  |  | 3 | 3 | 0 | 1e-09 | PASS
| 6 | Row 2 (50-minute hour, above target): attainment |  |  |  | 102.8% | 102.8% | 0 | 1e-09 | PASS
| 7 | Row 3 (short hour, no reason): target |  |  |  | 131 | 131 | 0 | 1e-09 | PASS
| 8 | Row 3 (short hour, no reason): gap |  |  |  | -31 | -31 | 0 | 1e-09 | PASS
| 9 | Row 3 (short hour, no reason): attainment |  |  |  | 76.34% | 76.34% | 0 | 1e-09 | PASS
| 10 | Row 4 (line B, half hour): target |  |  |  | 30 | 30 | 0 | 1e-09 | PASS
| 11 | Row 4 (line B, half hour): gap |  |  |  | 0 | 0 | 0 | 1e-09 | PASS
| 12 | Row 4 (line B, half hour): attainment |  |  |  | 100% | 100% | 0 | 1e-09 | PASS
| 13 | Row 1: status (95.4% against 100%) |  |  |  | Near target | Near target |  | exact | PASS
| 14 | Row 2: status (above target) |  |  |  | On target | On target |  | exact | PASS
| 15 | Row 2: cumulative target (hours 1-2) |  |  |  | 240 | 240 | 0 | 1e-09 | PASS
| 16 | Row 2: cumulative actual (hours 1-2) |  |  |  | 237 | 237 | 0 | 1e-09 | PASS
| 17 | Row 3: cumulative gap (hours 1-3) |  |  |  | -34 | -34 | 0 | 1e-09 | PASS
| 18 | Row 3: Check asks for the miss reason |  |  |  | Give the miss reason | Give the miss reason |  | exact | PASS
| 19 | Row 4: running total restarts for line B |  |  |  | 30 | 30 | 0 | 1e-09 | PASS
| 20 | All rows: attainment (Dashboard formula) |  |  |  | 91.52% | 91.52% | 0 | 1e-09 | PASS
| 21 | All rows: hours on target (Dashboard formula) |  |  |  | 50% | 50% | 0 | 1e-09 | PASS
| 22 | All rows: units short (Dashboard formula) |  |  |  | 37 | 37 | 0 | 1e-09 | PASS
Fixed test inputs
White cells are fixed test inputs; blue cells are the workbook's formulas evaluated on them.
Parameters
| Filter: from (0 = no limit) |  |  | 0
| Filter: to (2958465 = no limit) |  |  | 2958465
Filter: line (blank = all)
| Hourly attainment target |  |  | 100%
Test table: Board
| Date | Shift | Line | Hour | Product | Available (min) | Actual (units) | Miss reason | Takt (s) | Target (units) | Gap (units) | Short (units) | Attainment | Hit | Hour status | Cum. target | Cum. actual | Cum. gap | View date | Check | Countermeasure
| 2026-01-05 | S1 | A | 1 | P1 | 60 | 125 | R1 | 27.4737 | 131 | -6 | 6 | 95.42% | 0 | Near target | 131 | 125 | -6 | 2026-01-05 | OK
| 2026-01-05 | S1 | A | 2 | P1 | 50 | 112 |  | 27.4737 | 109 | 3 | 0 | 102.8% | 1 | On target | 240 | 237 | -3 | 2026-01-05 | OK
| 2026-01-05 | S1 | A | 3 | P1 | 60 | 100 |  | 27.4737 | 131 | -31 | 31 | 76.34% | 0 | Below target | 371 | 337 | -34 | 2026-01-05 | Give the miss reason
| 2026-01-05 | S1 | B | 1 | P2 | 30 | 30 |  | 60 | 30 | 0 | 0 | 100% | 1 | On target | 30 | 30 | 0 | 2026-01-05 | OK
Formulas:
View date = IF(tblVerifyBoard[[#This Row],[Date]]="","",IF(AND(tblVerifyBoard[[#This Row],[Date]]>=E38,tblVerifyBoard[[#This Row],[Date]]<=E39,OR(E40="",tblVerifyBoard[[#This Row],[Line]]=E40)),tblVerifyBoard[[#This Row],[Date]],""))