## Start Here
ISO 9001 Internal Audit Planner
| Read this first: what the workbook does and how to use it. |  |  |  | mfgcalcs.com
ISO 9001 Internal Audit Planner
Plan the internal audit programme, record each audit's checklist and findings, and see completion, conformance by clause and overdue corrective actions.
For: Quality managers, management representatives and internal auditors running an ISO 9001 (or IATF 16949, AS9100, ISO 13485) internal audit programme.
Version 1.0.0 · updated 15 October 2026
Quick start
| 1. | On Setup, set the status date, your targets and the time per question, then replace the example processes (with owners), auditors and finding grades.
| 2. | On Audit Programme, list the year's audits: process, lead auditor, planned date and the number of questions planned.
| 3. | During each audit, add a row per question on Audit Checklist: clause, question, evidence seen and the result; give each finding an owner.
| 4. | Mark the audit Done with its actual date, and type the closed date when each finding's action is verified.
| 5. | Move the status date forward and open the Dashboard for completion, conformance by clause and overdue actions.
What is in this workbook
|  | Start Here | Read this first: what the workbook does and how to use it.
|  | Setup | Status date, targets, time standard, and the process, auditor, finding grade and clause lists.
|  | Audit Programme | One row per planned audit: process, lead auditor, dates and status. Questions, findings and hours are calculated.
|  | Audit Checklist | One row per question asked: clause, question, evidence and result. Findings carry an owner, a due date and a closed date.
|  | Dashboard | Programme completion, conformance by clause, findings by process and the corrective actions still open.
|  | Method | How every number is calculated, with assumptions, limits and sources.
|  | Verify | Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference.
Colour key
|  | Input | Yellow cells are yours: type a value or pick from the list. Each one says what it accepts when you click it.
|  | Calculated | Blue cells are formulas. They update as you type; overwrite one and that row stops calculating.
|  | Note | Grey boxes are guidance and labelled example data.
|  | Status words | On target / PASS / OK | Near target / Check | Below target / FAIL
Status is always written in words; the colour only repeats it, so the workbook reads the same in black-and-white print and for colour-blind readers.
Self-check and links
|  | Self-check | PASS | 19 of 19 checks pass
The Verify sheet recomputes this workbook's formulas on fixed test inputs and compares them with an independent reference calculation. PASS means every check agreed when you opened the file.
|  | Run it live | Internal Audit Planning Time Calculator on mfgcalcs.com
|  | Latest version | mfgcalcs.com/templates/internal-audit-checklist
|  | More free templates | mfgcalcs.com/templates
|  | Version | 1.0.0 (updated 15 October 2026)
About the example data
Every number already in this workbook is example data for Wexford Components, a fictional business invented for this template, so the dashboard and charts show something meaningful on day one. It covers ten processes and fourteen audits planned for 2026, with checklists and findings for the audits done by the status date (9 October 2026), generated from a fixed seed. To clear it: on each working sheet, select the example rows of the table, right-click and choose Delete > Table Rows. The formulas stay, and every new row you type below the table picks them up.
Good to know
| • | Sheets Start Here, Dashboard, Method, Verify are protected without a password so formulas and layout are not overwritten by accident. To change them: Review > Unprotect Sheet.
| • | Setup and the working sheets are not protected, so tables grow as you add rows.
| • | Works in Excel 2016 and later, Microsoft 365, LibreOffice 24 and Google Sheets (File > Import). No macros, no external links, no add-ins.
| • | Money is shown in the currency you type on Setup; no exchange rates are applied.
Free from MFG Calcs - keep this credit when you share it.
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Setup
ISO 9001 Internal Audit Planner
| Status date, targets, time standard, and the process, auditor, finding grade and clause lists. |  | mfgcalcs.com
Site and status date
| Company or site name | Wexford Components (example)
| Status date (as of) | 2026-10-09
| Due soon window | 14 | days
| Programme completion target | 90%
| Findings closed target | 80%
Audit time standard (your own estimate)
| Minutes per checklist question | 5 | min per question
| Overhead and delay allowance | 10%
Targets and the time standard are yours to set. Estimated audit hours = questions x minutes per question / 60 x (1 + allowance), the Internal Audit Planning Time calculator's formula (5 minutes per question = 0.2 questions per minute).
Lists that feed the dropdowns
Edit, add or remove rows; the programme and checklist dropdowns read these lists. Give each process its owner: the programme's Check column flags an auditor who owns the process audited. Grades set the days allowed to respond to a finding. Clause sections follow ISO 9001:2015 clause numbers (titles shortened, text not reproduced).
Processes (the audit universe)
| Process | Owner | Main clauses
| Management and planning | J. Ellis | 4, 5, 6, 9.3
| Sales and contract review | M. Ruiz | 8.2
| Design and development | T. Mensah | 8.3
| Purchasing and suppliers | D. Shah | 8.4
| Production | K. Varga | 8.1, 8.5, 8.6
| Inspection and testing | L. Okoro | 8.6, 8.7
| Calibration | L. Okoro | 7.1.5
| Warehouse and shipping | S. Byrne | 8.5.4, 8.5.5
| People and training | A. Novak | 7.1.2, 7.2, 7.3
| Improvement and CAPA | P. Grant | 9.1, 10
Internal auditors
| Auditor | Notes
| P. Grant | Lead auditor, quality
| T. Mensah | Engineering
| K. Varga | Production planning
| D. Shah | Purchasing
Finding grades and response times
| Grade | Response (days) | Meaning
| Major NC | 30 | A requirement not met in a way that puts product or the system at risk
| Minor NC | 60 | A single lapse against a requirement
| OFI | 90 | Opportunity for improvement; no requirement broken
Clause sections (ISO 9001:2015)
Clause
4 Context
5 Leadership
6 Planning
7 Support
8 Operation
9 Evaluation
10 Improvement

## Audit Programme
ISO 9001 Internal Audit Planner
| One row per planned audit: process, lead auditor, dates and status. Questions, findings and hours are calculated. | [14 empty] | mfgcalcs.com
Example data for Wexford Components (fictional). Replace it with your own: select the example rows, right-click, Delete > Table Rows (do the same on Audit Checklist). Yellow = you type; blue = calculated; Check names any problem. Due status is measured to the status date on Setup.
| Audit no. | Process | Lead auditor | Planned date | Actual date | Status | Questions planned | Process owner | Questions asked | Major NC | Minor NC | OFI | Est. hours | Due status | Check | Notes
| IA-26-01 | Management and planning | T. Mensah | 2026-01-20 | 2026-01-20 | Done | 7 | J. Ellis | 7 | 0 | 1 | 1 | 0.64167 | Complete | OK
| IA-26-02 | Purchasing and suppliers | P. Grant | 2026-02-17 | 2026-02-18 | Done | 6 | D. Shah | 6 | 0 | 1 | 1 | 0.55 | Complete | OK
| IA-26-03 | Production | D. Shah | 2026-03-10 | 2026-03-10 | Done | 8 | K. Varga | 8 | 0 | 1 | 1 | 0.73333 | Complete | OK
| IA-26-04 | Calibration | K. Varga | 2026-04-14 | 2026-04-14 | Done | 5 | L. Okoro | 5 | 1 | 1 | 0 | 0.45833 | Complete | OK
| IA-26-05 | Sales and contract review | D. Shah | 2026-05-12 | 2026-05-19 | Done | 6 | M. Ruiz | 6 | 0 | 0 | 1 | 0.55 | Complete | OK | Moved one week at the sales manager's request
| IA-26-06 | Inspection and testing | T. Mensah | 2026-06-09 | 2026-06-09 | Done | 6 | L. Okoro | 6 | 0 | 1 | 1 | 0.55 | Complete | OK
| IA-26-07 | Design and development | P. Grant | 2026-07-07 | 2026-07-08 | Done | 6 | T. Mensah | 6 | 0 | 1 | 0 | 0.55 | Complete | OK
| IA-26-08 | People and training | K. Varga | 2026-08-11 | 2026-08-11 | Done | 5 | A. Novak | 5 | 0 | 1 | 0 | 0.45833 | Complete | OK
| IA-26-09 | Warehouse and shipping | T. Mensah | 2026-09-08 | 2026-09-09 | Done | 5 | S. Byrne | 5 | 0 | 0 | 1 | 0.45833 | Complete | OK
| IA-26-10 | Improvement and CAPA | D. Shah | 2026-09-22 |  | Postponed | 6 | P. Grant | 0 | 0 | 0 | 0 | 0.55 | Overdue | OK | Postponed: CAPA owner on leave; new date to be agreed
| IA-26-11 | Production | P. Grant | 2026-10-20 |  | Planned | 8 | K. Varga | 0 | 0 | 0 | 0 | 0.73333 | Due soon | OK
| IA-26-12 | Calibration | D. Shah | 2026-11-10 |  | Planned | 5 | L. Okoro | 0 | 0 | 0 | 0 | 0.45833 | OK | OK
| IA-26-13 | Inspection and testing | K. Varga | 2026-11-24 |  | Planned | 6 | L. Okoro | 0 | 0 | 0 | 0 | 0.55 | OK | OK
| IA-26-14 | Management and planning | T. Mensah | 2026-12-08 |  | Planned | 7 | J. Ellis | 0 | 0 | 0 | 0 | 0.64167 | OK | OK

## Audit Checklist
ISO 9001 Internal Audit Planner
| One row per question asked: clause, question, evidence and result. Findings carry an owner, a due date and a closed date. | [16 empty] | mfgcalcs.com
Example data for Wexford Components (fictional; questions written for this template, keyed to ISO 9001 clause numbers). Process, Audit date and Response (days) come from the programme and the grade list.
| Audit no. | Clause | Clause ref. | Question | Evidence | Result | Action owner | Closed | Process | Audit date | Response (days) | Finding | Response due | Open | Action status | Closed on time | Check | Notes
| IA-26-01 | 4 Context | 4.1 | Are internal and external issues reviewed and the review recorded? | Procedure and records reviewed | Conforms |  |  | Management and planning | 2026-01-20 |  | 0 |  | 0 |  |  | OK
| IA-26-01 | 4 Context | 4.3 | Is the scope of the QMS documented, with any exclusions justified? | Scope statement could name the second site | OFI | J. Ellis | 2026-03-31 | Management and planning | 2026-01-20 | 90 | 1 | 2026-04-20 | 0 | Complete | Yes | OK
| IA-26-01 | 5 Leadership | 5.2 | Is the quality policy available, communicated and understood by staff asked? | Sample of five orders | Conforms |  |  | Management and planning | 2026-01-20 |  | 0 |  | 0 |  |  | OK
| IA-26-01 | 6 Planning | 6.1 | Are risks and opportunities recorded with actions and owners? | Register reviewed | Conforms |  |  | Management and planning | 2026-01-20 |  | 0 |  | 0 |  |  | OK
| IA-26-01 | 6 Planning | 6.2 | Are quality objectives measurable, with plans and current results? | Two of five objectives had no plan to achieve them | Minor NC | J. Ellis | 2026-03-02 | Management and planning | 2026-01-20 | 60 | 1 | 2026-03-21 | 0 | Complete | Yes | OK
| IA-26-01 | 9 Evaluation | 9.3 | Did the last management review cover every required input and record decisions? | Records sampled | Conforms |  |  | Management and planning | 2026-01-20 |  | 0 |  | 0 |  |  | OK
| IA-26-01 | 5 Leadership | 5.3 | Are responsibilities and authorities for the QMS assigned and known? | Register reviewed | Conforms |  |  | Management and planning | 2026-01-20 |  | 0 |  | 0 |  |  | OK
| IA-26-02 | 8 Operation | 8.4.1 | Are suppliers evaluated, selected and re-evaluated against criteria? | Sample of five orders | Conforms |  |  | Purchasing and suppliers | 2026-02-18 |  | 0 |  | 0 |  |  | OK
| IA-26-02 | 8 Operation | 8.4.2 | Are controls on purchased product defined by risk (inspection, certificates)? | Plating supplier receipts accepted without certificates in March | Minor NC | D. Shah | 2026-04-11 | Purchasing and suppliers | 2026-02-18 | 60 | 1 | 2026-04-19 | 0 | Complete | Yes | OK
| IA-26-02 | 8 Operation | 8.4.3 | Do purchase orders state requirements, specifications and approvals? | Interviewed the process owner | Conforms |  |  | Purchasing and suppliers | 2026-02-18 |  | 0 |  | 0 |  |  | OK
| IA-26-02 | 9 Evaluation | 9.1.3 | Is supplier performance monitored and reviewed? | Supplier scorecard not yet reviewed quarterly | OFI | D. Shah |  | Purchasing and suppliers | 2026-02-18 | 90 | 1 | 2026-05-19 | 1 | Overdue |  | OK
| IA-26-02 | 7 Support | 7.5.3 | Are supplier certificates filed and traceable to receipts? | Interviewed the process owner | Conforms |  |  | Purchasing and suppliers | 2026-02-18 |  | 0 |  | 0 |  |  | OK
| IA-26-02 | 10 Improvement | 10.2 | Are supplier nonconformities raised and followed to closure? | Procedure and records reviewed | Conforms |  |  | Purchasing and suppliers | 2026-02-18 |  | 0 |  | 0 |  |  | OK
| IA-26-03 | 8 Operation | 8.5.1 | Are work instructions available at the workstation and current? | Procedure and records reviewed | Conforms |  |  | Production | 2026-03-10 |  | 0 |  | 0 |  |  | OK
| IA-26-03 | 8 Operation | 8.5.1 | Are set-up approvals and in-process checks recorded as the control plan requires? | Set-up approval missing on two jobs at press 4 | Minor NC | K. Varga | 2026-04-12 | Production | 2026-03-10 | 60 | 1 | 2026-05-09 | 0 | Complete | Yes | OK
| IA-26-03 | 8 Operation | 8.5.2 | Is product identified and traceable through the process? | Interviewed the process owner | Conforms |  |  | Production | 2026-03-10 |  | 0 |  | 0 |  |  | OK
| IA-26-03 | 7 Support | 7.1.3 | Is equipment maintained to plan, with records? | Register reviewed | Conforms |  |  | Production | 2026-03-10 |  | 0 |  | 0 |  |  | OK
| IA-26-03 | 8 Operation | 8.5.6 | Are process changes reviewed and authorised before use? | Register reviewed | Conforms |  |  | Production | 2026-03-10 |  | 0 |  | 0 |  |  | OK
| IA-26-03 | 7 Support | 7.1.4 | Is the work environment suitable (cleanliness, lighting, temperature where it matters)? | Lighting at the deburr bench is poor | OFI | K. Varga | 2026-06-03 | Production | 2026-03-10 | 90 | 1 | 2026-06-08 | 0 | Complete | Yes | OK
| IA-26-03 | 8 Operation | 8.7 | Is nonconforming product identified and segregated at the point of production? | Observed at the workstation | Conforms |  |  | Production | 2026-03-10 |  | 0 |  | 0 |  |  | OK
| IA-26-03 | 7 Support | 7.2 | Are operators trained and signed off for the jobs they run? | Observed at the workstation | Conforms |  |  | Production | 2026-03-10 |  | 0 |  | 0 |  |  | OK
| IA-26-04 | 7 Support | 7.1.5.1 | Does a register list every measuring instrument with interval and due date? | Register reviewed | Conforms |  |  | Calibration | 2026-04-14 |  | 0 |  | 0 |  |  | OK
| IA-26-04 | 7 Support | 7.1.5.2 | Are calibrations traceable to national standards, with certificates on file? | Interviewed the process owner | Conforms |  |  | Calibration | 2026-04-14 |  | 0 |  | 0 |  |  | OK
| IA-26-04 | 7 Support | 7.1.5.2 | Are out-of-tolerance finds assessed for their effect on product already measured? | No impact assessment for three gauges found out of tolerance | Major NC | L. Okoro | 2026-05-12 | Calibration | 2026-04-14 | 30 | 1 | 2026-05-14 | 0 | Complete | Yes | OK
| IA-26-04 | 7 Support | 7.1.5.2 | Are instruments identified with their status and protected from adjustment? | Register reviewed | Conforms |  |  | Calibration | 2026-04-14 |  | 0 |  | 0 |  |  | OK
| IA-26-04 | 7 Support | 7.1.5.1 | Are overdue instruments recalled and kept out of use? | Two overdue calipers found in a toolbox | Minor NC | L. Okoro | 2026-05-29 | Calibration | 2026-04-14 | 60 | 1 | 2026-06-13 | 0 | Complete | Yes | OK
| IA-26-05 | 8 Operation | 8.2.2 | Are customer requirements, including unstated ones, determined before acceptance? | Unstated requirements checklist would help quoting | OFI | M. Ruiz |  | Sales and contract review | 2026-05-19 | 90 | 1 | 2026-08-17 | 1 | Overdue |  | OK
| IA-26-05 | 8 Operation | 8.2.3 | Is each order reviewed before acceptance, with differences resolved and recorded? | Interviewed the process owner | Conforms |  |  | Sales and contract review | 2026-05-19 |  | 0 |  | 0 |  |  | OK
| IA-26-05 | 8 Operation | 8.2.4 | Are order changes communicated to the people affected? | Register reviewed | Conforms |  |  | Sales and contract review | 2026-05-19 |  | 0 |  | 0 |  |  | OK
| IA-26-05 | 8 Operation | 8.2.1 | Are customer complaints and feedback captured? | Interviewed the process owner | Conforms |  |  | Sales and contract review | 2026-05-19 |  | 0 |  | 0 |  |  | OK
| IA-26-05 | 9 Evaluation | 9.1.2 | Is customer satisfaction monitored, with results reviewed? | Sample of five orders | Conforms |  |  | Sales and contract review | 2026-05-19 |  | 0 |  | 0 |  |  | OK
| IA-26-05 | 7 Support | 7.5.3 | Are contract records retained and retrievable? | Observed at the workstation | Conforms |  |  | Sales and contract review | 2026-05-19 |  | 0 |  | 0 |  |  | OK
| IA-26-06 | 8 Operation | 8.6 | Is product release done against criteria by an authorised person, with records? | Observed at the workstation | Conforms |  |  | Inspection and testing | 2026-06-09 |  | 0 |  | 0 |  |  | OK
| IA-26-06 | 8 Operation | 8.7 | Are nonconforming parts tagged, segregated and dispositioned with records? | Sample of five orders | Conforms |  |  | Inspection and testing | 2026-06-09 |  | 0 |  | 0 |  |  | OK
| IA-26-06 | 7 Support | 7.1.5 | Are the gauges in use calibrated and within their due dates? | Height gauge in use 9 days past its due date | Minor NC | L. Okoro |  | Inspection and testing | 2026-06-09 | 60 | 1 | 2026-08-08 | 1 | Overdue |  | OK
| IA-26-06 | 7 Support | 7.5.3 | Are inspection records complete, legible and retained? | Interviewed the process owner | Conforms |  |  | Inspection and testing | 2026-06-09 |  | 0 |  | 0 |  |  | OK
| IA-26-06 | 9 Evaluation | 9.1.3 | Are inspection results analysed for trends? | Reject trend by part not charted | OFI | L. Okoro | 2026-08-08 | Inspection and testing | 2026-06-09 | 90 | 1 | 2026-09-07 | 0 | Complete | Yes | OK
| IA-26-06 | 8 Operation | 8.6 | Are first-off and last-off checks done as planned? | Observed at the workstation | Conforms |  |  | Inspection and testing | 2026-06-09 |  | 0 |  | 0 |  |  | OK
| IA-26-07 | 8 Operation | 8.3.2 | Is there a design plan with stages, reviews and responsibilities? | Register reviewed | Conforms |  |  | Design and development | 2026-07-08 |  | 0 |  | 0 |  |  | OK
| IA-26-07 | 8 Operation | 8.3.3 | Are design inputs complete, including legal and customer requirements? | Observed at the workstation | Conforms |  |  | Design and development | 2026-07-08 |  | 0 |  | 0 |  |  | OK
| IA-26-07 | 8 Operation | 8.3.4 | Are design reviews, verification and validation recorded? | Observed at the workstation | Conforms |  |  | Design and development | 2026-07-08 |  | 0 |  | 0 |  |  | OK
| IA-26-07 | 8 Operation | 8.3.5 | Do design outputs include acceptance criteria and special characteristics? | Records sampled | Conforms |  |  | Design and development | 2026-07-08 |  | 0 |  | 0 |  |  | OK
| IA-26-07 | 8 Operation | 8.3.6 | Are design changes reviewed, authorised and recorded? | Rev C change approved by e-mail only | Minor NC | T. Mensah |  | Design and development | 2026-07-08 | 60 | 1 | 2026-09-06 | 1 | Overdue |  | OK
| IA-26-07 | 7 Support | 7.5.2 | Are drawings controlled, with revision and approval visible? | Sample of five orders | Conforms |  |  | Design and development | 2026-07-08 |  | 0 |  | 0 |  |  | OK
| IA-26-08 | 7 Support | 7.2 | Are competence requirements defined for each role? | Sample of five orders | Conforms |  |  | People and training | 2026-08-11 |  | 0 |  | 0 |  |  | OK
| IA-26-08 | 7 Support | 7.2 | Are training records complete and effectiveness checked? | Training effectiveness not checked for new starters | Minor NC | A. Novak |  | People and training | 2026-08-11 | 60 | 1 | 2026-10-10 | 1 | Due soon |  | OK
| IA-26-08 | 7 Support | 7.3 | Do staff asked know the policy, their objectives and the effect of nonconformity? | Records sampled | Conforms |  |  | People and training | 2026-08-11 |  | 0 |  | 0 |  |  | OK
| IA-26-08 | 7 Support | 7.1.2 | Are people resources reviewed against the plan? | Records sampled | Conforms |  |  | People and training | 2026-08-11 |  | 0 |  | 0 |  |  | OK
| IA-26-08 | 7 Support | 7.4 | Are internal communications planned (what, when, who)? | Sample of five orders | Conforms |  |  | People and training | 2026-08-11 |  | 0 |  | 0 |  |  | OK
| IA-26-09 | 8 Operation | 8.5.4 | Is product preserved in storage (packaging, FIFO, shelf life)? | Sample of five orders | Conforms |  |  | Warehouse and shipping | 2026-09-09 |  | 0 |  | 0 |  |  | OK
| IA-26-09 | 8 Operation | 8.5.2 | Do shipments carry the identification and documents the customer requires? | Records sampled | Conforms |  |  | Warehouse and shipping | 2026-09-09 |  | 0 |  | 0 |  |  | OK
| IA-26-09 | 8 Operation | 8.5.5 | Are delivery and post-delivery requirements met? | Sample of five orders | Conforms |  |  | Warehouse and shipping | 2026-09-09 |  | 0 |  | 0 |  |  | OK
| IA-26-09 | 7 Support | 7.1.3 | Are storage areas organised and labelled? | Observed at the workstation | Conforms |  |  | Warehouse and shipping | 2026-09-09 |  | 0 |  | 0 |  |  | OK
| IA-26-09 | 8 Operation | 8.7 | Is returned or suspect stock held in a marked area? | Returned-goods area shares a rack with good stock | OFI | S. Byrne |  | Warehouse and shipping | 2026-09-09 | 90 | 1 | 2026-12-08 | 1 | OK |  | OK
Formulas:
Audit date = IF(tblChecklist[[#This Row],[Audit no.]]="","",IFERROR(INDEX(tblAudits[Actual date],MATCH(tblChecklist[[#This Row],[Audit no.]],tblAudits[Audit no.],0)),""))
Response due = IF(tblChecklist[[#This Row],[Audit no.]]="","",IF(OR(tblChecklist[[#This Row],[Finding]]=0,NOT(ISNUMBER(tblChecklist[[#This Row],[Audit date]]))),"",tblChecklist[[#This Row],[Audit date]]+tblChecklist[[#This Row],[Response (days)]]))

## Dashboard
ISO 9001 Internal Audit Planner
| Programme completion, conformance by clause, findings by process and the corrective actions still open. | [8 empty] | mfgcalcs.com
Status date 9 Oct 2026: 14 audits on the programme, 54 questions asked, 14 findings.
| AUDITS DONE TO DATE |  | OPEN FINDINGS |  |  | ACTIONS OVERDUE |  |  | QUESTIONS CONFORMING
| 90% |  | 6 |  |  | 4 |  |  | 74.07%
| 90% |  | NCs and OFIs not yet closed |  |  | 0 |  |  | Of all questions audited
| On target |  |  |  |  | Above target
| OPEN MAJOR NCS |  | FINDINGS CLOSED |  |  | AUDITS OVERDUE |  |  | AUDIT HOURS TO DO (EST.)
| 0 |  | 57.14% |  |  | 1 |  |  | 2.9333
| 0 |  | 80% |  |  | 0 |  |  | Planned and postponed audits
| On target |  | Below target |  |  | Above target
Conformance by clause section
| Clause section | Questions | Conforming | Major NC | Minor NC | OFI | Conformance
| 4 Context | 2 | 1 | 0 | 0 | 1 | 50%
| 5 Leadership | 2 | 2 | 0 | 0 | 0 | 100%
| 6 Planning | 2 | 1 | 0 | 1 | 0 | 50%
| 7 Support | 19 | 14 | 1 | 3 | 1 | 73.68%
| 8 Operation | 24 | 19 | 0 | 3 | 2 | 79.17%
| 9 Evaluation | 4 | 2 | 0 | 0 | 2 | 50%
| 10 Improvement | 1 | 1 | 0 | 0 | 0 | 100%
By process
| Process | Audits | Done | Last audited | Major NC | Minor NC | OFI | Open | Overdue
| Management and planning | 2 | 1 | 2026-01-20 | 0 | 1 | 1 | 0 | 0
| Sales and contract review | 1 | 1 | 2026-05-19 | 0 | 0 | 1 | 1 | 1
| Design and development | 1 | 1 | 2026-07-08 | 0 | 1 | 0 | 1 | 1
| Purchasing and suppliers | 1 | 1 | 2026-02-18 | 0 | 1 | 1 | 1 | 1
| Production | 2 | 1 | 2026-03-10 | 0 | 1 | 1 | 0 | 0
| Inspection and testing | 2 | 1 | 2026-06-09 | 0 | 1 | 1 | 1 | 1
| Calibration | 2 | 1 | 2026-04-14 | 1 | 1 | 0 | 0 | 0
| Warehouse and shipping | 1 | 1 | 2026-09-09 | 0 | 0 | 1 | 1 | 0
| People and training | 1 | 1 | 2026-08-11 | 0 | 1 | 0 | 1 | 0
| Improvement and CAPA | 1 | 0 |  | 0 | 0 | 0 | 0 | 0
The Dashboard shows the 10 processes of the Setup list and the 7 clause sections. If you add processes, extend the 'By process' block (see Method) or they will not appear here.
Formulas:
Major NC = IF(B48="","",IF(D48=0,"",SUMPRODUCT(MAX((tblAudits[Process]=B48)*(tblAudits[Status]="Done")*tblAudits[Actual date]))))

## Method
ISO 9001 Internal Audit Planner
| How every number is calculated, with assumptions, limits and sources. |  | mfgcalcs.com
What this workbook calculates
ISO 9001 asks for internal audits at planned intervals, in a programme that weighs the importance of each process and the results of earlier audits, by auditors who are objective and impartial. This workbook keeps the programme (one row per audit) and the checklist (one row per question asked, with its result). Findings get a due date from their grade and are closed when the action is verified; everything is measured to the status date on Setup, so the file never changes by itself.
Calculations
| Quantity | How it is calculated | Units
| Questions asked, Major NC, Minor NC, OFI | Checklist rows for the audit, and those with each result (COUNTIFS). | count
| Est. hours | Questions planned x minutes per question / 60 x (1 + allowance): the Internal Audit Planning Time calculator's formula. | h
| Due status (audit) | Done: Complete. Cancelled: Cancelled. Otherwise Overdue after the planned date, Due soon within the window, else OK. | -
| Finding | 1 when the result is on the Grades list (Major NC, Minor NC, OFI). | 0/1
| Response due | Audit date (from the programme) + the grade's response days. | date
| Open, action status | Open = a finding without a closed date. Status: Complete when closed; Overdue after the response due date; Due soon within the window; otherwise OK. | -
| Closed on time | Yes when closed on or before the response due date. | -
| Audits done to date | Audits done with a planned date up to the status date / audits (not cancelled) with a planned date up to the status date. | %
| Questions conforming | Questions with result Conforms / questions audited (all rows except Not audited); by clause section on the radar. | %
| Findings closed | Findings closed / findings raised: the Nonconformance Clearance Ratio calculator's ratio. | %
| Audit hours to do | Sum of the estimated hours of planned and postponed audits. | h
Assumptions
| • | One row per question asked. A question asked twice in one audit (two samples) can be two rows.
| • | An OFI counts as a finding with a response time, so it is tracked to closure; set a long response time if you do not track OFIs.
| • | Response due dates run from the audit's actual date; findings of audits without an actual date have no due date.
| • | Audit hours are a planning estimate from your own time standard, not a measured time.
Limitations
| • | The questions are examples written for this template; ISO 9001 text is not reproduced. Write your own from the standard, your procedures and earlier findings.
| • | The workbook records that an action was closed; root cause analysis and the action plan belong in your CAPA or NCR log.
| • | The 'By process' block has a fixed number of rows (a warning appears when the list grows).
| • | Conformance is a share of questions, not a measure of the system's effectiveness: a short checklist that avoids weak areas scores well.
Agreement with the live calculator
Estimated audit hours use the Internal Audit Planning Time calculator's formula: active hours = questions / questions per minute / 60, plus the overhead and delay allowance. With the calculator's default example (120 questions, 0.2 per minute = 5 minutes each, 10%) both give 11.0 hours. Findings closed is the Nonconformance Clearance Ratio calculator's closed / opened x 100 (230 of 250 = 92.0%). The template's reference is checked against both engines on every build.
Open the Internal Audit Planning Time Calculator
Self-check
The Verify sheet holds fixed test inputs. Its formulas are the same formula text as the working sheets, placed against those inputs, and each result is compared with a value computed independently by the template's Python reference implementation when the file was built. If you edit a formula on a working sheet, the Verify sheet still tests the original formula text, so it will not detect your change.
Sources and standards
| • | ISO 9001:2015, clause 9.2 Internal audit (requirements summarised in our own words, not reproduced).
| • | ISO 19011:2018, Guidelines for auditing management systems.
| • | MFG Calcs Internal Audit Planning Time and Nonconformance Clearance Ratio calculators.
Standards are cited by name so you can look them up; no copyrighted standard text or tables are reproduced. Statistical constants used are public.
Version history
| Version | Change | Date
| 1.0.0 | First release. | 15 October 2026
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Verify
ISO 9001 Internal Audit Planner
| Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference. | [16 empty] | mfgcalcs.com
| Self-check status |  | PASS |  | 19 of 19 checks pass
This sheet recomputes the workbook's own formulas on fixed test inputs and compares each result with a value computed independently by the template's Python reference implementation when the file was built. Every row should read PASS. The test inputs are fixed and do not change when you edit Setup or the working sheets.
Checks
| No. | Check |  |  |  | Expected (reference) | Workbook result | Difference | Tolerance | Result
| 1 | A1: estimated hours, calculator example (120 questions) |  |  |  | 11 | 11 | 0 | 1e-09 | PASS
| 2 | A1: major NCs |  |  |  | 1 | 1 | 0 | 1e-09 | PASS
| 3 | A3: postponed past its date |  |  |  | Overdue | Overdue |  | exact | PASS
| 4 | A4: due soon |  |  |  | Due soon | Due soon |  | exact | PASS
| 5 | A5: cancelled |  |  |  | Cancelled | Cancelled |  | exact | PASS
| 6 | A6: Check reports the auditor owns the process |  |  |  | Auditor owns this process | Auditor owns this process |  | exact | PASS
| 7 | Row 2: response due (30 days) |  |  |  | 2026-04-09 | 2026-04-09 | 0 | 1e-09 | PASS
| 8 | Row 2: closed on time |  |  |  | Yes | Yes |  | exact | PASS
| 9 | Row 3: action overdue |  |  |  | Overdue | Overdue |  | exact | PASS
| 10 | Row 4: OFI not yet due |  |  |  | OK | OK |  | exact | PASS
| 11 | Row 1: conforming question is not a finding |  |  |  | 0 | 0 | 0 | 1e-09 | PASS
| 12 | Row 5: Check reports a close after the status date |  |  |  | Closed after the status date | Closed after the status date |  | exact | PASS
| 13 | Row 7: Check reports the missing owner |  |  |  | Finding has no owner | Finding has no owner |  | exact | PASS
| 14 | Audits done to date (Dashboard formula) |  |  |  | 66.67% | 66.67% | 0 | 1e-09 | PASS
| 15 | Open findings (Dashboard formula) |  |  |  | 3 | 3 | 0 | 1e-09 | PASS
| 16 | Actions overdue (Dashboard formula) |  |  |  | 1 | 1 | 0 | 1e-09 | PASS
| 17 | Questions conforming (Dashboard formula) |  |  |  | 16.67% | 16.67% | 0 | 1e-09 | PASS
| 18 | Findings closed (Dashboard formula) |  |  |  | 40% | 40% | 0 | 1e-09 | PASS
| 19 | Audit hours to do (Dashboard formula) |  |  |  | 1.65 | 1.65 | 0 | 1e-09 | PASS
Fixed test inputs
White cells are fixed test inputs; blue cells are the workbook's formulas evaluated on them.
Parameters
| Status date |  |  | 2026-06-30
| Due soon window (days) |  |  | 14
| Minutes per question (calculator example) |  |  | 5
| Allowance (calculator example) |  |  | 10%
Test table: Processes
| Process | Owner | Main clauses
| P1 | O1
| P2 | O2
Test table: Grades
| Grade | Response (days) | Meaning
| Major NC | 30
| Minor NC | 60
| OFI | 90
Test table: Audits
| Audit no. | Process | Lead auditor | Planned date | Actual date | Status | Questions planned | Process owner | Questions asked | Major NC | Minor NC | OFI | Est. hours | Due status | Check | Notes
| A1 | P1 | X | 2026-03-10 | 2026-03-10 | Done | 120 | O1 | 3 | 1 | 1 | 0 | 11 | Complete | OK
| A2 | P2 | X | 2026-05-20 | 2026-05-21 | Done | 4 | O2 | 4 | 0 | 2 | 1 | 0.36667 | Complete | OK
| A3 | P1 | X | 2026-06-15 |  | Postponed | 6 | O1 | 0 | 0 | 0 | 0 | 0.55 | Overdue | OK
| A4 | P2 | X | 2026-07-08 |  | Planned | 6 | O2 | 0 | 0 | 0 | 0 | 0.55 | Due soon | OK
| A5 | P1 | X | 2026-06-01 |  | Cancelled | 6 | O1 | 0 | 0 | 0 | 0 | 0.55 | Cancelled | OK
| A6 | P2 | O2 | 2026-09-01 |  | Planned | 6 | O2 | 0 | 0 | 0 | 0 | 0.55 | OK | Auditor owns this process
Test table: Checklist
| Audit no. | Clause | Clause ref. | Question | Evidence | Result | Action owner | Closed | Process | Audit date | Response (days) | Finding | Response due | Open | Action status | Closed on time | Check | Notes
| A1 | 7 Support | x | Q | E | Conforms |  |  | P1 | 2026-03-10 |  | 0 |  | 0 |  |  | OK
| A1 | 7 Support | x | Q | E | Major NC | O1 | 2026-04-02 | P1 | 2026-03-10 | 30 | 1 | 2026-04-09 | 0 | Complete | Yes | OK
| A1 | 8 Operation | x | Q | E | Minor NC | O1 |  | P1 | 2026-03-10 | 60 | 1 | 2026-05-09 | 1 | Overdue |  | OK
| A2 | 8 Operation | x | Q | E | OFI | O2 |  | P2 | 2026-05-21 | 90 | 1 | 2026-08-19 | 1 | OK |  | OK
| A2 | 8 Operation | x | Q | E | Minor NC | O2 | 2026-07-25 | P2 | 2026-05-21 | 60 | 1 | 2026-07-20 | 0 | Complete | No | Closed after the status date
| A2 | 9 Evaluation | x | Q | E | Not audited |  |  | P2 | 2026-05-21 |  | 0 |  | 0 |  |  | OK
| A2 | 9 Evaluation | x | Q | E | Minor NC |  |  | P2 | 2026-05-21 | 60 | 1 | 2026-07-20 | 1 | OK |  | Finding has no owner