## Start Here
Kaizen Project Tracker
| Read this first: what the workbook does and how to use it. |  |  |  | mfgcalcs.com
Kaizen Project Tracker
Keep every kaizen project in one register and see savings against plan, ROI, payback and the open and overdue projects by area, type and PDCA stage.
For: Continuous-improvement and lean managers, plant managers, project leads and the finance partners who verify savings.
Version 1.0.0 · updated 15 October 2026
Quick start
| 1. | On Setup, type your plant name, currency, the year's savings plan and the status date, then replace the example areas and project types.
| 2. | On Projects, add one row per kaizen: area, type, lead, start and target dates, investment and the annual savings it should deliver.
| 3. | While a project runs, keep its PDCA stage current; when it is done, type the completed date and, once finance agrees, Verified = Yes.
| 4. | Read the Check column: anything other than OK names the problem in words.
| 5. | Before each review, set the status date on Setup and open the Dashboard.
What is in this workbook
|  | Start Here | Read this first: what the workbook does and how to use it.
|  | Setup | Savings plan, status date, currency and the lists that feed the dropdowns.
|  | Projects | One row per kaizen project: dates, PDCA stage, investment and annual savings. Net benefit, payback, ROI and status are calculated.
|  | Dashboard | Savings of completed projects against the plan, and the open and overdue projects by area, type and PDCA stage.
|  | Method | How every number is calculated, with assumptions, limits and sources.
|  | Verify | Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference.
Colour key
|  | Input | Yellow cells are yours: type a value or pick from the list. Each one says what it accepts when you click it.
|  | Calculated | Blue cells are formulas. They update as you type; overwrite one and that row stops calculating.
|  | Note | Grey boxes are guidance and labelled example data.
|  | Status words | On target / PASS / OK | Near target / Check | Below target / FAIL
Status is always written in words; the colour only repeats it, so the workbook reads the same in black-and-white print and for colour-blind readers.
Self-check and links
|  | Self-check | PASS | 17 of 17 checks pass
The Verify sheet recomputes this workbook's formulas on fixed test inputs and compares them with an independent reference calculation. PASS means every check agreed when you opened the file.
|  | Run it live | Manufacturing ROI Calculator on mfgcalcs.com
|  | Latest version | mfgcalcs.com/templates/kaizen-tracker
|  | More free templates | mfgcalcs.com/templates
|  | Version | 1.0.0 (updated 15 October 2026)
About the example data
Every number already in this workbook is example data for Halvorsen Pumps, a fictional business invented for this template, so the dashboard and charts show something meaningful on day one. It covers 30 improvement projects at a pump manufacturer started between December 2025 and September 2026, with status as of 9 October 2026, generated from a fixed seed. To clear it: on each working sheet, select the example rows of the table, right-click and choose Delete > Table Rows. The formulas stay, and every new row you type below the table picks them up.
Good to know
| • | Sheets Start Here, Dashboard, Method, Verify are protected without a password so formulas and layout are not overwritten by accident. To change them: Review > Unprotect Sheet.
| • | Setup and the working sheets are not protected, so tables grow as you add rows.
| • | Works in Excel 2016 and later, Microsoft 365, LibreOffice 24 and Google Sheets (File > Import). No macros, no external links, no add-ins.
| • | Money is shown in the currency you type on Setup; no exchange rates are applied.
Free from MFG Calcs - keep this credit when you share it.
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Setup
Kaizen Project Tracker
| Savings plan, status date, currency and the lists that feed the dropdowns. |  | mfgcalcs.com
Plant, plan and status date
| Plant or company name | Halvorsen Pumps (example)
| Currency label | CAD
| Savings year starts | 2026-01-01
| Savings plan for the year | 720000 | CAD per year
| Status date | 2026-10-09
| Plan to the status date | 556273.9726 | CAD per year
| Due soon window | 14 | days
| Completed on time target | 75%
The plan to date is the year's plan x the share of the year elapsed at the status date (straight line). Savings are annual run rates of completed projects, net of any added running cost; see Method.
Lists that feed the dropdowns
Areas
| Area | Owner | Description
| Machining | E. Lindgren | CNC lathes, horizontal machining centres, deburr
| Assembly | D. Mensah | Small and large pump assembly lines
| Test | C. Varga | Hydro-test and motor test benches
| Paint | F. Ortega | Masking, powder booths and cure oven
| Warehouse | H. Bose | Receiving, stores, packing and shipping
| Office | G. Laurent | Order entry, purchasing and engineering release
Project types
Keep names unique. Rows that use a renamed area or type stop matching, and their Check column says so.
| Type | Description
| Kaizen event | A 3 to 5 day focused team event
| SMED | Changeover time reduction
| Quality fix | Removes a cause of scrap, rework or escapes
| Energy | Cuts electricity, gas or compressed air use
| 5S | Workplace organisation
| Just-do-it | A small fix done by the team in days

## Projects
Kaizen Project Tracker
| One row per kaizen project: dates, PDCA stage, investment and annual savings. Net benefit, payback, ROI and status are calculated. | [20 empty] | mfgcalcs.com
Example data for Halvorsen Pumps (fictional; savings and costs are invented examples). Replace it with your own: select the example rows, right-click, Delete > Table Rows. Savings are annual run rates; status is measured to the status date on Setup.
[10 empty] | CAD | CAD/yr | CAD/yr | CAD/yr | CAD/yr |  | CAD/yr | months |  |  |  | days
| ID | Project | Area | Type | Lead | Start | Target date | Completed | PDCA stage | Investment | Labor savings | Scrap and material savings | Other savings | Added running cost | Verified | Net annual benefit | Payback | Annual ROI | Status | On time | Days open | Check
| KZ-001 | Kanban for packaging materials | Warehouse | Kaizen event | H. Bose | 2025-12-19 | 2026-01-31 | 2026-01-31 |  | 11000 | 41500 | 5000 | 6000 | 0 | Yes | 52500 | 2.5143 | 477.3% | Complete | Yes | 43 | OK
| KZ-002 | Shadow boards for lathe tooling | Machining | 5S | E. Lindgren | 2025-12-21 | 2026-01-19 | 2026-01-26 |  | 1500 | 4500 | 1000 | 0 | 0 | No | 5500 | 3.2727 | 366.7% | Complete | No | 36 | OK
| KZ-003 | Re-slotting the pick path | Warehouse | Kaizen event | S. Tanaka | 2026-01-16 | 2026-02-26 | 2026-02-26 |  | 16000 | 32500 | 6500 | 4000 | 0 | Yes | 43000 | 4.4651 | 268.8% | Complete | Yes | 41 | OK
| KZ-004 | Torque tool error-proofing | Assembly | Quality fix | D. Mensah | 2026-01-17 | 2026-03-28 | 2026-03-28 |  | 12500 | 500 | 33000 | 0 | 0 | Yes | 33500 | 4.4776 | 268% | Complete | Yes | 70 | OK
| KZ-005 | Casting inspection at receipt | Warehouse | Quality fix | H. Bose | 2026-01-22 | 2026-02-28 | 2026-02-28 |  | 7500 | 4000 | 11000 | 0 | 0 | Yes | 15000 | 6 | 200% | Complete | Yes | 37 | OK
| KZ-006 | Coolant concentration check at start of shift | Machining | Quality fix | E. Lindgren | 2026-01-28 | 2026-04-03 | 2026-05-05 |  | 4000 | 7500 | 16000 | 0 | 0 | Yes | 23500 | 2.0426 | 587.5% | Complete | No | 97 | OK
| KZ-007 | Paint rack redesign | Paint | Kaizen event | S. Tanaka | 2026-02-15 | 2026-04-09 | 2026-05-05 |  | 17500 | 13500 | 6500 | 4500 | 0 | No | 24500 | 8.5714 | 140% | Complete | No | 79 | OK
| KZ-008 | 5S in the deburr cell | Machining | 5S | E. Lindgren | 2026-02-17 | 2026-03-23 | 2026-03-18 |  | 3000 | 5500 | 1500 | 0 | 0 | No | 7000 | 5.1429 | 233.3% | Complete | Yes | 29 | OK
| KZ-009 | Order entry error reduction | Office | Quality fix | C. Varga | 2026-03-05 | 2026-04-09 | 2026-04-27 |  | 6500 | 5000 | 33500 | 0 | 0 | Yes | 38500 | 2.026 | 592.3% | Complete | No | 53 | OK
| KZ-010 | Assembly bench height standard | Assembly | Just-do-it | D. Mensah | 2026-03-07 | 2026-03-19 | 2026-03-20 |  | 1000 | 5500 | 2500 | 0 | 0 | No | 8000 | 1.5 | 800% | Complete | No | 13 | OK
| KZ-011 | Cure oven load pattern standard | Paint | Energy | F. Ortega | 2026-03-07 | 2026-04-26 | 2026-05-08 |  | 4500 | 0 | 0 | 6500 | 0 | Yes | 6500 | 8.3077 | 144.4% | Complete | No | 62 | OK
| KZ-012 | Automatic capture of test results | Test | Just-do-it | C. Varga | 2026-03-11 | 2026-03-21 |  | Act | 500 | 5500 | 2500 | 0 | 1200 | No | 6800 | 0.88235 | 1360% | Overdue |  | 212 | OK
| KZ-013 | Hydro-test fixture changeover | Test | SMED | C. Varga | 2026-03-24 | 2026-05-10 | 2026-05-22 |  | 17000 | 18000 | 4000 | 0 | 0 | Yes | 22000 | 9.2727 | 129.4% | Complete | No | 59 | OK
| KZ-014 | Pre-kitted seal kits for pump assembly | Assembly | Kaizen event | D. Mensah | 2026-04-02 | 2026-05-03 | 2026-05-11 |  | 7500 | 35500 | 4500 | 1000 | 0 | Yes | 41000 | 2.1951 | 546.7% | Complete | No | 39 | OK
| KZ-015 | Impeller balancing rework loop | Machining | Quality fix | F. Ortega | 2026-04-08 | 2026-05-12 | 2026-05-15 |  | 3500 | 5000 | 35000 | 0 | 0 | No | 40000 | 1.05 | 1143% | Complete | No | 37 | OK
| KZ-016 | Spindle warm-up program change | Machining | Energy | D. Mensah | 2026-04-17 | 2026-05-31 | 2026-05-31 |  | 15500 | 0 | 0 | 5000 | 0 | No | 5000 | 37.2 | 32.26% | Complete | Yes | 44 | OK
| KZ-017 | Engineering change release flow | Office | Kaizen event | G. Laurent | 2026-04-24 | 2026-05-27 | 2026-06-12 |  | 5500 | 10500 | 1000 | 3000 | 0 | Yes | 14500 | 4.5517 | 263.6% | Complete | No | 49 | OK
| KZ-018 | Powder reclaim on booth 2 | Paint | Kaizen event | S. Tanaka | 2026-05-02 | 2026-06-19 |  | Act | 6500 | 40500 | 6000 | 3500 | 900 | No | 49100 | 1.5886 | 755.4% | Overdue |  | 160 | OK
| KZ-019 | Compressed air leak survey and fixes | Machining | Energy | E. Lindgren | 2026-05-10 | 2026-06-14 | 2026-07-02 |  | 16000 | 0 | 0 | 12000 | 0 | Yes | 12000 | 16 | 75% | Complete | No | 53 | OK
| KZ-020 | Fewer purchase order approval steps | Office | Kaizen event | G. Laurent | 2026-06-17 | 2026-07-17 | 2026-07-17 |  | 5000 | 24000 | 4000 | 4500 | 0 | No | 32500 | 1.8462 | 650% | Complete | Yes | 30 | OK
| KZ-021 | Line-side supermarket for fasteners | Assembly | Kaizen event | G. Laurent | 2026-06-18 | 2026-07-31 | 2026-07-31 |  | 5000 | 15000 | 6000 | 500 | 0 | Yes | 21500 | 2.7907 | 430% | Complete | Yes | 43 | OK
| KZ-022 | Shorter motor test cycle | Test | Kaizen event | C. Varga | 2026-06-21 | 2026-07-20 | 2026-07-20 |  | 9000 | 17500 | 2500 | 5500 | 0 | Yes | 25500 | 4.2353 | 283.3% | Complete | Yes | 29 | OK
| KZ-023 | Returnable crates with the casting supplier | Warehouse | Kaizen event | F. Ortega | 2026-07-17 | 2026-09-05 | 2026-09-03 |  | 15500 | 26000 | 500 | 2500 | 0 | No | 29000 | 6.4138 | 187.1% | Complete | Yes | 48 | OK
| KZ-024 | Leak detection upgrade on bench 3 | Test | Quality fix | C. Varga | 2026-07-30 | 2026-09-15 |  | Act | 11000 | 7000 | 24500 | 0 | 0 | No | 31500 | 4.1905 | 286.4% | Overdue |  | 71 | OK
| KZ-025 | Dock door scheduling board | Warehouse | Just-do-it | H. Bose | 2026-08-07 | 2026-08-18 | 2026-08-21 |  | 500 | 3500 | 1000 | 0 | 0 | Yes | 4500 | 1.3333 | 900% | Complete | No | 14 | OK
| KZ-026 | Changeover cart for the press-fit station | Assembly | SMED | D. Mensah | 2026-08-09 | 2026-10-18 |  | Check | 15000 | 30500 | 4000 | 0 | 0 | No | 34500 | 5.2174 | 230% | Due soon |  | 61 | OK
| KZ-027 | One-piece flow on the small-pump line | Assembly | Kaizen event | D. Mensah | 2026-08-18 | 2026-09-22 | 2026-09-17 |  | 14500 | 17500 | 6500 | 1000 | 0 | No | 25000 | 6.96 | 172.4% | Complete | Yes | 30 | OK
| KZ-028 | Reusable masking plugs | Paint | Just-do-it | F. Ortega | 2026-08-26 | 2026-09-02 | 2026-09-01 |  | 0 | 6000 | 2000 | 0 | 0 | No | 8000 | 0 |  | Complete | Yes | 6 | OK
| KZ-029 | Quick-change fixtures on HMC-2 | Machining | SMED | E. Lindgren | 2026-09-06 | 2026-11-18 |  | Do | 19500 | 17500 | 0 | 0 | 0 | No | 17500 | 13.3714 | 89.74% | In progress |  | 33 | OK
| KZ-030 | LED lighting in the paint booths | Paint | Energy | F. Ortega | 2026-09-10 | 2026-11-18 |  | Do | 21500 | 0 | 0 | 14500 | 0 | No | 14500 | 17.7931 | 67.44% | In progress |  | 29 | OK

## Dashboard
Kaizen Project Tracker
| Savings of completed projects against the plan, and the open and overdue projects by area, type and PDCA stage. | [8 empty] | mfgcalcs.com
Halvorsen Pumps (example): 30 projects in the register. Savings year from 1 Jan 2026; status as of 9 Oct 2026. Savings are net annual run rates of projects completed in the year.
| SAVINGS COMPLETED THIS YEAR (CAD/YR) |  | PROJECTS COMPLETED THIS YEAR |  |  | OPEN PROJECTS |  |  | OVERDUE PROJECTS
| 538000 |  | 24 |  |  | 6 |  |  | 3
| 556273.9726 |  | Year start to status date |  |  | Not yet completed at the status date |  |  | Open past their target date
Near target
| SAVINGS VERIFIED BY FINANCE |  | COMPLETED ON TIME |  |  | PAYBACK OF THIS YEAR'S PROJECTS |  |  | AVERAGE DAYS TO COMPLETE
| 65.71% |  | 50% |  |  | 4.4498 |  |  | 43.375
| Share of this year's net savings |  | 75% |  |  | Months: investment / net savings x 12 |  |  | Start to completion, this year
Below target
By area (savings and investment of projects completed this year; open projects as of the status date)
| Area | Completed this year | Open, on schedule | Overdue | Net savings |  | Verified | Investment | Payback (months) | Owner
[5 empty] | CAD/yr |  | CAD/yr | CAD
| Machining | 6 | 1 | 0 | 93000 |  | 35500 | 43500 | 5.6129 | E. Lindgren
| Assembly | 5 | 1 | 0 | 129000 |  | 96000 | 40500 | 3.7674 | D. Mensah
| Test | 2 | 0 | 2 | 47500 |  | 47500 | 26000 | 6.5684 | C. Varga
| Paint | 3 | 1 | 1 | 39000 |  | 6500 | 22000 | 6.7692 | F. Ortega
| Warehouse | 5 | 0 | 0 | 144000 |  | 115000 | 50500 | 4.2083 | H. Bose
| Office | 3 | 0 | 0 | 85500 |  | 53000 | 17000 | 2.386 | G. Laurent
By type (projects completed this year)
| Type | Projects | Completed this year | Verified savings |  | Not yet verified |  | Investment | Annual ROI
|  |  |  | CAD/yr |  | CAD/yr |  | CAD
| Kaizen event | 11 | 10 | 198000 |  | 111000 |  | 106500 | 290.1%
| SMED | 3 | 1 | 22000 |  | 0 |  | 17000 | 129.4%
| Quality fix | 6 | 5 | 110500 |  | 40000 |  | 34000 | 442.6%
| Energy | 4 | 3 | 18500 |  | 5000 |  | 36000 | 65.28%
| 5S | 2 | 2 | 0 |  | 12500 |  | 4500 | 277.8%
| Just-do-it | 4 | 3 | 4500 |  | 16000 |  | 1500 | 1367%
Open projects by PDCA stage
| PDCA stage | Open, on schedule | Overdue | Savings expected
CAD/yr
| Plan | 0 | 0 | 0
| Do | 2 | 0 | 32000
| Check | 1 | 0 | 34500
| Act | 0 | 3 | 87400
By month of the savings year
| Month completed | Completed | Net savings | Verified | Cumulative | Plan (cumulative) | Investment
|  |  | CAD/yr | CAD/yr | CAD/yr | CAD/yr | CAD
| 2026-01-01 | 2 | 58000 | 52500 | 58000 | 60000 | 12500
| 2026-02-01 | 2 | 58000 | 58000 | 116000 | 120000 | 23500
| 2026-03-01 | 3 | 48500 | 33500 | 164500 | 180000 | 16500
| 2026-04-01 | 1 | 38500 | 38500 | 203000 | 240000 | 6500
| 2026-05-01 | 7 | 162500 | 93000 | 365500 | 300000 | 69500
| 2026-06-01 | 1 | 14500 | 14500 | 380000 | 360000 | 5500
| 2026-07-01 | 4 | 91500 | 59000 | 471500 | 420000 | 35000
| 2026-08-01 | 1 | 4500 | 4500 | 476000 | 480000 | 500
| 2026-09-01 | 3 | 62000 | 0 | 538000 | 540000 | 30000
| 2026-10-01 | 0 | 0 | 0 | 538000 | 600000 | 0
| 2026-11-01 | 0 | 0 | 0 |  | 660000 | 0
| 2026-12-01 | 0 | 0 | 0 |  | 720000 | 0
The Dashboard shows the 6 areas and 6 project types of the Setup lists and the 12 months from the year start. If you add areas or types, extend the 'By area' and 'By type' blocks (see Method) or they will not appear here.

## Method
Kaizen Project Tracker
| How every number is calculated, with assumptions, limits and sources. |  | mfgcalcs.com
What this workbook calculates
Each kaizen project is one row with its dates and its money. Savings are annual run rates: what the change saves in a full year once it is in place, net of any cost it adds. A project counts toward the year's savings when its completed date falls between the year start and the status date, so the headline compares the run rate delivered so far with the plan pro-rated to the same date. Money is in the currency label on Setup; no exchange rate is applied.
Calculations
| Quantity | How it is calculated | Units
| Net annual benefit | Labor savings + scrap and material savings + other savings - added running cost. Excel: =[@[Labor savings]]+[@[Scrap and material savings]]+[@[Other savings]]-[@[Added running cost]] | currency/yr
| Payback | Investment / net annual benefit x 12; 0 for a project with no investment; blank when the net benefit is zero or negative (it never pays back). | months
| Annual ROI | Net annual benefit / investment; blank with no investment. | %
| Status | Complete when a completed date is typed; Overdue when open past the target date; Due soon when due within the window on Setup; otherwise In progress. | -
| On time | Yes when completed on or before the target date. The KPI is on-time completions / completions this year. | %
| Days open | Completed - start; for an open project, status date - start. | days
| Plan to date | Savings plan x (status date - year start + 1) / days in the savings year, capped at 100%. | currency/yr
| Net annual savings, completed this year | Sum of the net annual benefit of projects completed from the year start to the status date. | currency/yr
| Savings verified | Net annual benefit of this year's completed projects marked Verified = Yes / all of it. | %
| Portfolio payback | Investment of this year's completed projects / their net annual benefit x 12. | months
| Monthly and cumulative | Net annual benefit of projects completed in each month, and the running total to the end of each month up to the status date; plan line = plan x month number / 12. | currency/yr
Assumptions
| • | Savings are typed as annual run rates estimated by the project team; the Verified column records when finance has confirmed them.
| • | A completed project delivers its full run rate from its completed date; the workbook does not phase savings in.
| • | Labor savings are only real if the hours are redeployed or removed; record them the way your finance team agrees to count them.
| • | Investment is the one-off cost you choose to count; team hours are included only if you cost them.
Limitations
| • | The savings this year are annual run rates of completed projects, not the cash saved to date; a project completed in October saves only part of its run rate in the same calendar year.
| • | The Dashboard has fixed blocks for six areas, six types and twelve months; longer lists need the blocks extended (a warning appears on the Dashboard).
| • | Payback and ROI are simple (undiscounted). For a large investment use the Capex NPV and IRR template.
| • | The Verify sheet tests the formulas as built; it cannot see later edits to them.
Agreement with the live calculator
For one project, this workbook and the live Manufacturing ROI calculator compute the same money: net annual benefit = savings - added annual cost, annual ROI = net / investment, payback = investment / net (the calculator in years, this workbook in months). The calculator's energy savings and throughput benefit together are this workbook's other savings, and its added maintenance is the added running cost. The reference implementation is checked against the calculator's engine for the calculator's own example (85,000 investment, 42,000 labor, 12,000 scrap, 3,500 energy and 18,000 throughput savings, 6,500 added maintenance: ROI 81.2%, payback 1.23 years = 14.8 months).
Open the Manufacturing ROI Calculator
Self-check
The Verify sheet holds fixed test inputs. Its formulas are the same formula text as the working sheets, placed against those inputs, and each result is compared with a value computed independently by the template's Python reference implementation when the file was built. If you edit a formula on a working sheet, the Verify sheet still tests the original formula text, so it will not detect your change.
Sources and standards
| • | Imai, M., Kaizen: The Key to Japan's Competitive Success, McGraw-Hill, 1986 (kaizen as continuous small-step improvement).
| • | Deming, W. E., Out of the Crisis, MIT Press, 1986 (the Plan-Do-Check-Act cycle; Deming called it Plan-Do-Study-Act later).
| • | MFG Calcs Manufacturing ROI calculator (manufacturing-roi): net annual benefit, annual ROI and payback for one project.
Standards are cited by name so you can look them up; no copyrighted standard text or tables are reproduced. Statistical constants used are public.
Version history
| Version | Change | Date
| 1.0.0 | First release. | 15 October 2026
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Verify
Kaizen Project Tracker
| Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference. | [20 empty] | mfgcalcs.com
| Self-check status |  | PASS |  | 17 of 17 checks pass
This sheet recomputes the workbook's own formulas on fixed test inputs and compares each result with a value computed independently by the template's Python reference implementation when the file was built. Every row should read PASS. The test inputs are fixed and do not change when you edit Setup or the working sheets.
Checks
| No. | Check |  |  |  | Expected (reference) | Workbook result | Difference | Tolerance | Result
| 1 | Project 1 (calculator example): net annual benefit |  |  |  | 69000 | 69000 | 0 | 1e-09 | PASS
| 2 | Project 1 (calculator example): payback (months) |  |  |  | 14.7826 | 14.7826 | 0 | 1e-09 | PASS
| 3 | Project 1 (calculator example): annual ROI |  |  |  | 81.18% | 81.18% | 0 | 1e-09 | PASS
| 4 | Project 1: completed on time |  |  |  | Yes | Yes |  | exact | PASS
| 5 | Project 2 (no investment): payback 0 months |  |  |  | 0 | 0 | 0 | 1e-09 | PASS
| 6 | Project 2: completed late |  |  |  | No | No |  | exact | PASS
| 7 | Project 2: days open |  |  |  | 18 | 18 | 0 | 1e-09 | PASS
| 8 | Project 3: status overdue |  |  |  | Overdue | Overdue |  | exact | PASS
| 9 | Project 3: days open to the status date |  |  |  | 100 | 100 | 0 | 1e-09 | PASS
| 10 | Project 4: status due soon |  |  |  | Due soon | Due soon |  | exact | PASS
| 11 | Project 4: net benefit negative |  |  |  | -500 | -500 | 0 | 1e-09 | PASS
| 12 | Project 6: Check names completed before start |  |  |  | Completed before start | Completed before start |  | exact | PASS
| 13 | Net savings completed this year (Dashboard formula) |  |  |  | 75500 | 75500 | 0 | 1e-09 | PASS
| 14 | Projects completed this year (Dashboard formula) |  |  |  | 3 | 3 | 0 | 1e-09 | PASS
| 15 | Overdue projects (Dashboard formula) |  |  |  | 1 | 1 | 0 | 1e-09 | PASS
| 16 | Savings verified (Dashboard formula) |  |  |  | 91.39% | 91.39% | 0 | 1e-09 | PASS
| 17 | Portfolio payback (Dashboard formula) |  |  |  | 13.6689 | 13.6689 | 0 | 1e-09 | PASS
Fixed test inputs
White cells are fixed test inputs; blue cells are the workbook's formulas evaluated on them.
Parameters
| Status date |  |  | 2026-10-09
| Savings year starts |  |  | 2026-01-01
| Due soon window (days) |  |  | 14
Test table: Projects
[10 empty] | CAD | CAD/yr | CAD/yr | CAD/yr | CAD/yr |  | CAD/yr | months |  |  |  | days
| ID | Project | Area | Type | Lead | Start | Target date | Completed | PDCA stage | Investment | Labor savings | Scrap and material savings | Other savings | Added running cost | Verified | Net annual benefit | Payback | Annual ROI | Status | On time | Days open | Check
| T-1 | Test | A | T | L | 2026-02-02 | 2026-03-31 | 2026-03-27 |  | 85000 | 42000 | 12000 | 21500 | 6500 | Yes | 69000 | 14.7826 | 81.18% | Complete | Yes | 53 | OK
| T-2 | Test | A | T | L | 2026-05-04 | 2026-05-15 | 2026-05-22 |  | 0 | 4500 | 0 | 0 | 0 | No | 4500 | 0 |  | Complete | No | 18 | OK
| T-3 | Test | A | T | L | 2026-07-01 | 2026-09-30 |  | Do | 12000 | 0 | 18000 | 0 | 0 | No | 18000 | 8 | 150% | Overdue |  | 100 | OK
| T-4 | Test | A | T | L | 2026-08-03 | 2026-10-20 |  | Check | 5000 | 0 | 0 | 1000 | 1500 | No | -500 |  | -10% | Due soon |  | 67 | OK
| T-5 | Test | A | T | L | 2025-10-06 | 2025-12-12 | 2025-12-19 |  | 9000 | 15000 | 0 | 0 | 0 | Yes | 15000 | 7.2 | 166.7% | Complete | No | 74 | OK
| T-6 | Test | A | T | L | 2026-06-01 | 2026-06-30 | 2026-05-29 |  | 1000 | 2000 | 0 | 0 | 0 | No | 2000 | 6 | 200% | Complete | Yes | -3 | Completed before start