## Start Here
Maintenance Work Order Log
| Read this first: what the workbook does and how to use it. |  |  |  | mfgcalcs.com
Maintenance Work Order Log
Log every maintenance work order and see the open backlog in crew-weeks, overdue jobs, emergency work and where the hours and money go.
For: Maintenance managers, planners, supervisors and technicians in plants that track work orders without a full CMMS.
Version 1.0.0 · updated 15 October 2026
Quick start
| 1. | On Setup, set the status date, your labour rate, the crew's weekly hours and your targets, then replace the example assets, work types, priorities and technicians.
| 2. | On Work Orders, add one row per job: number, date raised, asset, description, work type, priority, technician and status.
| 3. | Keep each row current: estimated and actual hours, parts and contractor cost, and the completion date when it is done.
| 4. | Read the Check column: anything other than OK names the problem in words.
| 5. | Move the status date forward when you update the log, then open the Dashboard (set Raised from and Raised to for a month or a quarter).
What is in this workbook
|  | Start Here | Read this first: what the workbook does and how to use it.
|  | Setup | Status date, labour rate, crew hours, your targets, and the asset, work type, priority and technician lists.
|  | Work Orders | One row per work order: what, where, priority, status, hours and cost. Due dates, age and backlog are calculated.
|  | Dashboard | Backlog, overdue and emergency work, on-time completion, and where maintenance hours and money go.
|  | Method | How every number is calculated, with assumptions, limits and sources.
|  | Verify | Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference.
Colour key
|  | Input | Yellow cells are yours: type a value or pick from the list. Each one says what it accepts when you click it.
|  | Calculated | Blue cells are formulas. They update as you type; overwrite one and that row stops calculating.
|  | Note | Grey boxes are guidance and labelled example data.
|  | Status words | On target / PASS / OK | Near target / Check | Below target / FAIL
Status is always written in words; the colour only repeats it, so the workbook reads the same in black-and-white print and for colour-blind readers.
Self-check and links
|  | Self-check | PASS | 21 of 21 checks pass
The Verify sheet recomputes this workbook's formulas on fixed test inputs and compares them with an independent reference calculation. PASS means every check agreed when you opened the file.
|  | Run it live | Maintenance Backlog Weeks Calculator on mfgcalcs.com
|  | Latest version | mfgcalcs.com/templates/maintenance-work-orders
|  | More free templates | mfgcalcs.com/templates
|  | Version | 1.0.0 (updated 15 October 2026)
About the example data
Every number already in this workbook is example data for Harbourside Foods, a fictional business invented for this template, so the dashboard and charts show something meaningful on day one. It covers twelve assets and a five-person crew over eight weeks (17 August to 9 October 2026, status date 9 October), plus a few older orders still open, generated from a fixed seed. To clear it: on each working sheet, select the example rows of the table, right-click and choose Delete > Table Rows. The formulas stay, and every new row you type below the table picks them up.
Good to know
| • | Sheets Start Here, Dashboard, Method, Verify are protected without a password so formulas and layout are not overwritten by accident. To change them: Review > Unprotect Sheet.
| • | Setup and the working sheets are not protected, so tables grow as you add rows.
| • | Works in Excel 2016 and later, Microsoft 365, LibreOffice 24 and Google Sheets (File > Import). No macros, no external links, no add-ins.
| • | Money is shown in the currency you type on Setup; no exchange rates are applied.
Free from MFG Calcs - keep this credit when you share it.
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Setup
Maintenance Work Order Log
| Status date, labour rate, crew hours, your targets, and the asset, work type, priority and technician lists. |  | mfgcalcs.com
Plant and costs
| Plant or site name | Harbourside Foods (example)
| Currency label | USD
| Status date (as of) | 2026-10-09
| Loaded labour rate | 48 | USD per hour
Crew capacity
| Crew hours per week | 160 | person-h/week
| Hours per week committed elsewhere | 40 | person-h/week
| Net crew hours for backlog work | 120 | person-h/week
Targets (yours to set)
| Backlog limit | 3 | crew-weeks
| Emergency work limit | 10%
| On-time completion target | 90%
| Due soon window | 3 | days
Targets are yours to set; nothing here assumes an industry benchmark. 'Near target' means within 5% of the target (for example 3.0 to 3.15 crew-weeks against a 3.0 limit).
Lists that feed the dropdowns
Edit, add or remove rows; the Work Orders dropdowns read these lists. Each work type maps to one of three categories the Dashboard uses (Emergency, Corrective, Planned), and each priority sets the days allowed to complete. Keep names unique: a renamed item stops matching old rows, and their Check column says so.
Assets
| Asset ID | Area | Asset
| MX-01 | Processing | Batch mixer 1
| MX-02 | Processing | Batch mixer 2
| PS-01 | Processing | Pasteuriser
| FL-01 | Line 1 | Bottle filler, Line 1
| CP-01 | Line 1 | Capper, Line 1
| LB-01 | Line 1 | Labeller, Line 1
| FL-02 | Line 2 | Pouch filler, Line 2
| CS-02 | Line 2 | Case packer, Line 2
| PL-01 | End of line | Palletiser
| AC-01 | Utilities | Air compressor
| BL-01 | Utilities | Steam boiler
| CH-01 | Utilities | Glycol chiller
Work types
| Work type | Category | Definition
| Emergency breakdown | Emergency | Break-in work that drops the schedule: asset stopped or unsafe
| Corrective repair | Corrective | A fault found and fixed through the plan, not as a break-in
| Preventive (PM) | Planned | Time- or usage-based routine from the PM schedule
| Predictive (PdM) | Planned | Condition-based task: vibration, oil analysis, thermography
| Improvement | Planned | Modification that removes a recurring problem
| Safety or compliance | Planned | Statutory inspection, guarding, permit or audit action
Priorities and target days to complete
| Priority | Target (days) | Meaning
| P1 Immediate | 1 | Safety risk or line stopped: start now
| P2 Urgent | 3 | Production at risk: complete within days
| P3 Normal | 14 | Plan and schedule within two weeks
| P4 Opportunity | 45 | Do when the asset is down or the crew is free
Technicians
| Technician | Craft | Notes
| Rivera | Mechanical | Day shift
| Okafor | Electrical | Day shift
| Lindqvist | Mechanical | Back shift
| Mehta | Instrumentation | Day shift
| Contractor | External | Booked per job

## Work Orders
Maintenance Work Order Log
| One row per work order: what, where, priority, status, hours and cost. Due dates, age and backlog are calculated. | [25 empty] | mfgcalcs.com
Example data for Harbourside Foods (fictional). Replace it with your own: select the example rows, right-click, Delete > Table Rows. Yellow = you type; blue = calculated; Check names any problem. Ages and overdue flags are measured to the status date on Setup.
[12 empty] | USD | USD | [8 empty] | USD | USD
| WO no. | Date raised | Asset | Description | Work type | Priority | Assigned to | Status | Date completed | Estimated (h) | Actual (h) | Parts cost | Contractor cost | Downtime (h) | Area | Category | Target (days) | Due date | Open | Age (days) | Remaining (h) | Labour cost | Total cost | Due status | On time | View date | Check
| WO-26-0401 | 2026-07-06 | MX-02 | Replace worn agitator coupling | Corrective repair | P3 Normal | Rivera | Waiting parts |  | 6 | 0 | 0 | 0 | 0 | Processing | Corrective | 14 | 2026-07-20 | 1 | 95 | 6 | 0 | 0 | Overdue |  | 2026-07-06 | OK
| WO-26-0402 | 2026-07-14 | PL-01 | Fit second light curtain on infeed (audit action) | Safety or compliance | P3 Normal | Okafor | Open |  | 10 | 0 | 0 | 0 | 0 | End of line | Planned | 14 | 2026-07-28 | 1 | 87 | 10 | 0 | 0 | Overdue |  | 2026-07-14 | OK
| WO-26-0403 | 2026-07-21 | BL-01 | Install condensate return meter | Improvement | P4 Opportunity | Mehta | Open |  | 16 | 0 | 0 | 0 | 0 | Utilities | Planned | 45 | 2026-09-04 | 1 | 80 | 16 | 0 | 0 | Overdue |  | 2026-07-21 | OK
| WO-26-0404 | 2026-07-28 | FL-01 | Redesign infeed guide to stop star wheel jams | Improvement | P4 Opportunity | Lindqvist | In progress |  | 32 | 16 | 0 | 0 | 0 | Line 1 | Planned | 45 | 2026-09-11 | 1 | 73 | 16 | 768 | 768 | Overdue |  | 2026-07-28 | OK
| WO-26-0405 | 2026-07-30 | PS-01 | Regasket pasteuriser plate pack (October shutdown) | Preventive (PM) | P4 Opportunity | Contractor | In progress |  | 40 | 0 | 0 | 0 | 0 | Processing | Planned | 45 | 2026-09-13 | 1 | 71 | 40 | 0 | 0 | Overdue |  | 2026-07-30 | OK
| WO-26-0406 | 2026-08-03 | CH-01 | Replace glycol pump seal | Corrective repair | P3 Normal | Lindqvist | Complete | 2026-08-15 | 4 | 4 | 310 | 0 | 0 | Utilities | Corrective | 14 | 2026-08-17 | 0 | 12 | 0 | 192 | 502 | Complete | Yes | 2026-08-03 | OK
| WO-26-0407 | 2026-08-05 | PS-01 | Recalibrate holding-tube temperature probes | Safety or compliance | P2 Urgent | Mehta | Complete | 2026-08-07 | 3 | 3 | 0 | 0 | 0 | Processing | Planned | 3 | 2026-08-08 | 0 | 2 | 0 | 144 | 144 | Complete | Yes | 2026-08-05 | OK
| WO-26-0408 | 2026-08-11 | AC-01 | Annual pressure vessel inspection | Safety or compliance | P3 Normal | Contractor | Complete | 2026-08-20 | 2 | 2 | 0 | 650 | 0 | Utilities | Planned | 14 | 2026-08-25 | 0 | 9 | 0 | 96 | 746 | Complete | Yes | 2026-08-11 | OK
| WO-26-0409 | 2026-08-17 | AC-01 | Monthly compressor PM: filters, oil, drains | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-08-29 | 3 | 3 | 0 | 0 | 0 | Utilities | Planned | 14 | 2026-08-31 | 0 | 12 | 0 | 144 | 144 | Complete | Yes | 2026-08-17 | OK
| WO-26-0410 | 2026-08-17 | BL-01 | Monthly boiler PM: water treatment, burner check | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-08-20 | 4 | 3.5 | 120 | 0 | 0 | Utilities | Planned | 14 | 2026-08-31 | 0 | 3 | 0 | 168 | 288 | Complete | Yes | 2026-08-17 | OK
| WO-26-0411 | 2026-08-17 | CP-01 | Weekly capper PM: chucks and torque check | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-08-18 | 2 | 2 | 60 | 0 | 0 | Line 1 | Planned | 14 | 2026-08-31 | 0 | 1 | 0 | 96 | 156 | Complete | Yes | 2026-08-17 | OK
| WO-26-0412 | 2026-08-17 | FL-01 | Weekly filler PM: seals, nozzles, lubrication | Preventive (PM) | P3 Normal | Okafor | Complete | 2026-08-18 | 4 | 4.5 | 0 | 0 | 0 | Line 1 | Planned | 14 | 2026-08-31 | 0 | 1 | 0 | 216 | 216 | Complete | Yes | 2026-08-17 | OK
| WO-26-0413 | 2026-08-17 | FL-02 | Weekly pouch filler PM: jaws and film path | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-08-19 | 3 | 3.5 | 40 | 0 | 0 | Line 2 | Planned | 14 | 2026-08-31 | 0 | 2 | 0 | 168 | 208 | Complete | Yes | 2026-08-17 | OK
| WO-26-0414 | 2026-08-17 | PL-01 | Weekly lubrication route, Lines 1 and 2 | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-08-17 | 5 | 5.5 | 0 | 0 | 0 | End of line | Planned | 14 | 2026-08-31 | 0 | 0 | 0 | 264 | 264 | Complete | Yes | 2026-08-17 | OK
| WO-26-0415 | 2026-08-18 | CH-01 | Monthly chiller PM: condenser clean, refrigerant check | Preventive (PM) | P3 Normal | Mehta | Complete | 2026-08-25 | 3 | 3 | 55 | 0 | 0 | Utilities | Planned | 14 | 2026-09-01 | 0 | 7 | 0 | 144 | 199 | Complete | Yes | 2026-08-18 | OK
| WO-26-0416 | 2026-08-18 | CS-02 | Monthly case packer PM: vacuum, glue, guards | Preventive (PM) | P3 Normal | Mehta | Complete | 2026-08-25 | 3 | 2.5 | 120 | 0 | 0 | Line 2 | Planned | 14 | 2026-09-01 | 0 | 7 | 0 | 120 | 240 | Complete | Yes | 2026-08-18 | OK
| WO-26-0417 | 2026-08-18 | FL-02 | Pouch film tracking off | Corrective repair | P3 Normal | Okafor | Complete | 2026-09-03 | 8 | 9.5 | 220 | 0 | 0 | Line 2 | Corrective | 14 | 2026-09-01 | 0 | 16 | 0 | 456 | 676 | Complete | No | 2026-08-18 | OK
| WO-26-0418 | 2026-08-19 | AC-01 | Vibration route: compressors, pumps, mixer gearboxes | Predictive (PdM) | P3 Normal | Mehta | Complete | 2026-08-20 | 6 | 6 | 0 | 0 | 0 | Utilities | Planned | 14 | 2026-09-02 | 0 | 1 | 0 | 288 | 288 | Complete | Yes | 2026-08-19 | OK
| WO-26-0419 | 2026-08-19 | FL-01 | Filler valve leaking, bottles under-filled | Emergency breakdown | P1 Immediate | Okafor | Complete | 2026-08-21 | 4 | 5.5 | 416 | 0 | 4.5 | Line 1 | Emergency | 1 | 2026-08-20 | 0 | 2 | 0 | 264 | 680 | Complete | No | 2026-08-19 | OK
| WO-26-0420 | 2026-08-19 | MX-02 | Monthly mixer PM: gearbox oil, seals | Preventive (PM) | P3 Normal | Mehta | Complete | 2026-08-24 | 2.5 | 3 | 30 | 0 | 0 | Processing | Planned | 14 | 2026-09-02 | 0 | 5 | 0 | 144 | 174 | Complete | Yes | 2026-08-19 | OK
| WO-26-0421 | 2026-08-19 | PS-01 | Monthly pasteuriser PM: plate pack and probes | Preventive (PM) | P3 Normal | Mehta | Complete | 2026-08-28 | 5 | 6 | 30 | 0 | 0 | Processing | Planned | 14 | 2026-09-02 | 0 | 9 | 0 | 288 | 318 | Complete | Yes | 2026-08-19 | OK
| WO-26-0422 | 2026-08-19 | PS-01 | Pasteuriser temperature alarm | Corrective repair | P3 Normal | Lindqvist | Complete | 2026-09-02 | 2 | 2 | 0 | 0 | 0 | Processing | Corrective | 14 | 2026-09-02 | 0 | 14 | 0 | 96 | 96 | Complete | Yes | 2026-08-19 | OK
| WO-26-0423 | 2026-08-20 | CS-02 | Case erector vacuum cup torn | Corrective repair | P3 Normal | Lindqvist | Complete | 2026-08-31 | 4 | 4 | 90 | 0 | 0 | Line 2 | Corrective | 14 | 2026-09-03 | 0 | 11 | 0 | 192 | 282 | Complete | Yes | 2026-08-20 | OK
| WO-26-0424 | 2026-08-20 | FL-02 | Pouch sealing jaw temperature low | Corrective repair | P3 Normal | Okafor | Complete | 2026-08-30 | 6 | 8 | 220 | 0 | 0 | Line 2 | Corrective | 14 | 2026-09-03 | 0 | 10 | 0 | 384 | 604 | Complete | Yes | 2026-08-20 | OK
| WO-26-0425 | 2026-08-20 | LB-01 | Monthly labeller PM: glue system, sensors | Preventive (PM) | P3 Normal | Lindqvist | Complete | 2026-08-21 | 2 | 2 | 30 | 0 | 0 | Line 1 | Planned | 14 | 2026-09-03 | 0 | 1 | 0 | 96 | 126 | Complete | Yes | 2026-08-20 | OK
| WO-26-0426 | 2026-08-20 | MX-01 | Monthly mixer PM: gearbox oil, seals | Preventive (PM) | P3 Normal | Lindqvist | Complete | 2026-08-26 | 2.5 | 3 | 30 | 0 | 0 | Processing | Planned | 14 | 2026-09-03 | 0 | 6 | 0 | 144 | 174 | Complete | Yes | 2026-08-20 | OK
| WO-26-0427 | 2026-08-21 | FL-01 | Filler valve leaking, bottles under-filled | Emergency breakdown | P1 Immediate | Okafor | Complete | 2026-08-22 | 5 | 5.5 | 416 | 0 | 5 | Line 1 | Emergency | 1 | 2026-08-22 | 0 | 1 | 0 | 264 | 680 | Complete | Yes | 2026-08-21 | OK
| WO-26-0428 | 2026-08-24 | AC-01 | Fix compressed-air leaks found in survey | Improvement | P3 Normal | Lindqvist | Complete | 2026-09-03 | 12 | 12 | 180 | 0 | 0 | Utilities | Planned | 14 | 2026-09-07 | 0 | 10 | 0 | 576 | 756 | Complete | Yes | 2026-08-24 | OK
| WO-26-0429 | 2026-08-24 | CP-01 | Weekly capper PM: chucks and torque check | Preventive (PM) | P3 Normal | Okafor | Complete | 2026-08-27 | 2 | 2 | 0 | 0 | 0 | Line 1 | Planned | 14 | 2026-09-07 | 0 | 3 | 0 | 96 | 96 | Complete | Yes | 2026-08-24 | OK
| WO-26-0430 | 2026-08-24 | CS-02 | Case erector vacuum cup torn | Emergency breakdown | P1 Immediate | Okafor | Complete | 2026-08-25 | 5 | 6.5 | 120 | 0 | 7 | Line 2 | Emergency | 1 | 2026-08-25 | 0 | 1 | 0 | 312 | 432 | Complete | Yes | 2026-08-24 | OK
| WO-26-0431 | 2026-08-24 | FL-01 | Weekly filler PM: seals, nozzles, lubrication | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-08-27 | 4 | 4 | 25 | 0 | 0 | Line 1 | Planned | 14 | 2026-09-07 | 0 | 3 | 0 | 192 | 217 | Complete | Yes | 2026-08-24 | OK
| WO-26-0432 | 2026-08-24 | FL-02 | Weekly pouch filler PM: jaws and film path | Preventive (PM) | P3 Normal | Lindqvist | Complete | 2026-08-27 | 3 | 3.5 | 60 | 0 | 0 | Line 2 | Planned | 14 | 2026-09-07 | 0 | 3 | 0 | 168 | 228 | Complete | Yes | 2026-08-24 | OK
| WO-26-0433 | 2026-08-24 | PL-01 | Weekly lubrication route, Lines 1 and 2 | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-08-24 | 5 | 5 | 0 | 0 | 0 | End of line | Planned | 14 | 2026-09-07 | 0 | 0 | 0 | 240 | 240 | Complete | Yes | 2026-08-24 | OK
| WO-26-0434 | 2026-08-25 | BL-01 | Thermography survey: panels, motors, steam traps | Predictive (PdM) | P3 Normal | Okafor | Complete | 2026-08-27 | 5 | 5 | 0 | 0 | 0 | Utilities | Planned | 14 | 2026-09-08 | 0 | 2 | 0 | 240 | 240 | Complete | Yes | 2026-08-25 | OK
| WO-26-0435 | 2026-08-25 | CS-02 | Case erector vacuum cup torn | Corrective repair | P2 Urgent | Mehta | Complete | 2026-08-26 | 2 | 2 | 150 | 0 | 0 | Line 2 | Corrective | 3 | 2026-08-28 | 0 | 1 | 0 | 96 | 246 | Complete | Yes | 2026-08-25 | OK
| WO-26-0436 | 2026-08-26 | CS-02 | Hot-melt glue gun blocked | Emergency breakdown | P1 Immediate | Lindqvist | Complete | 2026-08-28 | 3 | 4 | 0 | 0 | 4.5 | Line 2 | Emergency | 1 | 2026-08-27 | 0 | 2 | 0 | 192 | 192 | Complete | No | 2026-08-26 | OK
| WO-26-0437 | 2026-08-26 | PL-01 | Palletiser light curtain fault | Corrective repair | P3 Normal | Okafor | Complete | 2026-09-12 | 12 | 10 | 35 | 0 | 0 | End of line | Corrective | 14 | 2026-09-09 | 0 | 17 | 0 | 480 | 515 | Complete | No | 2026-08-26 | OK
| WO-26-0438 | 2026-08-27 | MX-01 | Mixer discharge valve sticking | Corrective repair | P2 Urgent | Mehta | Complete | 2026-08-29 | 16 | 20 | 220 | 0 | 0 | Processing | Corrective | 3 | 2026-08-30 | 0 | 2 | 0 | 960 | 1180 | Complete | Yes | 2026-08-27 | OK
| WO-26-0439 | 2026-08-28 | FL-02 | Pouch film tracking off | Emergency breakdown | P1 Immediate | Rivera | Complete | 2026-08-28 | 4 | 6 | 480 | 0 | 5.5 | Line 2 | Emergency | 1 | 2026-08-29 | 0 | 0 | 0 | 288 | 768 | Complete | Yes | 2026-08-28 | OK
| WO-26-0440 | 2026-08-28 | LB-01 | Label sensor misreading | Corrective repair | P3 Normal | Okafor | Waiting parts |  | 8 | 0 | 0 | 0 | 0 | Line 1 | Corrective | 14 | 2026-09-11 | 1 | 42 | 8 | 0 | 0 | Overdue |  | 2026-08-28 | OK
| WO-26-0441 | 2026-08-31 | CP-01 | Torque head bearing noisy | Corrective repair | P3 Normal | Lindqvist | Complete | 2026-09-12 | 3 | 3.5 | 90 | 0 | 0 | Line 1 | Corrective | 14 | 2026-09-14 | 0 | 12 | 0 | 168 | 258 | Complete | Yes | 2026-08-31 | OK
| WO-26-0442 | 2026-08-31 | CP-01 | Weekly capper PM: chucks and torque check | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-09-03 | 2 | 2 | 0 | 0 | 0 | Line 1 | Planned | 14 | 2026-09-14 | 0 | 3 | 0 | 96 | 96 | Complete | Yes | 2026-08-31 | OK
| WO-26-0443 | 2026-08-31 | FL-01 | Level probe fault, filler stopped | Emergency breakdown | P1 Immediate | Mehta | Complete | 2026-09-01 | 2 | 2.5 | 0 | 0 | 2 | Line 1 | Emergency | 1 | 2026-09-01 | 0 | 1 | 0 | 120 | 120 | Complete | Yes | 2026-08-31 | OK
| WO-26-0444 | 2026-08-31 | FL-01 | Weekly filler PM: seals, nozzles, lubrication | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-09-01 | 4 | 4 | 25 | 0 | 0 | Line 1 | Planned | 14 | 2026-09-14 | 0 | 1 | 0 | 192 | 217 | Complete | Yes | 2026-08-31 | OK
| WO-26-0445 | 2026-08-31 | FL-02 | Weekly pouch filler PM: jaws and film path | Preventive (PM) | P3 Normal | Okafor | Complete | 2026-09-02 | 3 | 3 | 0 | 0 | 0 | Line 2 | Planned | 14 | 2026-09-14 | 0 | 2 | 0 | 144 | 144 | Complete | Yes | 2026-08-31 | OK
| WO-26-0446 | 2026-08-31 | PL-01 | Weekly lubrication route, Lines 1 and 2 | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-08-31 | 5 | 5.5 | 0 | 0 | 0 | End of line | Planned | 14 | 2026-09-14 | 0 | 0 | 0 | 264 | 264 | Complete | Yes | 2026-08-31 | OK
| WO-26-0447 | 2026-09-01 | CP-01 | Cap chute blocked | Corrective repair | P3 Normal | Rivera | Complete | 2026-09-09 | 12 | 14 | 35 | 0 | 0 | Line 1 | Corrective | 14 | 2026-09-15 | 0 | 8 | 0 | 672 | 707 | Complete | Yes | 2026-09-01 | OK
| WO-26-0448 | 2026-09-01 | MX-02 | Load cell drift on mixer 2 | Corrective repair | P3 Normal | Lindqvist | Waiting parts |  | 6 | 0 | 0 | 0 | 0 | Processing | Corrective | 14 | 2026-09-15 | 1 | 38 | 6 | 0 | 0 | Overdue |  | 2026-09-01 | OK
| WO-26-0449 | 2026-09-02 | AC-01 | Vibration route: compressors, pumps, mixer gearboxes | Predictive (PdM) | P3 Normal | Mehta | Complete | 2026-09-03 | 6 | 6 | 0 | 0 | 0 | Utilities | Planned | 14 | 2026-09-16 | 0 | 1 | 0 | 288 | 288 | Complete | Yes | 2026-09-02 | OK
| WO-26-0450 | 2026-09-02 | CH-01 | Chiller low refrigerant pressure | Corrective repair | P2 Urgent | Rivera | Complete | 2026-09-06 | 3 | 3.5 | 220 | 0 | 0 | Utilities | Corrective | 3 | 2026-09-05 | 0 | 4 | 0 | 168 | 388 | Complete | No | 2026-09-02 | OK
| WO-26-0451 | 2026-09-02 | CP-01 | Capper chuck slipping, loose caps | Corrective repair | P3 Normal | Mehta | Complete | 2026-09-14 | 3 | 3 | 0 | 0 | 0 | Line 1 | Corrective | 14 | 2026-09-16 | 0 | 12 | 0 | 144 | 144 | Complete | Yes | 2026-09-02 | OK
| WO-26-0452 | 2026-09-02 | FL-01 | Filler valve leaking (duplicate request) | Corrective repair | P2 Urgent | Rivera | Cancelled |  | 2 | 0 | 0 | 0 | 0 | Line 1 | Corrective | 3 | 2026-09-05 | 0 |  | 0 | 0 | 0 |  |  | 2026-09-02 | OK
| WO-26-0453 | 2026-09-03 | CS-02 | Hot-melt glue gun blocked | Corrective repair | P3 Normal | Rivera | Complete | 2026-09-08 | 16 | 19 | 90 | 0 | 0 | Line 2 | Corrective | 14 | 2026-09-17 | 0 | 5 | 0 | 912 | 1002 | Complete | Yes | 2026-09-03 | OK
| WO-26-0454 | 2026-09-07 | CP-01 | Weekly capper PM: chucks and torque check | Preventive (PM) | P3 Normal | Lindqvist | Complete | 2026-09-07 | 2 | 2.5 | 0 | 0 | 0 | Line 1 | Planned | 14 | 2026-09-21 | 0 | 0 | 0 | 120 | 120 | Complete | Yes | 2026-09-07 | OK
| WO-26-0455 | 2026-09-07 | FL-01 | Rebuild filler valve block (spare unit) | Improvement | P3 Normal | Lindqvist | Complete | 2026-10-03 | 24 | 24 | 2400 | 0 | 0 | Line 1 | Planned | 14 | 2026-09-21 | 0 | 26 | 0 | 1152 | 3552 | Complete | No | 2026-09-07 | OK
| WO-26-0456 | 2026-09-07 | FL-01 | Weekly filler PM: seals, nozzles, lubrication | Preventive (PM) | P3 Normal | Okafor | Complete | 2026-09-08 | 4 | 4.5 | 25 | 0 | 0 | Line 1 | Planned | 14 | 2026-09-21 | 0 | 1 | 0 | 216 | 241 | Complete | Yes | 2026-09-07 | OK
| WO-26-0457 | 2026-09-07 | FL-02 | Weekly pouch filler PM: jaws and film path | Preventive (PM) | P3 Normal | Lindqvist | Complete | 2026-09-09 | 3 | 3 | 60 | 0 | 0 | Line 2 | Planned | 14 | 2026-09-21 | 0 | 2 | 0 | 144 | 204 | Complete | Yes | 2026-09-07 | OK
| WO-26-0458 | 2026-09-07 | LB-01 | Label sensor misreading | Corrective repair | P3 Normal | Okafor | Complete | 2026-09-19 | 8 | 8 | 90 | 0 | 0 | Line 1 | Corrective | 14 | 2026-09-21 | 0 | 12 | 0 | 384 | 474 | Complete | Yes | 2026-09-07 | OK
| WO-26-0459 | 2026-09-07 | LB-01 | Monthly labeller PM: glue system, sensors | Preventive (PM) | P3 Normal | Okafor | Complete | 2026-09-09 | 2 | 2 | 30 | 0 | 0 | Line 1 | Planned | 14 | 2026-09-21 | 0 | 2 | 0 | 96 | 126 | Complete | Yes | 2026-09-07 | OK
| WO-26-0460 | 2026-09-07 | MX-02 | Load cell drift on mixer 2 | Corrective repair | P3 Normal | Lindqvist | Complete | 2026-09-20 | 2 | 2 | 0 | 0 | 0 | Processing | Corrective | 14 | 2026-09-21 | 0 | 13 | 0 | 96 | 96 | Complete | Yes | 2026-09-07 | OK
| WO-26-0461 | 2026-09-07 | PL-01 | Weekly lubrication route, Lines 1 and 2 | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-09-22 | 5 | 5 | 0 | 0 | 0 | End of line | Planned | 14 | 2026-09-21 | 0 | 15 | 0 | 240 | 240 | Complete | No | 2026-09-07 | OK
| WO-26-0462 | 2026-09-08 | BL-01 | Monthly boiler PM: water treatment, burner check | Preventive (PM) | P3 Normal | Okafor | Complete | 2026-09-09 | 4 | 5 | 55 | 0 | 0 | Utilities | Planned | 14 | 2026-09-22 | 0 | 1 | 0 | 240 | 295 | Complete | Yes | 2026-09-08 | OK
| WO-26-0463 | 2026-09-08 | BL-01 | Thermography survey: panels, motors, steam traps | Predictive (PdM) | P3 Normal | Okafor | Complete | 2026-09-10 | 5 | 5 | 0 | 0 | 0 | Utilities | Planned | 14 | 2026-09-22 | 0 | 2 | 0 | 240 | 240 | Complete | Yes | 2026-09-08 | OK
| WO-26-0464 | 2026-09-08 | CH-01 | Chiller low refrigerant pressure | Corrective repair | P2 Urgent | Lindqvist | Complete | 2026-09-12 | 6 | 5 | 0 | 0 | 0 | Utilities | Corrective | 3 | 2026-09-11 | 0 | 4 | 0 | 240 | 240 | Complete | No | 2026-09-08 | OK
| WO-26-0465 | 2026-09-08 | CH-01 | Monthly chiller PM: condenser clean, refrigerant check | Preventive (PM) | P3 Normal | Mehta | Complete | 2026-09-17 | 3 | 3.5 | 120 | 0 | 0 | Utilities | Planned | 14 | 2026-09-22 | 0 | 9 | 0 | 168 | 288 | Complete | Yes | 2026-09-08 | OK
| WO-26-0466 | 2026-09-08 | CS-02 | Monthly case packer PM: vacuum, glue, guards | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-09-10 | 3 | 3 | 120 | 0 | 0 | Line 2 | Planned | 14 | 2026-09-22 | 0 | 2 | 0 | 144 | 264 | Complete | Yes | 2026-09-08 | OK
| WO-26-0467 | 2026-09-08 | FL-01 | Infeed conveyor chain jumped | Emergency breakdown | P1 Immediate | Mehta | Complete | 2026-09-09 | 2 | 2 | 768 | 0 | 2 | Line 1 | Emergency | 1 | 2026-09-09 | 0 | 1 | 0 | 96 | 864 | Complete | Yes | 2026-09-08 | OK
| WO-26-0468 | 2026-09-09 | AC-01 | Monthly compressor PM: filters, oil, drains | Preventive (PM) | P3 Normal | Okafor | Complete | 2026-09-16 | 3 | 3 | 55 | 0 | 0 | Utilities | Planned | 14 | 2026-09-23 | 0 | 7 | 0 | 144 | 199 | Complete | Yes | 2026-09-09 | OK
| WO-26-0469 | 2026-09-09 | FL-01 | Filler valve leaking, bottles under-filled | Emergency breakdown | P1 Immediate | Rivera | Complete | 2026-09-09 | 4 | 4.5 | 72 | 0 | 4 | Line 1 | Emergency | 1 | 2026-09-10 | 0 | 0 | 0 | 216 | 288 | Complete | Yes | 2026-09-09 | OK
| WO-26-0470 | 2026-09-09 | MX-01 | Agitator gearbox oil leak | Corrective repair | P3 Normal | Lindqvist | Complete | 2026-09-25 | 12 | 10 | 0 | 0 | 0 | Processing | Corrective | 14 | 2026-09-23 | 0 | 16 | 0 | 480 | 480 | Complete | No | 2026-09-09 | OK
| WO-26-0471 | 2026-09-09 | MX-01 | Monthly mixer PM: gearbox oil, seals | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-09-15 | 2.5 | 3 | 0 | 0 | 0 | Processing | Planned | 14 | 2026-09-23 | 0 | 6 | 0 | 144 | 144 | Complete | Yes | 2026-09-09 | OK
| WO-26-0472 | 2026-09-09 | PS-01 | Plate pack gasket leak | Corrective repair | P3 Normal | Rivera | Complete | 2026-09-13 | 6 | 6 | 90 | 0 | 0 | Processing | Corrective | 14 | 2026-09-23 | 0 | 4 | 0 | 288 | 378 | Complete | Yes | 2026-09-09 | OK
| WO-26-0473 | 2026-09-10 | LB-01 | Labels creasing, glue roller worn | Corrective repair | P3 Normal | Rivera | Complete | 2026-09-25 | 6 | 8 | 90 | 0 | 0 | Line 1 | Corrective | 14 | 2026-09-24 | 0 | 15 | 0 | 384 | 474 | Complete | No | 2026-09-10 | OK
| WO-26-0474 | 2026-09-10 | MX-02 | Monthly mixer PM: gearbox oil, seals | Preventive (PM) | P3 Normal | Mehta | Complete | 2026-09-14 | 2.5 | 3 | 80 | 0 | 0 | Processing | Planned | 14 | 2026-09-24 | 0 | 4 | 0 | 144 | 224 | Complete | Yes | 2026-09-10 | OK
| WO-26-0475 | 2026-09-10 | PL-01 | Layer gripper air leak | Corrective repair | P2 Urgent | Rivera | Complete | 2026-09-13 | 3 | 3 | 150 | 0 | 0 | End of line | Corrective | 3 | 2026-09-13 | 0 | 3 | 0 | 144 | 294 | Complete | Yes | 2026-09-10 | OK
| WO-26-0476 | 2026-09-10 | PS-01 | Monthly pasteuriser PM: plate pack and probes | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-09-19 | 5 | 5 | 120 | 0 | 0 | Processing | Planned | 14 | 2026-09-24 | 0 | 9 | 0 | 240 | 360 | Complete | Yes | 2026-09-10 | OK
| WO-26-0477 | 2026-09-11 | CS-02 | Hot-melt glue gun blocked | Corrective repair | P2 Urgent | Lindqvist | Complete | 2026-09-14 | 4 | 5 | 220 | 0 | 0 | Line 2 | Corrective | 3 | 2026-09-14 | 0 | 3 | 0 | 240 | 460 | Complete | Yes | 2026-09-11 | OK
| WO-26-0478 | 2026-09-11 | FL-01 | Level probe fault, filler stopped | Corrective repair | P2 Urgent | Okafor | Waiting parts |  | 2 | 0 | 0 | 0 | 0 | Line 1 | Corrective | 3 | 2026-09-14 | 1 | 28 | 2 | 0 | 0 | Overdue |  | 2026-09-11 | OK
| WO-26-0479 | 2026-09-14 | CP-01 | Weekly capper PM: chucks and torque check | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-09-17 | 2 | 2 | 40 | 0 | 0 | Line 1 | Planned | 14 | 2026-09-28 | 0 | 3 | 0 | 96 | 136 | Complete | Yes | 2026-09-14 | OK
| WO-26-0480 | 2026-09-14 | FL-01 | Weekly filler PM: seals, nozzles, lubrication | Preventive (PM) | P3 Normal | Okafor | Complete | 2026-09-16 | 4 | 4.5 | 40 | 0 | 0 | Line 1 | Planned | 14 | 2026-09-28 | 0 | 2 | 0 | 216 | 256 | Complete | Yes | 2026-09-14 | OK
| WO-26-0481 | 2026-09-14 | FL-02 | Weekly pouch filler PM: jaws and film path | Preventive (PM) | P3 Normal | Okafor | Complete | 2026-09-14 | 3 | 2.5 | 60 | 0 | 0 | Line 2 | Planned | 14 | 2026-09-28 | 0 | 0 | 0 | 120 | 180 | Complete | Yes | 2026-09-14 | OK
| WO-26-0482 | 2026-09-14 | LB-01 | Fit glue-level sensor to labeller | Improvement | P4 Opportunity | Okafor | In progress |  | 8 | 4 | 0 | 0 | 0 | Line 1 | Planned | 45 | 2026-10-29 | 1 | 25 | 4 | 192 | 192 | OK |  | 2026-09-14 | OK
| WO-26-0483 | 2026-09-14 | PL-01 | Weekly lubrication route, Lines 1 and 2 | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-09-17 | 5 | 4.5 | 0 | 0 | 0 | End of line | Planned | 14 | 2026-09-28 | 0 | 3 | 0 | 216 | 216 | Complete | Yes | 2026-09-14 | OK
| WO-26-0484 | 2026-09-15 | AC-01 | Compressor high-temperature trip | Emergency breakdown | P1 Immediate | Rivera | Complete | 2026-09-15 | 6 | 8 | 900 | 0 | 8 | Utilities | Emergency | 1 | 2026-09-16 | 0 | 0 | 0 | 384 | 1284 | Complete | Yes | 2026-09-15 | OK
| WO-26-0485 | 2026-09-15 | LB-01 | Labels creasing, glue roller worn | Corrective repair | P3 Normal | Rivera | Complete | 2026-09-28 | 12 | 13 | 150 | 0 | 0 | Line 1 | Corrective | 14 | 2026-09-29 | 0 | 13 | 0 | 624 | 774 | Complete | Yes | 2026-09-15 | OK
| WO-26-0486 | 2026-09-16 | AC-01 | Vibration route: compressors, pumps, mixer gearboxes | Predictive (PdM) | P3 Normal | Mehta | Complete | 2026-09-17 | 6 | 6 | 0 | 0 | 0 | Utilities | Planned | 14 | 2026-09-30 | 0 | 1 | 0 | 288 | 288 | Complete | Yes | 2026-09-16 | OK
| WO-26-0487 | 2026-09-16 | MX-01 | Mixer discharge valve sticking | Corrective repair | P2 Urgent | Mehta | Complete | 2026-09-18 | 12 | 13 | 150 | 0 | 0 | Processing | Corrective | 3 | 2026-09-19 | 0 | 2 | 0 | 624 | 774 | Complete | Yes | 2026-09-16 | OK
| WO-26-0488 | 2026-09-17 | MX-01 | Mixer discharge valve sticking | Corrective repair | P3 Normal | Mehta | Complete | 2026-09-26 | 4 | 3.5 | 0 | 0 | 0 | Processing | Corrective | 14 | 2026-10-01 | 0 | 9 | 0 | 168 | 168 | Complete | Yes | 2026-09-17 | OK
| WO-26-0489 | 2026-09-18 | FL-01 | Fill nozzle seal failed | Emergency breakdown | P1 Immediate | Okafor | Complete | 2026-09-18 | 2 | 3 | 0 | 0 | 2 | Line 1 | Emergency | 1 | 2026-09-19 | 0 | 0 | 0 | 144 | 144 | Complete | Yes | 2026-09-18 | OK
| WO-26-0490 | 2026-09-21 | CP-01 | Weekly capper PM: chucks and torque check | Preventive (PM) | P3 Normal | Lindqvist | Complete | 2026-09-22 | 2 | 2 | 0 | 0 | 0 | Line 1 | Planned | 14 | 2026-10-05 | 0 | 1 | 0 | 96 | 96 | Complete | Yes | 2026-09-21 | OK
| WO-26-0491 | 2026-09-21 | CS-02 | Hot-melt glue gun blocked | Corrective repair | P3 Normal | Rivera | Complete | 2026-10-05 | 12 | 13.5 | 0 | 0 | 0 | Line 2 | Corrective | 14 | 2026-10-05 | 0 | 14 | 0 | 648 | 648 | Complete | Yes | 2026-09-21 | OK
| WO-26-0492 | 2026-09-21 | CS-02 | Replace case packer guard interlocks | Safety or compliance | P2 Urgent | Okafor | Complete | 2026-09-24 | 6 | 6 | 410 | 0 | 0 | Line 2 | Planned | 3 | 2026-09-24 | 0 | 3 | 0 | 288 | 698 | Complete | Yes | 2026-09-21 | OK
| WO-26-0493 | 2026-09-21 | FL-01 | Filler valve leaking, bottles under-filled | Emergency breakdown | P1 Immediate | Okafor | Complete | 2026-09-23 | 2 | 3 | 0 | 0 | 3 | Line 1 | Emergency | 1 | 2026-09-22 | 0 | 2 | 0 | 144 | 144 | Complete | No | 2026-09-21 | OK
| WO-26-0494 | 2026-09-21 | FL-01 | Weekly filler PM: seals, nozzles, lubrication | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-09-23 | 4 | 3.5 | 40 | 0 | 0 | Line 1 | Planned | 14 | 2026-10-05 | 0 | 2 | 0 | 168 | 208 | Complete | Yes | 2026-09-21 | OK
| WO-26-0495 | 2026-09-21 | FL-02 | Weekly pouch filler PM: jaws and film path | Preventive (PM) | P3 Normal | Okafor | Complete | 2026-09-23 | 3 | 2.5 | 40 | 0 | 0 | Line 2 | Planned | 14 | 2026-10-05 | 0 | 2 | 0 | 120 | 160 | Complete | Yes | 2026-09-21 | OK
| WO-26-0496 | 2026-09-21 | PL-01 | Weekly lubrication route, Lines 1 and 2 | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-09-23 | 5 | 6 | 0 | 0 | 0 | End of line | Planned | 14 | 2026-10-05 | 0 | 2 | 0 | 288 | 288 | Complete | Yes | 2026-09-21 | OK
| WO-26-0497 | 2026-09-22 | BL-01 | Thermography survey: panels, motors, steam traps | Predictive (PdM) | P3 Normal | Okafor | Complete | 2026-09-24 | 5 | 5 | 0 | 0 | 0 | Utilities | Planned | 14 | 2026-10-06 | 0 | 2 | 0 | 240 | 240 | Complete | Yes | 2026-09-22 | OK
| WO-26-0498 | 2026-09-22 | CP-01 | Cap chute blocked | Corrective repair | P2 Urgent | Okafor | Complete | 2026-09-26 | 2 | 2 | 0 | 0 | 0 | Line 1 | Corrective | 3 | 2026-09-25 | 0 | 4 | 0 | 96 | 96 | Complete | No | 2026-09-22 | OK
| WO-26-0499 | 2026-09-22 | MX-01 | Mixer discharge valve sticking | Corrective repair | P3 Normal | Mehta | Complete | 2026-10-09 | 6 | 7.5 | 150 | 0 | 0 | Processing | Corrective | 14 | 2026-10-06 | 0 | 17 | 0 | 360 | 510 | Complete | No | 2026-09-22 | OK
| WO-26-0500 | 2026-09-23 | AC-01 | Air dryer drain stuck | Corrective repair | P2 Urgent | Mehta | Complete | 2026-09-24 | 4 | 4.5 | 150 | 0 | 0 | Utilities | Corrective | 3 | 2026-09-26 | 0 | 1 | 0 | 216 | 366 | Complete | Yes | 2026-09-23 | OK
| WO-26-0501 | 2026-09-23 | CH-01 | Glycol pump seal weeping | Corrective repair | P3 Normal | Mehta | Complete | 2026-09-26 | 2 | 1.5 | 340 | 0 | 0 | Utilities | Corrective | 14 | 2026-10-07 | 0 | 3 | 0 | 72 | 412 | Complete | Yes | 2026-09-23 | OK
| WO-26-0502 | 2026-09-24 | PL-01 | Palletiser light curtain fault | Corrective repair | P3 Normal | Mehta | Open |  | 16 | 0 | 0 | 0 | 0 | End of line | Corrective | 14 | 2026-10-08 | 1 | 15 | 16 | 0 | 0 | Overdue |  | 2026-09-24 | OK
| WO-26-0503 | 2026-09-25 | AC-01 | Compressor high-temperature trip | Corrective repair | P3 Normal | Rivera | Open |  | 16 | 0 | 0 | 0 | 0 | Utilities | Corrective | 14 | 2026-10-09 | 1 | 14 | 16 | 0 | 0 | Due soon |  | 2026-09-25 | OK
| WO-26-0504 | 2026-09-25 | CH-01 | Chiller low refrigerant pressure | Corrective repair | P2 Urgent | Mehta | Complete | 2026-09-26 | 12 | 13 | 0 | 0 | 0 | Utilities | Corrective | 3 | 2026-09-28 | 0 | 1 | 0 | 624 | 624 | Complete | Yes | 2026-09-25 | OK
| WO-26-0505 | 2026-09-28 | BL-01 | Boiler annual inspection preparation | Safety or compliance | P3 Normal | Mehta | In progress |  | 12 | 6 | 0 | 0 | 0 | Utilities | Planned | 14 | 2026-10-12 | 1 | 11 | 6 | 288 | 288 | Due soon |  | 2026-09-28 | OK
| WO-26-0506 | 2026-09-28 | CP-01 | Weekly capper PM: chucks and torque check | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-09-28 | 2 | 2 | 25 | 0 | 0 | Line 1 | Planned | 14 | 2026-10-12 | 0 | 0 | 0 | 96 | 121 | Complete | Yes | 2026-09-28 | OK
| WO-26-0507 | 2026-09-28 | FL-01 | Level probe fault, filler stopped | Corrective repair | P3 Normal | Okafor | Complete | 2026-10-05 | 2 | 2.5 | 220 | 0 | 0 | Line 1 | Corrective | 14 | 2026-10-12 | 0 | 7 | 0 | 120 | 340 | Complete | Yes | 2026-09-28 | OK
| WO-26-0508 | 2026-09-28 | FL-01 | Weekly filler PM: seals, nozzles, lubrication | Preventive (PM) | P3 Normal | Okafor | Complete | 2026-10-01 | 4 | 4 | 0 | 0 | 0 | Line 1 | Planned | 14 | 2026-10-12 | 0 | 3 | 0 | 192 | 192 | Complete | Yes | 2026-09-28 | OK
| WO-26-0509 | 2026-09-28 | FL-02 | Weekly pouch filler PM: jaws and film path | Preventive (PM) | P3 Normal | Lindqvist | Complete | 2026-10-01 | 3 | 3.5 | 25 | 0 | 0 | Line 2 | Planned | 14 | 2026-10-12 | 0 | 3 | 0 | 168 | 193 | Complete | Yes | 2026-09-28 | OK
| WO-26-0510 | 2026-09-28 | PL-01 | Weekly lubrication route, Lines 1 and 2 | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-09-30 | 5 | 6 | 25 | 0 | 0 | End of line | Planned | 14 | 2026-10-12 | 0 | 2 | 0 | 288 | 313 | Complete | Yes | 2026-09-28 | OK
| WO-26-0511 | 2026-09-28 | PS-01 | Plate pack gasket leak | Corrective repair | P3 Normal | Rivera | Complete | 2026-10-03 | 3 | 3 | 150 | 0 | 0 | Processing | Corrective | 14 | 2026-10-12 | 0 | 5 | 0 | 144 | 294 | Complete | Yes | 2026-09-28 | OK
| WO-26-0512 | 2026-09-29 | CP-01 | Cap chute blocked | Emergency breakdown | P1 Immediate | Mehta | Complete | 2026-10-01 | 4 | 5.5 | 260 | 0 | 4.5 | Line 1 | Emergency | 1 | 2026-09-30 | 0 | 2 | 0 | 264 | 524 | Complete | No | 2026-09-29 | OK
| WO-26-0513 | 2026-09-29 | CS-02 | Case erector vacuum cup torn | Emergency breakdown | P1 Immediate | Lindqvist | Complete | 2026-10-01 | 3 | 4 | 260 | 0 | 3.5 | Line 2 | Emergency | 1 | 2026-09-30 | 0 | 2 | 0 | 192 | 452 | Complete | No | 2026-09-29 | OK
| WO-26-0514 | 2026-09-29 | CS-02 | Hot-melt glue gun blocked | Corrective repair | P3 Normal | Okafor | In progress |  | 4 | 0 | 150 | 0 | 0 | Line 2 | Corrective | 14 | 2026-10-13 | 1 | 10 | 4 | 0 | 150 | OK |  | 2026-09-29 | OK
| WO-26-0515 | 2026-09-30 | AC-01 | Vibration route: compressors, pumps, mixer gearboxes | Predictive (PdM) | P3 Normal | Mehta | Complete | 2026-10-01 | 6 | 6 | 0 | 0 | 0 | Utilities | Planned | 14 | 2026-10-14 | 0 | 1 | 0 | 288 | 288 | Complete | Yes | 2026-09-30 | OK
| WO-26-0516 | 2026-09-30 | CP-01 | Capper chuck slipping, loose caps | Corrective repair | P3 Normal | Lindqvist | Complete | 2026-10-09 | 3 | 3 | 150 | 0 | 0 | Line 1 | Corrective | 14 | 2026-10-14 | 0 | 9 | 0 | 144 | 294 | Complete | Yes | 2026-09-30 | OK
| WO-26-0517 | 2026-09-30 | CS-02 | Case erector vacuum cup torn | Emergency breakdown | P1 Immediate | Okafor | Complete | 2026-09-30 | 3 | 3 | 260 | 0 | 5 | Line 2 | Emergency | 1 | 2026-10-01 | 0 | 0 | 0 | 144 | 404 | Complete | Yes | 2026-09-30 | OK
| WO-26-0518 | 2026-10-01 | CS-02 | Case erector vacuum cup torn | Corrective repair | P2 Urgent | Rivera | Complete | 2026-10-04 | 8 | 8 | 220 | 0 | 0 | Line 2 | Corrective | 3 | 2026-10-04 | 0 | 3 | 0 | 384 | 604 | Complete | Yes | 2026-10-01 | OK
| WO-26-0519 | 2026-10-01 | FL-01 | Level probe fault, filler stopped | Corrective repair | P2 Urgent | Okafor | Waiting parts |  | 12 | 0 | 0 | 0 | 0 | Line 1 | Corrective | 3 | 2026-10-04 | 1 | 8 | 12 | 0 | 0 | Overdue |  | 2026-10-01 | OK
| WO-26-0520 | 2026-10-02 | CH-01 | Glycol pump seal weeping | Corrective repair | P2 Urgent | Mehta | Complete | 2026-10-06 | 12 | 12.5 | 90 | 0 | 0 | Utilities | Corrective | 3 | 2026-10-05 | 0 | 4 | 0 | 600 | 690 | Complete | No | 2026-10-02 | OK
| WO-26-0521 | 2026-10-02 | CP-01 | Cap chute blocked | Corrective repair | P3 Normal | Lindqvist | Complete | 2026-10-08 | 2 | 2.5 | 35 | 0 | 0 | Line 1 | Corrective | 14 | 2026-10-16 | 0 | 6 | 0 | 120 | 155 | Complete | Yes | 2026-10-02 | OK
| WO-26-0522 | 2026-10-05 | AC-01 | Air dryer drain stuck | Corrective repair | P3 Normal | Lindqvist | In progress |  | 8 | 4 | 150 | 0 | 0 | Utilities | Corrective | 14 | 2026-10-19 | 1 | 4 | 4 | 192 | 342 | OK |  | 2026-10-05 | OK
| WO-26-0523 | 2026-10-05 | CP-01 | Weekly capper PM: chucks and torque check | Preventive (PM) | P3 Normal | Lindqvist | Complete | 2026-10-05 | 2 | 2.5 | 40 | 0 | 0 | Line 1 | Planned | 14 | 2026-10-19 | 0 | 0 | 0 | 120 | 160 | Complete | Yes | 2026-10-05 | OK
| WO-26-0524 | 2026-10-05 | CS-02 | Monthly case packer PM: vacuum, glue, guards | Preventive (PM) | P3 Normal | Okafor | Open |  | 3 | 0 | 0 | 0 | 0 | Line 2 | Planned | 14 | 2026-10-19 | 1 | 4 | 3 | 0 | 0 | OK |  | 2026-10-05 | OK
| WO-26-0525 | 2026-10-05 | FL-01 | Weekly filler PM: seals, nozzles, lubrication | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-10-08 | 4 | 5 | 0 | 0 | 0 | Line 1 | Planned | 14 | 2026-10-19 | 0 | 3 | 0 | 240 | 240 | Complete | Yes | 2026-10-05 | OK
| WO-26-0526 | 2026-10-05 | FL-02 | Weekly pouch filler PM: jaws and film path | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-10-08 | 3 | 3 | 0 | 0 | 0 | Line 2 | Planned | 14 | 2026-10-19 | 0 | 3 | 0 | 144 | 144 | Complete | Yes | 2026-10-05 | OK
| WO-26-0527 | 2026-10-05 | LB-01 | Monthly labeller PM: glue system, sensors | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-10-08 | 2 | 2 | 80 | 0 | 0 | Line 1 | Planned | 14 | 2026-10-19 | 0 | 3 | 0 | 96 | 176 | Complete | Yes | 2026-10-05 | OK
| WO-26-0528 | 2026-10-05 | MX-02 | Monthly mixer PM: gearbox oil, seals | Preventive (PM) | P3 Normal | Okafor | Complete | 2026-10-09 | 2.5 | 2 | 30 | 0 | 0 | Processing | Planned | 14 | 2026-10-19 | 0 | 4 | 0 | 96 | 126 | Complete | Yes | 2026-10-05 | OK
| WO-26-0529 | 2026-10-05 | PL-01 | Layer gripper air leak | Corrective repair | P3 Normal | Okafor | Open |  | 4 | 0 | 0 | 0 | 0 | End of line | Corrective | 14 | 2026-10-19 | 1 | 4 | 4 | 0 | 0 | OK |  | 2026-10-05 | OK
| WO-26-0530 | 2026-10-05 | PL-01 | Replace palletiser layer gripper cylinders | Corrective repair | P3 Normal | Rivera | Waiting parts |  | 10 | 0 | 0 | 0 | 0 | End of line | Corrective | 14 | 2026-10-19 | 1 | 4 | 10 | 0 | 0 | OK |  | 2026-10-05 | OK
| WO-26-0531 | 2026-10-05 | PL-01 | Weekly lubrication route, Lines 1 and 2 | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-10-05 | 5 | 5.5 | 0 | 0 | 0 | End of line | Planned | 14 | 2026-10-19 | 0 | 0 | 0 | 264 | 264 | Complete | Yes | 2026-10-05 | OK
| WO-26-0532 | 2026-10-06 | BL-01 | Thermography survey: panels, motors, steam traps | Predictive (PdM) | P3 Normal | Okafor | Complete | 2026-10-08 | 5 | 5 | 0 | 0 | 0 | Utilities | Planned | 14 | 2026-10-20 | 0 | 2 | 0 | 240 | 240 | Complete | Yes | 2026-10-06 | OK
| WO-26-0533 | 2026-10-06 | FL-01 | Level probe fault, filler stopped | Emergency breakdown | P1 Immediate | Rivera | Complete | 2026-10-06 | 6 | 6.5 | 416 | 0 | 5.5 | Line 1 | Emergency | 1 | 2026-10-07 | 0 | 0 | 0 | 312 | 728 | Complete | Yes | 2026-10-06 | OK
| WO-26-0534 | 2026-10-06 | FL-01 | Level probe fault, filler stopped | Corrective repair | P3 Normal | Lindqvist | In progress |  | 16 | 4 | 0 | 0 | 0 | Line 1 | Corrective | 14 | 2026-10-20 | 1 | 3 | 12 | 192 | 192 | OK |  | 2026-10-06 | OK
| WO-26-0535 | 2026-10-06 | MX-01 | Agitator gearbox oil leak | Corrective repair | P3 Normal | Mehta | In progress |  | 8 | 2 | 150 | 0 | 0 | Processing | Corrective | 14 | 2026-10-20 | 1 | 3 | 6 | 96 | 246 | OK |  | 2026-10-06 | OK
| WO-26-0536 | 2026-10-06 | MX-01 | Monthly mixer PM: gearbox oil, seals | Preventive (PM) | P3 Normal | Mehta | Open |  | 2.5 | 0 | 0 | 0 | 0 | Processing | Planned | 14 | 2026-10-20 | 1 | 3 | 2.5 | 0 | 0 | OK |  | 2026-10-06 | OK
| WO-26-0537 | 2026-10-07 | BL-01 | Burner flame failure | Corrective repair | P2 Urgent | Mehta | Complete | 2026-10-09 | 4 | 4.5 | 340 | 0 | 0 | Utilities | Corrective | 3 | 2026-10-10 | 0 | 2 | 0 | 216 | 556 | Complete | Yes | 2026-10-07 | OK
| WO-26-0538 | 2026-10-07 | PS-01 | Monthly pasteuriser PM: plate pack and probes | Preventive (PM) | P3 Normal | Mehta | Complete | 2026-10-09 | 5 | 5 | 0 | 0 | 0 | Processing | Planned | 14 | 2026-10-21 | 0 | 2 | 0 | 240 | 240 | Complete | Yes | 2026-10-07 | OK
| WO-26-0539 | 2026-10-08 | AC-01 | Monthly compressor PM: filters, oil, drains | Preventive (PM) | P3 Normal | Rivera | Open |  | 3 | 0 | 0 | 0 | 0 | Utilities | Planned | 14 | 2026-10-22 | 1 | 1 | 3 | 0 | 0 | OK |  | 2026-10-08 | OK
| WO-26-0540 | 2026-10-08 | BL-01 | Boiler feed pump noisy | Corrective repair | P3 Normal | Okafor | Waiting parts |  | 8 | 0 | 0 | 0 | 0 | Utilities | Corrective | 14 | 2026-10-22 | 1 | 1 | 8 | 0 | 0 | OK |  | 2026-10-08 | OK
| WO-26-0541 | 2026-10-08 | BL-01 | Monthly boiler PM: water treatment, burner check | Preventive (PM) | P3 Normal | Okafor | Open |  | 4 | 0 | 0 | 0 | 0 | Utilities | Planned | 14 | 2026-10-22 | 1 | 1 | 4 | 0 | 0 | OK |  | 2026-10-08 | OK
| WO-26-0542 | 2026-10-08 | CH-01 | Monthly chiller PM: condenser clean, refrigerant check | Preventive (PM) | P3 Normal | Rivera | Complete | 2026-10-09 | 3 | 2.5 | 55 | 0 | 0 | Utilities | Planned | 14 | 2026-10-22 | 0 | 1 | 0 | 120 | 175 | Complete | Yes | 2026-10-08 | OK
| WO-26-0543 | 2026-10-09 | CH-01 | Chiller low refrigerant pressure | Corrective repair | P3 Normal | Lindqvist | Open |  | 6 | 0 | 0 | 0 | 0 | Utilities | Corrective | 14 | 2026-10-23 | 1 | 0 | 6 | 0 | 0 | OK |  | 2026-10-09 | OK
| WO-26-0544 | 2026-10-09 | FL-01 | Level probe fault, filler stopped | Emergency breakdown | P1 Immediate | Rivera | Complete | 2026-10-09 | 6 | 8.5 | 72 | 0 | 5 | Line 1 | Emergency | 1 | 2026-10-10 | 0 | 0 | 0 | 408 | 480 | Complete | Yes | 2026-10-09 | OK
Formulas:
Due date = IF(tblWorkOrders[[#This Row],[WO no.]]="","",IF(tblWorkOrders[[#This Row],[Target (days)]]="","",tblWorkOrders[[#This Row],[Date raised]]+tblWorkOrders[[#This Row],[Target (days)]]))
View date = IF(tblWorkOrders[[#This Row],[WO no.]]="","",IF(AND(tblWorkOrders[[#This Row],[Date raised]]>=FFrom,tblWorkOrders[[#This Row],[Date raised]]<=FTo),tblWorkOrders[[#This Row],[Date raised]],""))

## Dashboard
Maintenance Work Order Log
| Backlog, overdue and emergency work, on-time completion, and where maintenance hours and money go. | [8 empty] | mfgcalcs.com
| Raised from |  |  |  | Raised to
Period figures: 144 work orders raised between the dates (blank = all). Backlog figures: every order open on the status date, 9 Oct 2026.
| BACKLOG (CREW-WEEKS) |  | EMERGENCY WORK SHARE |  |  | COMPLETED ON TIME |  |  | OVERDUE OPEN ORDERS
| 1.8708 |  | 11.19% |  |  | 86.44% |  |  | 10
| 3 |  | 10% |  |  | 90% |  |  | Open past their priority's target date
| On target |  | Above target |  |  | Near target
| BACKLOG (PERSON-HOURS) |  | OPEN WORK ORDERS |  |  | PLANNED WORK SHARE (HOURS) |  |  | MAINTENANCE COST (USD)
| 224.5 |  | 25 |  |  | 46.55% |  |  | 45769
| Estimated hours left on open orders |  | Open, Waiting parts or In progress |  |  | PM, PdM, improvement and compliance hours |  |  | Labour + parts + contractors, period
Weekly flow (the 8 weeks up to the status date; not filtered)
| Week starting (Mon) | Raised | Emergency raised | Completed | Completed on time | Hours on completed orders | Open at week end
| 2026-08-17 | 19 | 2 | 10 | 9 | 40 | 15
| 2026-08-24 | 13 | 3 | 17 | 16 | 86.5 | 11
| 2026-08-31 | 12 | 1 | 11 | 9 | 54 | 12
| 2026-09-07 | 25 | 2 | 16 | 14 | 92 | 21
| 2026-09-14 | 11 | 2 | 17 | 17 | 79 | 15
| 2026-09-21 | 15 | 1 | 15 | 10 | 75.5 | 15
| 2026-09-28 | 17 | 3 | 12 | 9 | 82 | 20
| 2026-10-05 | 23 | 2 | 18 | 16 | 93.5 | 25
By work category
| Work category | Orders (period) | Share of orders | Actual hours (period) | Share of hours | Total cost (period) | Open now | Backlog (h)
USD
| Emergency | 16 | 11.19% | 78 | 12.08% | 8184 | 0 | 0
| Corrective | 52 | 36.36% | 267 | 41.36% | 17731 | 15 | 120
| Planned | 75 | 52.45% | 300.5 | 46.55% | 19854 | 10 | 104.5
| Open backlog by priority (average age, status date) |  |  |  |  | Maintenance cost by asset, period (Pareto)
| Priority | Open now | Overdue | Backlog (h) | Age (days) | Rank | Asset |  | Total cost | Share | Cumulative | Helper: Asset (list order) | Helper: value (-1 = unused slot) | Helper: rank, ties by list order
| P1 Immediate | 0 | 0 | 0 |  |  |  |  | USD | % | %
| P2 Urgent | 2 | 2 | 14 | 18 | 1 | FL-01 |  | 10767 | 23.52% | 23.52% | MX-01 | 3676 | 4
| P3 Normal | 19 | 5 | 134.5 | 17.8947 | 2 | CS-02 |  | 6074 | 13.27% | 36.8% | MX-02 | 620 | 12
| P4 Opportunity | 4 | 3 | 76 | 62.25 | 3 | AC-01 |  | 4989 | 10.9% | 47.7% | PS-01 | 1830 | 11
[6 empty] | 4 | MX-01 |  | 3676 | 8.032% | 55.73% | FL-01 | 10767 | 1
| Workload by technician (hours: period) |  |  |  |  | 5 | CH-01 |  | 3518 | 7.686% | 63.41% | CP-01 | 3159 | 7
| Assigned to | Open orders | Backlog (h) | Hours |  | 6 | FL-02 |  | 3509 | 7.667% | 71.08% | LB-01 | 2342 | 10
| Rivera | 4 | 35 | 220.5 |  | 7 | CP-01 |  | 3159 | 6.902% | 77.98% | FL-02 | 3509 | 6
| Okafor | 10 | 59 | 136 |  | 8 | PL-01 |  | 2898 | 6.332% | 84.31% | CS-02 | 6074 | 2
| Lindqvist | 5 | 44 | 131 |  | 9 | BL-01 |  | 2387 | 5.215% | 89.53% | PL-01 | 2898 | 8
| Mehta | 5 | 46.5 | 156 |  | 10 | LB-01 |  | 2342 | 5.117% | 94.65% | AC-01 | 4989 | 3
| Contractor | 1 | 40 | 2 |  | 11 | PS-01 |  | 1830 | 3.998% | 98.65% | BL-01 | 2387 | 9
[6 empty] | 12 | MX-02 |  | 620 | 1.355% | 100% | CH-01 | 3518 | 5
[7 empty] | Total |  | 45769
The Dashboard shows the 12 assets, 4 priorities and 5 technicians of the Setup lists. If you add more, extend those blocks (see Method) or they will not appear here.

## Method
Maintenance Work Order Log
| How every number is calculated, with assumptions, limits and sources. |  | mfgcalcs.com
What this workbook calculates
A work order is one job for one asset. This workbook keeps every order in one table and works out, per row, when it is due (date raised plus the days its priority allows), whether it is still open, how old it is, how many estimated hours are left, and what it cost. The Dashboard then answers the questions a maintenance meeting asks: how many weeks of work are waiting for the crew, what is overdue, how much of the work is emergency break-in, how much finishes on time, and which assets take the money. Backlog figures are a snapshot of every open order on the status date; period figures use the orders raised between the Dashboard's From and To dates.
Calculations
| Quantity | How it is calculated | Units
| Due date | Date raised + the priority's target days (Setup). | date
| Open | 1 when the status is Open, Waiting parts or In progress; 0 when Complete or Cancelled. | 1/0
| Age | Open order: status date - date raised. Completed order: date completed - date raised. Cancelled: blank. | days
| Remaining hours | Open order: MAX(0, estimated hours - actual hours booked). Closed orders: 0. This is the order's share of the backlog. | person-h
| Labour cost | Actual hours x loaded labour rate (Setup). | currency
| Total cost | Labour cost + parts cost + contractor cost. | currency
| Due status | Cancelled: blank. Closed: Complete. Open: Overdue when the status date is after the due date, Due soon when the due date is within the Setup window, otherwise OK. | -
| On time | Completed orders only: Yes when date completed <= due date, otherwise No. | -
| Backlog (person-hours) | Sum of remaining hours over all open orders. | person-h
| Net crew hours | Crew hours per week - hours per week committed elsewhere (Setup). | person-h/week
| Backlog (crew-weeks) | Backlog person-hours / net crew hours per week: how long the crew would take to clear it with no new work (the Maintenance Backlog Weeks calculator). | weeks
| Emergency work share | Orders raised in the period whose work type is in the Emergency category / all orders raised in the period, cancelled orders excluded (the Emergency Work Ratio calculator). | %
| Completed on time | Orders raised in the period, completed and with On time = Yes / orders raised in the period with status Complete. | %
| Planned work share | Actual hours on Planned-category orders / all actual hours, orders raised in the period. | %
| Open at week end | Orders raised before the end of the week (not cancelled) - orders completed before the end of the week. | orders
| Age by priority | Average age of the open orders of each priority: sum of their ages / number of open orders. | days
| Cost Pareto | Total cost per asset for the period, ranked largest first by COUNTIF ranks (ties keep list order), with share and cumulative share. Hidden helper columns AO:AQ on the Dashboard hold the unsorted values and ranks. | currency, %
Assumptions
| • | Estimated hours are the planner's estimate for the whole job; remaining hours assume the estimate still holds.
| • | Net crew hours are available for backlog work every week; holidays, absence and overtime are not modelled week by week.
| • | Costs belong to the period in which the order was raised, not the period in which the money was spent.
| • | The categories Emergency, Corrective and Planned are fixed words the Dashboard counts; rename work types freely, but map each one to one of the three.
Limitations
| • | Status is what you typed: an order left Open after the work was done stays in the backlog until you update it.
| • | Backlog weeks do not distinguish crafts: an electrical backlog cannot be cleared by mechanics, so check the by-technician block too.
| • | The weekly block shows the eight weeks up to the status date and counts orders by their own dates; orders logged before the first row are not known to it.
| • | The Dashboard has fixed blocks for 12 assets, 4 priorities and 5 technicians; longer Setup lists need the blocks extended (copy a block row and change its slot number), and the Dashboard warns when a list is longer.
Agreement with the live calculator
Backlog (crew-weeks) is the live Maintenance Backlog Weeks calculator's formula: recorded backlog labour / (weekly gross crew capacity - weekly other commitments); here the backlog labour is summed from the open orders' remaining hours. The emergency work share is the Emergency Work Ratio calculator's emergency orders / total orders. The workbook adds the log, due dates, costs and the Dashboard. The template's reference implementation is checked against both calculator engines on every build, for each calculator's own example (1,680 backlog hours, 320 crew hours and 80 other hours: 7.0 weeks; 42 emergency orders of 310: 13.5%) and for the Verify sheet's test orders.
Open the Maintenance Backlog Weeks Calculator
Self-check
The Verify sheet holds fixed test inputs. Its formulas are the same formula text as the working sheets, placed against those inputs, and each result is compared with a value computed independently by the template's Python reference implementation when the file was built. If you edit a formula on a working sheet, the Verify sheet still tests the original formula text, so it will not detect your change.
Sources and standards
| • | EN 13306:2017, Maintenance - Maintenance terminology (corrective, preventive and condition-based maintenance), by definition.
| • | SMRP Best Practices, Maintenance and Reliability Body of Knowledge metrics (backlog, planned work and reactive work metrics), by name; no published target values are used.
| • | MFG Calcs Maintenance Backlog Weeks calculator (maintenance-backlog-weeks) and Emergency Work Ratio calculator (emergency-work-ratio): the same formulas for one snapshot.
Standards are cited by name so you can look them up; no copyrighted standard text or tables are reproduced. Statistical constants used are public.
Version history
| Version | Change | Date
| 1.0.0 | First release. | 15 October 2026
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Verify
Maintenance Work Order Log
| Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference. | [25 empty] | mfgcalcs.com
| Self-check status |  | PASS |  | 21 of 21 checks pass
This sheet recomputes the workbook's own formulas on fixed test inputs and compares each result with a value computed independently by the template's Python reference implementation when the file was built. Every row should read PASS. The test inputs are fixed and do not change when you edit Setup or the working sheets.
Checks
| No. | Check |  |  |  | Expected (reference) | Workbook result | Difference | Tolerance | Result
| 1 | T-1: due date (raised + 3 days) |  |  |  | 2026-03-05 | 2026-03-05 | 0 | 1e-09 | PASS
| 2 | T-1: age of a completed order |  |  |  | 2 | 2 | 0 | 1e-09 | PASS
| 3 | T-1: labour cost (3.5 h x 50) |  |  |  | 175 | 175 | 0 | 1e-09 | PASS
| 4 | T-1: total cost |  |  |  | 295 | 295 | 0 | 1e-09 | PASS
| 5 | T-1: on time |  |  |  | Yes | Yes |  | exact | PASS
| 6 | T-2: emergency finished after its 1-day target |  |  |  | No | No |  | exact | PASS
| 7 | T-2: total cost with a contractor |  |  |  | 550 | 550 | 0 | 1e-09 | PASS
| 8 | T-3: open order age to the status date |  |  |  | 21 | 21 | 0 | 1e-09 | PASS
| 9 | T-3: remaining hours |  |  |  | 4 | 4 | 0 | 1e-09 | PASS
| 10 | T-3: due status |  |  |  | Overdue | Overdue |  | exact | PASS
| 11 | T-4: due status (due in 3 days) |  |  |  | Due soon | Due soon |  | exact | PASS
| 12 | T-5: remaining never below zero (actual > estimate) |  |  |  | 0 | 0 | 0 | 1e-09 | PASS
| 13 | T-5: due status (not yet due) |  |  |  | OK | OK |  | exact | PASS
| 14 | T-6: cancelled order is closed |  |  |  | 0 | 0 | 0 | 1e-09 | PASS
| 15 | T-7: Check reports completed before raised |  |  |  | Completed before raised | Completed before raised |  | exact | PASS
| 16 | All rows: backlog person-hours (Dashboard formula) |  |  |  | 12 | 12 | 0 | 1e-09 | PASS
| 17 | All rows: backlog crew-weeks (Dashboard formula) |  |  |  | 0.05 | 0.05 | 0 | 1e-09 | PASS
| 18 | All rows: emergency work share (Dashboard formula) |  |  |  | 16.67% | 16.67% | 0 | 1e-09 | PASS
| 19 | All rows: completed on time (Dashboard formula) |  |  |  | 66.67% | 66.67% | 0 | 1e-09 | PASS
| 20 | All rows: planned work share of hours (Dashboard formula) |  |  |  | 65.12% | 65.12% | 0 | 1e-09 | PASS
| 21 | All rows: overdue open orders (Dashboard formula) |  |  |  | 1 | 1 | 0 | 1e-09 | PASS
Fixed test inputs
White cells are fixed test inputs; blue cells are the workbook's formulas evaluated on them.
Parameters
| Status date |  |  | 2026-03-13
| Loaded labour rate |  |  | 50
| Due soon window (days) |  |  | 3
| Filter: raised from (0 = no limit) |  |  | 0
| Filter: raised to (2958465 = no limit) |  |  | 2958465
Test crew capacity (the Maintenance Backlog Weeks calculator's example)
| Crew hours per week |  |  | 320 | person-h/week
| Hours per week committed elsewhere |  |  | 80 | person-h/week
| Net crew hours for backlog work |  |  | 240 | person-h/week
Test table: WorkOrders
[12 empty] | USD | USD | [8 empty] | USD | USD
| WO no. | Date raised | Asset | Description | Work type | Priority | Assigned to | Status | Date completed | Estimated (h) | Actual (h) | Parts cost | Contractor cost | Downtime (h) | Area | Category | Target (days) | Due date | Open | Age (days) | Remaining (h) | Labour cost | Total cost | Due status | On time | View date | Check
| T-1 | 2026-03-02 | A1 | Completed on time | Corrective repair | P2 Urgent | Tech | Complete | 2026-03-04 | 4 | 3.5 | 120 | 0 | 0 | Line 1 | Corrective | 3 | 2026-03-05 | 0 | 2 | 0 | 175 | 295 | Complete | Yes | 2026-03-02 | OK
| T-2 | 2026-03-02 | A1 | Emergency, finished late | Emergency breakdown | P1 Immediate | Tech | Complete | 2026-03-04 | 2 | 3 | 0 | 400 | 2.5 | Line 1 | Emergency | 1 | 2026-03-03 | 0 | 2 | 0 | 150 | 550 | Complete | No | 2026-03-02 | OK
| T-3 | 2026-02-20 | A2 | Open past its due date | Preventive (PM) | P3 Normal | Tech | In progress |  | 6 | 2 | 0 | 0 | 0 | Line 1 | Planned | 14 | 2026-03-06 | 1 | 21 | 4 | 100 | 100 | Overdue |  | 2026-02-20 | OK
| T-4 | 2026-03-02 | A2 | Due within the window | Corrective repair | P3 Normal | Tech | Waiting parts |  | 8 | 0 | 0 | 0 | 0 | Line 1 | Corrective | 14 | 2026-03-16 | 1 | 11 | 8 | 0 | 0 | Due soon |  | 2026-03-02 | OK
| T-5 | 2026-03-12 | A3 | Open, not yet due | Improvement | P4 Opportunity | Tech | Open |  | 10 | 12 | 0 | 0 | 0 | Line 1 | Planned | 30 | 2026-04-11 | 1 | 1 | 0 | 600 | 600 | OK |  | 2026-03-12 | OK
| T-6 | 2026-03-03 | A3 | Cancelled | Corrective repair | P2 Urgent | Tech | Cancelled |  | 2 | 0 | 0 | 0 | 0 | Line 1 | Corrective | 3 | 2026-03-06 | 0 |  | 0 | 0 | 0 |  |  | 2026-03-03 | OK
| T-7 | 2026-03-10 | A1 | Check: completed before raised | Corrective repair | P3 Normal | Tech | Complete | 2026-03-09 | 1 | 1 | 0 | 0 | 0 | Line 1 | Corrective | 14 | 2026-03-24 | 0 | -1 | 0 | 50 | 50 | Complete | Yes | 2026-03-10 | Completed before raised
Formulas:
Due date = IF(tblVerifyWorkOrders[[#This Row],[WO no.]]="","",IF(tblVerifyWorkOrders[[#This Row],[Target (days)]]="","",tblVerifyWorkOrders[[#This Row],[Date raised]]+tblVerifyWorkOrders[[#This Row],[Target (days)]]))
View date = IF(tblVerifyWorkOrders[[#This Row],[WO no.]]="","",IF(AND(tblVerifyWorkOrders[[#This Row],[Date raised]]>=E40,tblVerifyWorkOrders[[#This Row],[Date raised]]<=E41),tblVerifyWorkOrders[[#This Row],[Date raised]],""))