## Start Here
PPAP Submission Tracker
| Read this first: what the workbook does and how to use it. |  |  |  | mfgcalcs.com
PPAP Submission Tracker
Track every PPAP package and the elements it needs, and see what is overdue, how ready each open package is and how often customers approve first time.
For: Supplier quality engineers, APQP and launch leads, and quality managers at automotive and other suppliers who submit or review PPAP packages.
Version 1.0.0 · updated 15 October 2026
Quick start
| 1. | On Setup, set the status date, the due-soon window, your first-time approval target and the workload figures, then replace the example customers, reasons and functions.
| 2. | On PPAP Log, add one row per package: PPAP number, part, customer, reason, submission level, owner and the customer's required date.
| 3. | On Element Tracker, add one row for each element the package needs, with owner, due date and status; mark it Complete with the date when it is done.
| 4. | When you submit, type the submitted date; when the customer decides, type the disposition and decision date (and the resubmit-by date after a rejection).
| 5. | Move the status date forward each time you update the log, then open the Dashboard and filter by customer if you need to.
What is in this workbook
|  | Start Here | Read this first: what the workbook does and how to use it.
|  | Setup | Status date, due-soon window, your targets, the workload figures, and the customer, reason, function and element lists.
|  | PPAP Log | One row per PPAP package: part, customer, level, required date, submission and the customer's decision.
|  | Element Tracker | One row per element a package needs: owner, due date, status and the date it was done.
|  | Dashboard | Open and overdue PPAP packages, element readiness, first-time approval and where packages get stuck.
|  | Method | How every number is calculated, with assumptions, limits and sources.
|  | Verify | Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference.
Colour key
|  | Input | Yellow cells are yours: type a value or pick from the list. Each one says what it accepts when you click it.
|  | Calculated | Blue cells are formulas. They update as you type; overwrite one and that row stops calculating.
|  | Note | Grey boxes are guidance and labelled example data.
|  | Status words | On target / PASS / OK | Near target / Check | Below target / FAIL
Status is always written in words; the colour only repeats it, so the workbook reads the same in black-and-white print and for colour-blind readers.
Self-check and links
|  | Self-check | PASS | 21 of 21 checks pass
The Verify sheet recomputes this workbook's formulas on fixed test inputs and compares them with an independent reference calculation. PASS means every check agreed when you opened the file.
|  | Run it live | PPAP Review Workload Calculator on mfgcalcs.com
|  | Latest version | mfgcalcs.com/templates/ppap-tracker
|  | More free templates | mfgcalcs.com/templates
|  | Version | 1.0.0 (updated 15 October 2026)
About the example data
Every number already in this workbook is example data for Halden Stamping, a fictional business invented for this template, so the dashboard and charts show something meaningful on day one. It covers 14 PPAP packages for three fictional customers from February to December 2026, with the status date 9 October 2026, generated from a fixed seed. To clear it: on each working sheet, select the example rows of the table, right-click and choose Delete > Table Rows. The formulas stay, and every new row you type below the table picks them up.
Good to know
| • | Sheets Start Here, Dashboard, Method, Verify are protected without a password so formulas and layout are not overwritten by accident. To change them: Review > Unprotect Sheet.
| • | Setup and the working sheets are not protected, so tables grow as you add rows.
| • | Works in Excel 2016 and later, Microsoft 365, LibreOffice 24 and Google Sheets (File > Import). No macros, no external links, no add-ins.
| • | Money is shown in the currency you type on Setup; no exchange rates are applied.
Free from MFG Calcs - keep this credit when you share it.
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Setup
PPAP Submission Tracker
| Status date, due-soon window, your targets, the workload figures, and the customer, reason, function and element lists. |  | mfgcalcs.com
Site and status date
| Plant or company name | Halden Stamping (example)
| Status date (as of) | 2026-10-09
| Due soon window | 14 | days
| First-time approval target | 85%
Workload planning (estimates you set)
| Hours per package | 24 | h per package
| Resubmission allowance | 30%
| Hours available to the deadline | 180 | h
Targets and workload figures are yours to set; nothing here assumes an industry benchmark. 'Near target' means within 5% of the target (80.75% to 85% against an 85% target). Hours available read Near capacity above 90%.
Lists that feed the dropdowns
Edit, add or remove rows; the PPAP Log and Element Tracker dropdowns read these lists. The element list gives short labels for the 18 PPAP elements; which ones a package needs depends on your customer's requirements and the submission level (see the AIAG PPAP manual and your customer's specific requirements). Keep names unique.
Customers
| Customer | Notes
| Northline Motors (example) | Vehicle maker; PPAP through its supplier portal (fictional)
| Vantis Seating (example) | Tier 1 seating; PSW by e-mail (fictional)
| Brightway Axles (example) | Tier 1 driveline (fictional)
Reasons for submission
| Reason | Notes
| New part | First submission of a new part number
| Engineering change | Change to design records, specifications or materials
| Tooling change | Transfer, replacement or refurbishment of tooling
| Process change | New line, press, site or method
| Supplier or material change | New sub-supplier or material source
| Correction of discrepancy | Fixing a previously submitted discrepancy
Owner functions
| Function | Notes
| Quality | Supplier quality and plant quality engineers
| Engineering | Product and manufacturing engineering
| Metrology | CMM and gauge room
| Production | Press shop and assembly
| Tool room | Dies, fixtures and checking aids
| Purchasing | Sub-supplier material and certificates
PPAP elements (short labels)
| Element | No. | Usual owner
| Design records | 1 | Engineering
| Engineering change docs | 2 | Engineering
| Customer eng. approval | 3 | Engineering
| Design FMEA | 4 | Engineering
| Process flow diagram | 5 | Engineering
| Process FMEA | 6 | Quality
| Control plan | 7 | Quality
| MSA studies | 8 | Metrology
| Dimensional results | 9 | Metrology
| Material and performance tests | 10 | Purchasing
| Initial process studies | 11 | Quality
| Qualified lab documentation | 12 | Quality
| Appearance approval report | 13 | Quality
| Sample production parts | 14 | Production
| Master sample | 15 | Quality
| Checking aids | 16 | Tool room
| Customer-specific requirements | 17 | Quality
| Part submission warrant | 18 | Quality

## PPAP Log
PPAP Submission Tracker
| One row per PPAP package: part, customer, level, required date, submission and the customer's decision. | [25 empty] | mfgcalcs.com
Example data for Halden Stamping (fictional). Replace it with your own: select the example rows, right-click, Delete > Table Rows (do the same on the Element Tracker). Yellow = you type; blue = calculated; Check names any problem. Due status is measured to the status date on Setup.
| PPAP no. | Part number | Part name | Customer | Reason | Level | Owner | Required date | Submitted | Disposition | Decision date | Resubmissions | Resubmit by | Elements | Complete | Ready | Due by | Due status | Submitted on time | Customer review (days) | First-time approval | Open | To submit | In view | Open rank | Check | Notes
| P26-01 | BR-2207 | Seat bracket LH | Vantis Seating (example) | New part | 3 | A. Kaur | 2026-03-13 | 2026-03-10 | Approved | 2026-03-27 | 0 |  | 15 | 15 | 100% | 2026-03-13 | Complete | Yes | 17 | Yes | 0 | 0 | 1 |  | OK
| P26-02 | BR-2208 | Seat bracket RH | Vantis Seating (example) | New part | 3 | A. Kaur | 2026-03-13 | 2026-03-11 | Approved | 2026-03-30 | 0 |  | 15 | 15 | 100% | 2026-03-13 | Complete | Yes | 19 | Yes | 0 | 0 | 1 |  | OK
| P26-03 | HS-4410 | Heat shield | Northline Motors (example) | New part | 3 | M. Lopez | 2026-04-24 | 2026-04-28 | Approved | 2026-06-02 | 1 |  | 15 | 15 | 100% | 2026-04-24 | Complete | No | 35 | No | 0 | 0 | 1 |  | OK | Rejected 12 May: PFMEA missing a special characteristic; resubmitted 20 May
| P26-04 | CL-118 | Hose clip | Northline Motors (example) | Engineering change | 2 | M. Lopez | 2026-05-15 | 2026-05-14 | Approved | 2026-05-22 | 0 |  | 9 | 9 | 100% | 2026-05-15 | Complete | Yes | 8 | Yes | 0 | 0 | 1 |  | OK
| P26-05 | AX-3021 | Axle bracket | Brightway Axles (example) | Tooling change | 3 | J. Novak | 2026-06-19 | 2026-06-17 | Approved | 2026-07-03 | 0 |  | 9 | 9 | 100% | 2026-06-19 | Complete | Yes | 16 | Yes | 0 | 0 | 1 |  | OK
| P26-06 | BR-2207 | Seat bracket LH rev B | Vantis Seating (example) | Engineering change | 2 | A. Kaur | 2026-07-10 | 2026-07-08 | Approved | 2026-07-21 | 0 |  | 9 | 9 | 100% | 2026-07-10 | Complete | Yes | 13 | Yes | 0 | 0 | 1 |  | OK
| P26-07 | MT-5502 | Motor mount | Northline Motors (example) | New part | 3 | M. Lopez | 2026-08-21 | 2026-08-25 | Rejected | 2026-09-08 | 0 | 2026-10-16 | 15 | 11 | 73.33% | 2026-10-16 | Due soon | No | 14 | No | 1 | 1 | 1 | 4 | OK | Rejected 8 Sep: two hole positions out; die rework, new dimensional results and capability study
| P26-08 | BK-7710 | Brake line bracket | Brightway Axles (example) | New part | 3 | J. Novak | 2026-09-25 | 2026-09-24 | Submitted |  | 0 |  | 15 | 15 | 100% | 2026-09-25 | In progress | Yes |  |  | 1 | 0 | 1 | 1 | OK
| P26-09 | HS-4411 | Heat shield RH | Northline Motors (example) | New part | 3 | M. Lopez | 2026-10-02 | 2026-09-30 | Interim approval | 2026-10-07 | 0 |  | 15 | 15 | 100% | 2026-10-02 | In progress | Yes | 7 | No | 1 | 0 | 1 | 2 | OK | Interim: capability on flange height below the customer's requirement; 30-piece study running
| P26-10 | CV-9001 | Battery cover | Northline Motors (example) | New part | 3 | M. Lopez | 2026-10-16 |  | Open |  | 0 |  | 16 | 12 | 75% | 2026-10-16 | Due soon |  |  |  | 1 | 1 | 1 | 5 | OK
| P26-11 | BR-2310 | Seat rail bracket | Vantis Seating (example) | New part | 4 | A. Kaur | 2026-10-05 |  | Open |  | 0 |  | 15 | 13 | 86.67% | 2026-10-05 | Overdue |  |  |  | 1 | 1 | 1 | 3 | OK | Gauge for rail width late from the tool room
| P26-12 | AX-3022 | Axle bracket rev C | Brightway Axles (example) | Process change | 3 | J. Novak | 2026-11-20 |  | Open |  | 0 |  | 9 | 4 | 44.44% | 2026-11-20 | OK |  |  |  | 1 | 1 | 1 | 6 | OK
| P26-13 | HS-4410 | Heat shield rev B | Northline Motors (example) | Engineering change | 2 | M. Lopez | 2026-12-11 |  | Open |  | 0 |  | 9 | 1 | 11.11% | 2026-12-11 | OK |  |  |  | 1 | 1 | 1 | 7 | OK
| P26-14 | CL-120 | Hose clip, long | Northline Motors (example) | Engineering change | 2 | J. Novak | 2026-12-18 |  | Open |  | 0 |  | 9 | 0 | 0% | 2026-12-18 | OK |  |  |  | 1 | 1 | 1 | 8 | OK
Formulas:
Due by = IF(tblPPAPs[[#This Row],[PPAP no.]]="","",IF(AND(tblPPAPs[[#This Row],[Disposition]]="Rejected",ISNUMBER(tblPPAPs[[#This Row],[Resubmit by]])),tblPPAPs[[#This Row],[Resubmit by]],tblPPAPs[[#This Row],[Required date]]))

## Element Tracker
PPAP Submission Tracker
| One row per element a package needs: owner, due date, status and the date it was done. | [12 empty] | mfgcalcs.com
Example data for Halden Stamping (fictional). List only the elements each package needs; Part number, Customer and Open package come from the PPAP Log.
| PPAP no. | Element | Owner | Due date | Status | Done date | Part number | Customer | Open package | Days to due | Due status | In view | Check | Notes
| P26-01 | Design records | Engineering | 2026-01-02 | Complete | 2026-01-06 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | Design FMEA | Engineering | 2026-01-09 | Complete | 2026-01-06 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | Process flow diagram | Engineering | 2026-01-09 | Complete | 2026-01-10 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | Process FMEA | Quality | 2026-01-16 | Complete | 2026-01-12 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | Control plan | Quality | 2026-01-30 | Complete | 2026-01-29 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | MSA studies | Metrology | 2026-02-06 | Complete | 2026-02-01 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | Checking aids | Tool room | 2026-02-06 | Complete | 2026-02-03 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | Dimensional results | Metrology | 2026-02-13 | Complete | 2026-02-17 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | Material and performance tests | Purchasing | 2026-02-13 | Complete | 2026-02-17 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | Qualified lab documentation | Quality | 2026-02-13 | Complete | 2026-02-15 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | Initial process studies | Quality | 2026-02-20 | Complete | 2026-02-21 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | Sample production parts | Production | 2026-02-27 | Complete | 2026-02-24 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | Master sample | Quality | 2026-02-27 | Complete | 2026-02-22 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | Customer-specific requirements | Quality | 2026-03-03 | Complete | 2026-03-04 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-01 | Part submission warrant | Quality | 2026-03-10 | Complete | 2026-03-09 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Design records | Engineering | 2026-01-02 | Complete | 2026-01-06 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Design FMEA | Engineering | 2026-01-09 | Complete | 2026-01-07 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Process flow diagram | Engineering | 2026-01-09 | Complete | 2026-01-07 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Process FMEA | Quality | 2026-01-16 | Complete | 2026-01-15 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Control plan | Quality | 2026-01-30 | Complete | 2026-01-28 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | MSA studies | Metrology | 2026-02-06 | Complete | 2026-02-08 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Checking aids | Tool room | 2026-02-06 | Complete | 2026-02-06 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Dimensional results | Metrology | 2026-02-13 | Complete | 2026-02-13 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Material and performance tests | Purchasing | 2026-02-13 | Complete | 2026-02-14 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Qualified lab documentation | Quality | 2026-02-13 | Complete | 2026-02-17 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Initial process studies | Quality | 2026-02-20 | Complete | 2026-02-14 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Sample production parts | Production | 2026-02-27 | Complete | 2026-03-01 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Master sample | Quality | 2026-02-27 | Complete | 2026-02-28 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Customer-specific requirements | Quality | 2026-03-03 | Complete | 2026-03-03 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-02 | Part submission warrant | Quality | 2026-03-10 | Complete | 2026-03-07 | BR-2208 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-03 | Design records | Engineering | 2026-02-13 | Complete | 2026-02-14 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | Design FMEA | Engineering | 2026-02-20 | Complete | 2026-02-20 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | Process flow diagram | Engineering | 2026-02-20 | Complete | 2026-02-17 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | Process FMEA | Quality | 2026-02-27 | Complete | 2026-03-02 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | Control plan | Quality | 2026-03-13 | Complete | 2026-03-15 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | MSA studies | Metrology | 2026-03-20 | Complete | 2026-03-18 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | Checking aids | Tool room | 2026-03-20 | Complete | 2026-03-24 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | Dimensional results | Metrology | 2026-03-27 | Complete | 2026-03-26 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | Material and performance tests | Purchasing | 2026-03-27 | Complete | 2026-03-29 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | Qualified lab documentation | Quality | 2026-03-27 | Complete | 2026-03-28 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | Initial process studies | Quality | 2026-04-03 | Complete | 2026-04-02 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | Sample production parts | Production | 2026-04-10 | Complete | 2026-04-09 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | Master sample | Quality | 2026-04-10 | Complete | 2026-04-07 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | Customer-specific requirements | Quality | 2026-04-14 | Complete | 2026-04-15 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-03 | Part submission warrant | Quality | 2026-04-21 | Complete | 2026-04-21 | HS-4410 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-04 | Design records | Engineering | 2026-03-06 | Complete | 2026-03-01 | CL-118 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-04 | Engineering change docs | Engineering | 2026-03-16 | Complete | 2026-03-13 | CL-118 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-04 | Process FMEA | Quality | 2026-03-20 | Complete | 2026-03-21 | CL-118 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-04 | Control plan | Quality | 2026-04-03 | Complete | 2026-04-05 | CL-118 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-04 | Dimensional results | Metrology | 2026-04-17 | Complete | 2026-04-20 | CL-118 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-04 | Material and performance tests | Purchasing | 2026-04-17 | Complete | 2026-04-21 | CL-118 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-04 | Sample production parts | Production | 2026-05-01 | Complete | 2026-04-30 | CL-118 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-04 | Customer-specific requirements | Quality | 2026-05-05 | Complete | 2026-05-05 | CL-118 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-04 | Part submission warrant | Quality | 2026-05-12 | Complete | 2026-05-14 | CL-118 | Northline Motors (example) | 0 |  | Complete | 1 | OK
| P26-05 | Process flow diagram | Engineering | 2026-04-17 | Complete | 2026-04-17 | AX-3021 | Brightway Axles (example) | 0 |  | Complete | 1 | OK
| P26-05 | Process FMEA | Quality | 2026-04-24 | Complete | 2026-04-28 | AX-3021 | Brightway Axles (example) | 0 |  | Complete | 1 | OK
| P26-05 | Control plan | Quality | 2026-05-08 | Complete | 2026-05-03 | AX-3021 | Brightway Axles (example) | 0 |  | Complete | 1 | OK
| P26-05 | MSA studies | Metrology | 2026-05-15 | Complete | 2026-05-15 | AX-3021 | Brightway Axles (example) | 0 |  | Complete | 1 | OK
| P26-05 | Checking aids | Tool room | 2026-05-15 | Complete | 2026-05-10 | AX-3021 | Brightway Axles (example) | 0 |  | Complete | 1 | OK
| P26-05 | Dimensional results | Metrology | 2026-05-22 | Complete | 2026-05-17 | AX-3021 | Brightway Axles (example) | 0 |  | Complete | 1 | OK
| P26-05 | Initial process studies | Quality | 2026-05-29 | Complete | 2026-05-29 | AX-3021 | Brightway Axles (example) | 0 |  | Complete | 1 | OK
| P26-05 | Sample production parts | Production | 2026-06-05 | Complete | 2026-06-08 | AX-3021 | Brightway Axles (example) | 0 |  | Complete | 1 | OK
| P26-05 | Part submission warrant | Quality | 2026-06-16 | Complete | 2026-06-10 | AX-3021 | Brightway Axles (example) | 0 |  | Complete | 1 | OK
| P26-06 | Design records | Engineering | 2026-05-01 | Complete | 2026-05-01 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-06 | Engineering change docs | Engineering | 2026-05-11 | Complete | 2026-05-11 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-06 | Process FMEA | Quality | 2026-05-15 | Complete | 2026-05-17 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-06 | Control plan | Quality | 2026-05-29 | Complete | 2026-06-02 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-06 | Dimensional results | Metrology | 2026-06-12 | Complete | 2026-06-14 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-06 | Material and performance tests | Purchasing | 2026-06-12 | Complete | 2026-06-09 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-06 | Sample production parts | Production | 2026-06-26 | Complete | 2026-06-20 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-06 | Customer-specific requirements | Quality | 2026-06-30 | Complete | 2026-07-02 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-06 | Part submission warrant | Quality | 2026-07-07 | Complete | 2026-07-06 | BR-2207 | Vantis Seating (example) | 0 |  | Complete | 1 | OK
| P26-07 | Design records | Engineering | 2026-06-12 | Complete | 2026-06-16 | MT-5502 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-07 | Design FMEA | Engineering | 2026-06-19 | Complete | 2026-06-21 | MT-5502 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-07 | Process flow diagram | Engineering | 2026-06-19 | Complete | 2026-06-22 | MT-5502 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-07 | Process FMEA | Quality | 2026-06-26 | Complete | 2026-06-25 | MT-5502 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-07 | Control plan | Quality | 2026-07-10 | Complete | 2026-07-05 | MT-5502 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-07 | MSA studies | Metrology | 2026-07-17 | Complete | 2026-07-15 | MT-5502 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-07 | Checking aids | Tool room | 2026-07-17 | Complete | 2026-07-21 | MT-5502 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-07 | Dimensional results | Metrology | 2026-10-12 | In progress |  | MT-5502 | Northline Motors (example) | 1 | 3 | Due soon | 1 | OK | Redo after die rework
| P26-07 | Material and performance tests | Purchasing | 2026-07-24 | Complete | 2026-07-23 | MT-5502 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-07 | Qualified lab documentation | Quality | 2026-07-24 | Complete | 2026-07-26 | MT-5502 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-07 | Initial process studies | Quality | 2026-10-14 | In progress |  | MT-5502 | Northline Motors (example) | 1 | 5 | Due soon | 1 | OK | Redo after die rework
| P26-07 | Sample production parts | Production | 2026-08-07 | Complete | 2026-08-01 | MT-5502 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-07 | Master sample | Quality | 2026-08-07 | Complete | 2026-08-07 | MT-5502 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-07 | Customer-specific requirements | Quality | 2026-08-11 | In progress |  | MT-5502 | Northline Motors (example) | 1 | -59 | Overdue | 1 | OK
| P26-07 | Part submission warrant | Quality | 2026-10-15 | Not started |  | MT-5502 | Northline Motors (example) | 1 | 6 | Due soon | 1 | OK
| P26-08 | Design records | Engineering | 2026-07-17 | Complete | 2026-07-16 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | Design FMEA | Engineering | 2026-07-24 | Complete | 2026-07-26 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | Process flow diagram | Engineering | 2026-07-24 | Complete | 2026-07-28 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | Process FMEA | Quality | 2026-07-31 | Complete | 2026-07-26 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | Control plan | Quality | 2026-08-14 | Complete | 2026-08-11 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | MSA studies | Metrology | 2026-08-21 | Complete | 2026-08-19 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | Checking aids | Tool room | 2026-08-21 | Complete | 2026-08-24 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | Dimensional results | Metrology | 2026-08-28 | Complete | 2026-08-30 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | Material and performance tests | Purchasing | 2026-08-28 | Complete | 2026-08-23 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | Qualified lab documentation | Quality | 2026-08-28 | Complete | 2026-08-23 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | Initial process studies | Quality | 2026-09-04 | Complete | 2026-09-08 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | Sample production parts | Production | 2026-09-11 | Complete | 2026-09-07 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | Master sample | Quality | 2026-09-11 | Complete | 2026-09-14 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | Customer-specific requirements | Quality | 2026-09-15 | Complete | 2026-09-15 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-08 | Part submission warrant | Quality | 2026-09-22 | Complete | 2026-09-19 | BK-7710 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-09 | Design records | Engineering | 2026-07-24 | Complete | 2026-07-23 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | Design FMEA | Engineering | 2026-07-31 | Complete | 2026-07-25 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | Process flow diagram | Engineering | 2026-07-31 | Complete | 2026-07-26 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | Process FMEA | Quality | 2026-08-07 | Complete | 2026-08-07 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | Control plan | Quality | 2026-08-21 | Complete | 2026-08-19 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | MSA studies | Metrology | 2026-08-28 | Complete | 2026-08-26 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | Checking aids | Tool room | 2026-08-28 | Complete | 2026-08-25 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | Dimensional results | Metrology | 2026-09-04 | Complete | 2026-09-03 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | Material and performance tests | Purchasing | 2026-09-04 | Complete | 2026-09-01 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | Qualified lab documentation | Quality | 2026-09-04 | Complete | 2026-09-01 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | Initial process studies | Quality | 2026-09-11 | Complete | 2026-09-10 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | Sample production parts | Production | 2026-09-18 | Complete | 2026-09-18 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | Master sample | Quality | 2026-09-18 | Complete | 2026-09-22 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | Customer-specific requirements | Quality | 2026-09-22 | Complete | 2026-09-24 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-09 | Part submission warrant | Quality | 2026-09-29 | Complete | 2026-09-29 | HS-4411 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-10 | Design records | Engineering | 2026-08-07 | Complete | 2026-08-04 | CV-9001 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-10 | Design FMEA | Engineering | 2026-08-14 | Complete | 2026-08-15 | CV-9001 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-10 | Process flow diagram | Engineering | 2026-08-14 | Complete | 2026-08-14 | CV-9001 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-10 | Process FMEA | Quality | 2026-08-21 | Complete | 2026-08-16 | CV-9001 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-10 | Control plan | Quality | 2026-09-04 | Complete | 2026-08-31 | CV-9001 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-10 | MSA studies | Metrology | 2026-09-11 | Complete | 2026-09-05 | CV-9001 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-10 | Checking aids | Tool room | 2026-09-11 | Complete | 2026-09-10 | CV-9001 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-10 | Dimensional results | Metrology | 2026-09-18 | Complete | 2026-09-21 | CV-9001 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-10 | Material and performance tests | Purchasing | 2026-09-18 | Complete | 2026-09-19 | CV-9001 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-10 | Qualified lab documentation | Quality | 2026-09-18 | Complete | 2026-09-14 | CV-9001 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-10 | Initial process studies | Quality | 2026-09-25 | Complete | 2026-09-24 | CV-9001 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-10 | Appearance approval report | Quality | 2026-09-25 | Complete | 2026-09-29 | CV-9001 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-10 | Sample production parts | Production | 2026-10-02 | In progress |  | CV-9001 | Northline Motors (example) | 1 | -7 | Overdue | 1 | OK
| P26-10 | Master sample | Quality | 2026-10-02 | In progress |  | CV-9001 | Northline Motors (example) | 1 | -7 | Overdue | 1 | OK
| P26-10 | Customer-specific requirements | Quality | 2026-10-06 | Not started |  | CV-9001 | Northline Motors (example) | 1 | -3 | Overdue | 1 | OK
| P26-10 | Part submission warrant | Quality | 2026-10-13 | Not started |  | CV-9001 | Northline Motors (example) | 1 | 4 | Due soon | 1 | OK
| P26-11 | Design records | Engineering | 2026-07-27 | Complete | 2026-07-29 | BR-2310 | Vantis Seating (example) | 1 |  | Complete | 1 | OK
| P26-11 | Design FMEA | Engineering | 2026-08-03 | Complete | 2026-07-28 | BR-2310 | Vantis Seating (example) | 1 |  | Complete | 1 | OK
| P26-11 | Process flow diagram | Engineering | 2026-08-03 | Complete | 2026-07-30 | BR-2310 | Vantis Seating (example) | 1 |  | Complete | 1 | OK
| P26-11 | Process FMEA | Quality | 2026-08-10 | Complete | 2026-08-14 | BR-2310 | Vantis Seating (example) | 1 |  | Complete | 1 | OK
| P26-11 | Control plan | Quality | 2026-08-24 | Complete | 2026-08-27 | BR-2310 | Vantis Seating (example) | 1 |  | Complete | 1 | OK
| P26-11 | MSA studies | Metrology | 2026-08-31 | Complete | 2026-08-27 | BR-2310 | Vantis Seating (example) | 1 |  | Complete | 1 | OK
| P26-11 | Checking aids | Tool room | 2026-08-31 | Complete | 2026-08-30 | BR-2310 | Vantis Seating (example) | 1 |  | Complete | 1 | OK
| P26-11 | Dimensional results | Metrology | 2026-09-07 | Complete | 2026-09-10 | BR-2310 | Vantis Seating (example) | 1 |  | Complete | 1 | OK
| P26-11 | Material and performance tests | Purchasing | 2026-09-07 | Complete | 2026-09-08 | BR-2310 | Vantis Seating (example) | 1 |  | Complete | 1 | OK
| P26-11 | Qualified lab documentation | Quality | 2026-09-07 | Complete | 2026-09-10 | BR-2310 | Vantis Seating (example) | 1 |  | Complete | 1 | OK
| P26-11 | Initial process studies | Quality | 2026-09-14 | Complete | 2026-09-15 | BR-2310 | Vantis Seating (example) | 1 |  | Complete | 1 | OK
| P26-11 | Sample production parts | Production | 2026-09-21 | Complete | 2026-09-18 | BR-2310 | Vantis Seating (example) | 1 |  | Complete | 1 | OK
| P26-11 | Master sample | Quality | 2026-09-21 | Complete | 2026-09-23 | BR-2310 | Vantis Seating (example) | 1 |  | Complete | 1 | OK
| P26-11 | Customer-specific requirements | Quality | 2026-09-25 | In progress |  | BR-2310 | Vantis Seating (example) | 1 | -14 | Overdue | 1 | OK
| P26-11 | Part submission warrant | Quality | 2026-10-02 | In progress |  | BR-2310 | Vantis Seating (example) | 1 | -7 | Overdue | 1 | OK
| P26-12 | Process flow diagram | Engineering | 2026-09-18 | Complete | 2026-09-21 | AX-3022 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-12 | Process FMEA | Quality | 2026-09-25 | Complete | 2026-09-27 | AX-3022 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-12 | Control plan | Quality | 2026-10-09 | Complete | 2026-10-07 | AX-3022 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-12 | MSA studies | Metrology | 2026-10-16 | Complete | 2026-10-08 | AX-3022 | Brightway Axles (example) | 1 |  | Complete | 1 | OK
| P26-12 | Checking aids | Tool room | 2026-10-16 | In progress |  | AX-3022 | Brightway Axles (example) | 1 | 7 | Due soon | 1 | OK
| P26-12 | Dimensional results | Metrology | 2026-10-23 | In progress |  | AX-3022 | Brightway Axles (example) | 1 | 14 | Due soon | 1 | OK
| P26-12 | Initial process studies | Quality | 2026-10-30 | Not started |  | AX-3022 | Brightway Axles (example) | 1 | 21 | OK | 1 | OK
| P26-12 | Sample production parts | Production | 2026-11-06 | Not started |  | AX-3022 | Brightway Axles (example) | 1 | 28 | OK | 1 | OK
| P26-12 | Part submission warrant | Quality | 2026-11-17 | Not started |  | AX-3022 | Brightway Axles (example) | 1 | 39 | OK | 1 | OK
| P26-13 | Design records | Engineering | 2026-10-02 | Complete | 2026-09-26 | HS-4410 | Northline Motors (example) | 1 |  | Complete | 1 | OK
| P26-13 | Engineering change docs | Engineering | 2026-10-12 | In progress |  | HS-4410 | Northline Motors (example) | 1 | 3 | Due soon | 1 | OK
| P26-13 | Process FMEA | Quality | 2026-10-16 | In progress |  | HS-4410 | Northline Motors (example) | 1 | 7 | Due soon | 1 | OK
| P26-13 | Control plan | Quality | 2026-10-30 | Not started |  | HS-4410 | Northline Motors (example) | 1 | 21 | OK | 1 | OK
| P26-13 | Dimensional results | Metrology | 2026-11-13 | Not started |  | HS-4410 | Northline Motors (example) | 1 | 35 | OK | 1 | OK
| P26-13 | Material and performance tests | Purchasing | 2026-11-13 | Not started |  | HS-4410 | Northline Motors (example) | 1 | 35 | OK | 1 | OK
| P26-13 | Sample production parts | Production | 2026-11-27 | Not started |  | HS-4410 | Northline Motors (example) | 1 | 49 | OK | 1 | OK
| P26-13 | Customer-specific requirements | Quality | 2026-12-01 | Not started |  | HS-4410 | Northline Motors (example) | 1 | 53 | OK | 1 | OK
| P26-13 | Part submission warrant | Quality | 2026-12-08 | Not started |  | HS-4410 | Northline Motors (example) | 1 | 60 | OK | 1 | OK
| P26-14 | Design records | Engineering | 2026-10-09 | Not started |  | CL-120 | Northline Motors (example) | 1 | 0 | Due soon | 1 | OK
| P26-14 | Engineering change docs | Engineering | 2026-10-19 | Not started |  | CL-120 | Northline Motors (example) | 1 | 10 | Due soon | 1 | OK
| P26-14 | Process FMEA | Quality | 2026-10-23 | Not started |  | CL-120 | Northline Motors (example) | 1 | 14 | Due soon | 1 | OK
| P26-14 | Control plan | Quality | 2026-11-06 | Not started |  | CL-120 | Northline Motors (example) | 1 | 28 | OK | 1 | OK
| P26-14 | Dimensional results | Metrology | 2026-11-20 | Not started |  | CL-120 | Northline Motors (example) | 1 | 42 | OK | 1 | OK
| P26-14 | Material and performance tests | Purchasing | 2026-11-20 | Not started |  | CL-120 | Northline Motors (example) | 1 | 42 | OK | 1 | OK
| P26-14 | Sample production parts | Production | 2026-12-04 | Not started |  | CL-120 | Northline Motors (example) | 1 | 56 | OK | 1 | OK
| P26-14 | Customer-specific requirements | Quality | 2026-12-08 | Not started |  | CL-120 | Northline Motors (example) | 1 | 60 | OK | 1 | OK
| P26-14 | Part submission warrant | Quality | 2026-12-15 | Not started |  | CL-120 | Northline Motors (example) | 1 | 67 | OK | 1 | OK

## Dashboard
PPAP Submission Tracker
| Open and overdue PPAP packages, element readiness, first-time approval and where packages get stuck. | [8 empty] | mfgcalcs.com
Customer
Showing 14 packages and 175 element rows (blank filter = all customers). Status date 9 Oct 2026.
| OPEN PACKAGES | SUBMISSIONS OVERDUE |  |  |  | ELEMENTS COMPLETE |  |  | FIRST-TIME APPROVAL
| 8 | 1 |  |  |  | 68.93% |  |  | 62.5%
| Not yet approved by the customer | 0 |  |  |  | On packages not yet approved |  |  | 85%
|  | Above target | [6 empty] | Below target
| ELEMENTS OVERDUE | CUSTOMER REVIEW (DAYS) |  |  |  | PACKAGES TO SUBMIT |  |  | HOURS TO FINISH (EST.)
| 6 | 16.125 |  |  |  | 6 |  |  | 187.2
| 0 | Average, submission to decision |  |  |  | Open or rejected |  |  | x hours per package x (1 + allowance)
Above target
Open packages, earliest required date first (up to 8)
| PPAP no. | Part |  | Due by | Disposition |  | Complete | In progress | Not started | Overdue | Due status
| P26-08 | BK-7710 Brake line bracket |  | 2026-09-25 | Submitted |  | 15 | 0 | 0 | 0 | In progress
| P26-09 | HS-4411 Heat shield RH |  | 2026-10-02 | Interim approval |  | 15 | 0 | 0 | 0 | In progress
| P26-11 | BR-2310 Seat rail bracket |  | 2026-10-05 | Open |  | 13 | 2 | 0 | 2 | Overdue
| P26-07 | MT-5502 Motor mount |  | 2026-10-16 | Rejected |  | 11 | 3 | 1 | 1 | Due soon
| P26-10 | CV-9001 Battery cover |  | 2026-10-16 | Open |  | 12 | 2 | 2 | 3 | Due soon
| P26-12 | AX-3022 Axle bracket rev C |  | 2026-11-20 | Open |  | 4 | 2 | 3 | 0 | OK
| P26-13 | HS-4410 Heat shield rev B |  | 2026-12-11 | Open |  | 1 | 2 | 6 | 0 | OK
| P26-14 | CL-120 Hose clip, long |  | 2026-12-18 | Open |  | 0 | 0 | 9 | 0 | OK
Workload to finish the packages still to submit (planning estimate)
| Packages to submit |  |  | 6 | packages
| Hours per package (Setup) |  |  | 24 | h
| Hours to finish (est.) |  |  | 187.2 | h
| Hours available (Setup) |  |  | 180 | h
| Share of hours available |  |  | 104% | of hours
| Hours left over (negative = short) |  |  | -7.2 | h
| Capacity |  |  | Over capacity
By customer (all packages; not filtered)
| Customer | Packages | Approved | Open | Overdue | First-time approval | Review (days)
| Northline Motors (example) | 7 | 2 | 5 | 0 | 25% | 16
| Vantis Seating (example) | 4 | 3 | 1 | 1 | 100% | 16.3333
| Brightway Axles (example) | 3 | 1 | 2 | 0 | 100% | 16
Elements on open packages
| Element | On open packages | Complete | Open, overdue | Open, not overdue | Complete share
| Design records | 7 | 6 | 0 | 1 | 85.71%
| Engineering change docs | 2 | 0 | 0 | 2 | 0%
| Customer eng. approval | 0 | 0 | 0 | 0
| Design FMEA | 5 | 5 | 0 | 0 | 100%
| Process flow diagram | 6 | 6 | 0 | 0 | 100%
| Process FMEA | 8 | 6 | 0 | 2 | 75%
| Control plan | 8 | 6 | 0 | 2 | 75%
| MSA studies | 6 | 6 | 0 | 0 | 100%
| Dimensional results | 8 | 4 | 0 | 4 | 50%
| Material and performance tests | 7 | 5 | 0 | 2 | 71.43%
| Initial process studies | 6 | 4 | 0 | 2 | 66.67%
| Qualified lab documentation | 5 | 5 | 0 | 0 | 100%
| Appearance approval report | 1 | 1 | 0 | 0 | 100%
| Sample production parts | 8 | 4 | 1 | 3 | 50%
| Master sample | 5 | 4 | 1 | 0 | 80%
| Checking aids | 6 | 5 | 0 | 1 | 83.33%
| Customer-specific requirements | 7 | 2 | 3 | 2 | 28.57%
| Part submission warrant | 8 | 2 | 1 | 5 | 25%
The Dashboard shows the first 8 open packages by required date, the 18 elements and the 3 customers of the Setup lists. If you add more customers or elements, extend those blocks (see Method); every open package is still on the PPAP Log.
Formulas:
Due by = IF(B43="","",INDEX(tblPPAPs[Due by],MATCH(B43,tblPPAPs[PPAP no.],0)))

## Method
PPAP Submission Tracker
| How every number is calculated, with assumptions, limits and sources. |  | mfgcalcs.com
What this workbook calculates
A PPAP package is ready when every element the customer requires is complete, and done when the customer approves it. This workbook keeps one row per package on the PPAP Log and one row per required element on the Element Tracker; each package counts its own elements, and every date is compared with the status date on Setup (a typed date, so the file never changes by itself). Which elements a package needs is your call from the customer's requirements and the submission level; the workbook does not decide it.
Calculations
| Quantity | How it is calculated | Units
| Elements, complete, ready | Element rows for the package; those with Status Complete; complete / elements. | count, %
| Due status (package) | Approved: Complete. Submitted or interim approval: In progress (with the customer). Open or rejected: Overdue after the required date (the resubmit-by date after a rejection), Due soon within the Setup window, otherwise OK. | -
| Submitted on time | Yes when the submitted date is on or before the required date. | -
| Customer review | Decision date - submitted date. | days
| First-time approval | Yes: approved with no resubmission. No: approved after a resubmission, interim approval or rejected. Blank while open or with the customer. Rate = Yes / (Yes + No). | %
| Due status (element) | Complete when the status is Complete; else Overdue after the due date, Due soon within the window, otherwise OK. | -
| Elements complete (tile) | Complete element rows on packages not yet approved / all element rows on those packages. | %
| Open rank | Helper column on the PPAP Log: the order of open packages by required date (resubmit-by after a rejection), used for the Dashboard's open-package block. | -
| Hours to finish (est.) | Packages to submit (open or rejected) x hours per package x (1 + resubmission allowance), all from Setup: the PPAP Review Workload calculator's formula. | h
| Share of hours available | Hours to finish / hours available. Above 100% reads Over capacity, above 90% Near capacity. | %
Assumptions
| • | One row per package. A new package number is used for each engineering change or new submission; a resubmission after a rejection stays on the same row (count it under Resubmissions).
| • | An interim approval counts as not approved first time, and the package stays open until full approval.
| • | Element due dates are typed; the example spaces them back from the required date, process flow first and the warrant last.
| • | The workload estimate is the same for every package: it ignores how far each one has got. Use it for a launch wave, not one package.
Limitations
| • | The workbook tracks status; it does not hold the documents. Keep the package in your document system and link it in Notes.
| • | The AIAG PPAP manual's table of which elements to submit at each level and its forms (including the Part Submission Warrant) are not reproduced; use the manual and your customer's specific requirements.
| • | The Dashboard's open-package block shows the first 8 by required date; the element and customer blocks have fixed rows (a warning appears when lists grow).
Agreement with the live calculator
The workload block uses the PPAP Review Workload calculator's formula: hours required = submissions x hours per submission x (1 + resubmission rate); share of capacity = required / available; hours remaining = available - required. With the calculator's default example (35 packages, 6 h each, 30%, 320 h available) both give 273.0 h, 85.3% and 47.0 h; the template's reference is checked against the engine on every build. The workbook adds the package and element logs and the Dashboard.
Open the PPAP Review Workload Calculator
Self-check
The Verify sheet holds fixed test inputs. Its formulas are the same formula text as the working sheets, placed against those inputs, and each result is compared with a value computed independently by the template's Python reference implementation when the file was built. If you edit a formula on a working sheet, the Verify sheet still tests the original formula text, so it will not detect your change.
Sources and standards
| • | AIAG, Production Part Approval Process (PPAP), 4th edition, 2006 (element names; levels and forms by reference only).
| • | IATF 16949:2016, clause 8.3.4.4 Product approval process (referenced, not reproduced).
| • | MFG Calcs PPAP Review Workload calculator: packages x hours per package x (1 + resubmission rate).
Standards are cited by name so you can look them up; no copyrighted standard text or tables are reproduced. Statistical constants used are public.
Version history
| Version | Change | Date
| 1.0.0 | First release. | 15 October 2026
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Verify
PPAP Submission Tracker
| Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference. | [25 empty] | mfgcalcs.com
| Self-check status |  | PASS |  | 21 of 21 checks pass
This sheet recomputes the workbook's own formulas on fixed test inputs and compares each result with a value computed independently by the template's Python reference implementation when the file was built. Every row should read PASS. The test inputs are fixed and do not change when you edit Setup or the working sheets.
Checks
| No. | Check |  |  |  | Expected (reference) | Workbook result | Difference | Tolerance | Result
| 1 | A1: ready (2 of 2 elements) |  |  |  | 100% | 100% | 0 | 1e-09 | PASS
| 2 | A1: due status |  |  |  | Complete | Complete |  | exact | PASS
| 3 | A2: first-time approval after a resubmission |  |  |  | No | No |  | exact | PASS
| 4 | A2: submitted on time |  |  |  | No | No |  | exact | PASS
| 5 | A2: customer review (days) |  |  |  | 21 | 21 | 0 | 1e-09 | PASS
| 6 | A3: ready (1 of 3 elements) |  |  |  | 33.33% | 33.33% | 0 | 1e-09 | PASS
| 7 | A3: due status past the required date |  |  |  | Overdue | Overdue |  | exact | PASS
| 8 | A4: due status within the window |  |  |  | Due soon | Due soon |  | exact | PASS
| 9 | A5: rejected, judged on the resubmit-by date |  |  |  | OK | OK |  | exact | PASS
| 10 | A6: with the customer |  |  |  | In progress | In progress |  | exact | PASS
| 11 | A7: Check reports the customer |  |  |  | Customer not on Setup list | Customer not on Setup list |  | exact | PASS
| 12 | Element 4: due status |  |  |  | Overdue | Overdue |  | exact | PASS
| 13 | Element 5: due status |  |  |  | Due soon | Due soon |  | exact | PASS
| 14 | Element 9: Check reports the package |  |  |  | PPAP no. not on the log | PPAP no. not on the log |  | exact | PASS
| 15 | Open packages (Dashboard formula) |  |  |  | 4 | 4 | 0 | 1e-09 | PASS
| 16 | Submissions overdue (Dashboard formula) |  |  |  | 1 | 1 | 0 | 1e-09 | PASS
| 17 | Elements overdue (Dashboard formula) |  |  |  | 1 | 1 | 0 | 1e-09 | PASS
| 18 | Elements complete on open packages (Dashboard formula) |  |  |  | 50% | 50% | 0 | 1e-09 | PASS
| 19 | Packages to submit (Dashboard formula) |  |  |  | 3 | 3 | 0 | 1e-09 | PASS
| 20 | First-time approval, A7 counted as approved (Dashboard formula) |  |  |  | 50% | 50% | 0 | 1e-09 | PASS
| 21 | Hours to finish: calculator example, 35 packages x 6 h x 1.3 |  |  |  | 273 | 273 | 0 | 1e-09 | PASS
Fixed test inputs
White cells are fixed test inputs; blue cells are the workbook's formulas evaluated on them.
Parameters
| Status date |  |  | 2026-06-30
| Due soon window (days) |  |  | 14
Filter: customer (blank = all)
| Hours per package (calculator example) |  |  | 6
| Resubmission allowance |  |  | 30%
| Hours available |  |  | 320
Test table: Customers
| Customer | Notes
C1
C2
Test table: Reasons
| Reason | Notes
New part
Engineering change
Test table: ElementList
| Element | No. | Usual owner
| Design records | 1 | Quality
| Engineering change docs | 2 | Quality
| Customer eng. approval | 3 | Quality
| Design FMEA | 4 | Quality
| Process flow diagram | 5 | Quality
| Process FMEA | 6 | Quality
Test table: PPAPs
| PPAP no. | Part number | Part name | Customer | Reason | Level | Owner | Required date | Submitted | Disposition | Decision date | Resubmissions | Resubmit by | Elements | Complete | Ready | Due by | Due status | Submitted on time | Customer review (days) | First-time approval | Open | To submit | In view | Open rank | Check | Notes
| A1 | X-A1 | Part | C1 | New part | 3 | QE | 2026-05-01 | 2026-04-28 | Approved | 2026-05-12 | 0 |  | 2 | 2 | 100% | 2026-05-01 | Complete | Yes | 14 | Yes | 0 | 0 | 1 |  | OK
| A2 | X-A2 | Part | C1 | New part | 3 | QE | 2026-05-15 | 2026-05-20 | Approved | 2026-06-10 | 1 |  | 0 | 0 |  | 2026-05-15 | Complete | No | 21 | No | 0 | 0 | 1 |  | No elements on the tracker
| A3 | X-A3 | Part | C2 | New part | 3 | QE | 2026-06-20 |  | Open |  | 0 |  | 3 | 1 | 33.33% | 2026-06-20 | Overdue |  |  |  | 1 | 1 | 1 | 1 | OK
| A4 | X-A4 | Part | C2 | New part | 3 | QE | 2026-07-10 |  | Open |  | 0 |  | 1 | 0 | 0% | 2026-07-10 | Due soon |  |  |  | 1 | 1 | 1 | 3 | OK
| A5 | X-A5 | Part | C1 | New part | 3 | QE | 2026-06-01 | 2026-06-01 | Rejected | 2026-06-15 | 0 | 2026-08-31 | 1 | 1 | 100% | 2026-08-31 | OK | Yes | 14 | No | 1 | 1 | 1 | 4 | OK
| A6 | X-A6 | Part | C2 | New part | 3 | QE | 2026-06-25 | 2026-06-24 | Submitted |  | 0 |  | 1 | 1 | 100% | 2026-06-25 | In progress | Yes |  |  | 1 | 0 | 1 | 2 | OK
| A7 | X-A7 | Part | C9 | New part | 3 | QE | 2026-06-25 |  | Approved |  | 0 |  | 0 | 0 |  | 2026-06-25 | Complete |  |  | Yes | 0 | 0 | 1 |  | Customer not on Setup list
Test table: Elements
| PPAP no. | Element | Owner | Due date | Status | Done date | Part number | Customer | Open package | Days to due | Due status | In view | Check | Notes
| A1 | Design records | Quality | 2026-04-01 | Complete | 2026-03-30 | X-A1 | C1 | 0 |  | Complete | 1 | OK
| A1 | Process FMEA | Quality | 2026-04-15 | Complete | 2026-04-14 | X-A1 | C1 | 0 |  | Complete | 1 | OK
| A3 | Design records | Quality | 2026-05-20 | Complete | 2026-05-19 | X-A3 | C2 | 1 |  | Complete | 1 | OK
| A3 | Process flow diagram | Quality | 2026-06-10 | In progress |  | X-A3 | C2 | 1 | -20 | Overdue | 1 | OK
| A3 | Process FMEA | Quality | 2026-07-05 | Not started |  | X-A3 | C2 | 1 | 5 | Due soon | 1 | OK
| A4 | Design records | Quality | 2026-08-01 | Not started |  | X-A4 | C2 | 1 | 32 | OK | 1 | OK
| A5 | Design records | Quality | 2026-05-01 | Complete | 2026-05-02 | X-A5 | C1 | 1 |  | Complete | 1 | OK
| A6 | Design records | Quality | 2026-06-01 | Complete | 2026-06-01 | X-A6 | C2 | 1 |  | Complete | 1 | OK
| A9 | Engineering change docs | Quality | 2026-06-01 | Complete | [5 empty] | Complete | 1 | PPAP no. not on the log