## Start Here
Production Schedule Gantt
| Read this first: what the workbook does and how to use it. |  |  |  | mfgcalcs.com
Production Schedule Gantt
Schedule jobs on machines in working days, see each job's end date, slack to due date and progress, and check machine load against usable capacity on a Gantt dashboard.
For: Production planners, schedulers, shop supervisors and owners of machine shops and job shops.
Version 1.0.0 · updated 15 October 2026
Quick start
| 1. | On Setup, set the plan start, the horizon in working days and the status (as of) date, then replace the example machines (hours per day, availability, efficiency) and holidays.
| 2. | On Schedule, add one row per job: machine, quantity, setup hours, cycle minutes per piece, start date, due date and percent complete.
| 3. | Read the end date, slack and progress columns, and fix anything the Check column names (overlaps, non-working start days).
| 4. | Open Timeline for the day-by-day Gantt grid to print for the shop floor.
| 5. | Open the Dashboard: the Gantt chart, machine load against capacity, and the late and behind-schedule counts.
What is in this workbook
|  | Start Here | Read this first: what the workbook does and how to use it.
|  | Setup | Plan dates, capacity thresholds, the machines with their usable hours, and holidays.
|  | Schedule | One row per job: machine, quantity, times, start and due dates. End date, slack and progress follow.
|  | Timeline | The day-by-day Gantt grid: one row per job, one column per working day. Green = done, blue = still to do.
|  | Dashboard | Jobs on a Gantt chart, machine load against usable capacity, and the jobs that are late or behind.
|  | Method | How every number is calculated, with assumptions, limits and sources.
|  | Verify | Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference.
Colour key
|  | Input | Yellow cells are yours: type a value or pick from the list. Each one says what it accepts when you click it.
|  | Calculated | Blue cells are formulas. They update as you type; overwrite one and that row stops calculating.
|  | Note | Grey boxes are guidance and labelled example data.
|  | Status words | On target / PASS / OK | Near target / Check | Below target / FAIL
Status is always written in words; the colour only repeats it, so the workbook reads the same in black-and-white print and for colour-blind readers.
Self-check and links
|  | Self-check | PASS | 29 of 29 checks pass
The Verify sheet recomputes this workbook's formulas on fixed test inputs and compares them with an independent reference calculation. PASS means every check agreed when you opened the file.
|  | Run it live | Finite Capacity Load Calculator on mfgcalcs.com
|  | Latest version | mfgcalcs.com/templates/production-schedule
|  | More free templates | mfgcalcs.com/templates
|  | Version | 1.0.0 (updated 15 October 2026)
About the example data
Every number already in this workbook is example data for Hartwell Precision, a fictional business invented for this template, so the dashboard and charts show something meaningful on day one. It covers sixteen jobs on four CNC machines over a 20-working-day plan starting 2 November 2026, with a shutdown day on 20 November. To clear it: on each working sheet, select the example rows of the table, right-click and choose Delete > Table Rows. The formulas stay, and every new row you type below the table picks them up.
Good to know
| • | Sheets Start Here, Dashboard, Method, Verify are protected without a password so formulas and layout are not overwritten by accident. To change them: Review > Unprotect Sheet.
| • | Setup and the working sheets are not protected, so tables grow as you add rows.
| • | Works in Excel 2016 and later, Microsoft 365, LibreOffice 24 and Google Sheets (File > Import). No macros, no external links, no add-ins.
| • | Money is shown in the currency you type on Setup; no exchange rates are applied.
Free from MFG Calcs - keep this credit when you share it.
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Setup
Production Schedule Gantt
| Plan dates, capacity thresholds, the machines with their usable hours, and holidays. | [5 empty] | mfgcalcs.com
Plan
| Plant or shop name |  | Hartwell Precision (example)
| Plan starts |  | 2026-11-02
| Plan horizon |  | 20 | working days
| Plan ends (last working day) |  | 2026-11-30
| Status as of |  | 2026-11-11
| Near capacity from |  | 85%
| Over capacity above |  | 100%
Machines
Usable hours per working day = hours per day x availability x efficiency. Availability covers breakdowns and unplanned stops; efficiency covers speed losses and small stops. Setups are not in these factors: they are planned per job on the Schedule. The thresholds and factors are yours to set; none is an industry benchmark.
Machines (example)
| Machine | Description | Hours per day (h) | Availability (%) | Efficiency (%) | Usable (h/day)
| VMC-1 | 3-axis vertical machining centre | 16 | 90% | 85% | 12.24
| VMC-2 | 3-axis vertical machining centre | 16 | 88% | 85% | 11.968
| HMC-1 | Horizontal machining centre, pallet pool | 22 | 92% | 88% | 17.8112
| LATHE-1 | CNC lathe with bar feeder, one shift | 8 | 90% | 90% | 6.48
Holidays and shutdown days
Days that are not worked, besides Saturdays and Sundays. Keep at least one row; a date outside the plan does no harm.
Holidays (example)
| Date | Name
| 2026-11-20 | Plant shutdown day (example)

## Schedule
Production Schedule Gantt
| One row per job: machine, quantity, times, start and due dates. End date, slack and progress follow. | [17 empty] | mfgcalcs.com
Example data for Hartwell Precision (fictional). Replace it with your own: select the example rows, right-click, Delete > Table Rows. Yellow = you type; blue = calculated; Check names any problem. List jobs by machine, in run order.
| Job | Customer | Part | Machine | Qty (pcs) | Setup (h) | Cycle (min/pc) | Start | Due | Complete (%) | Work (h) | Usable (h/day) | Days (working) | End | Slack (days) | On time | Progress | Check | Notes
| J-4101 | Corvane Pumps | Pump housing PH-220 | VMC-1 | 120 | 3 | 18 | 2026-11-02 | 2026-11-10 | 100% | 39 | 12.24 | 3.1863 | 2026-11-05 | 3 | Yes | Complete | OK
| J-4105 | Aldermoor Valves | Valve body VB-40 | VMC-1 | 300 | 2.5 | 8.5 | 2026-11-06 | 2026-11-13 | 75% | 45 | 12.24 | 3.6765 | 2026-11-11 | 2 | Yes | In progress | OK
| J-4109 | Brightwater Instruments | Sensor block SB-7 | VMC-1 | 600 | 2 | 4.2 | 2026-11-12 | 2026-11-24 | 0% | 44 | 12.24 | 3.5948 | 2026-11-17 | 4 | Yes | Not started | OK
| J-4113 | Corvane Pumps | End cover EC-220 | VMC-1 | 240 | 1.5 | 9 | 2026-11-18 | 2026-11-26 | 0% | 37.5 | 12.24 | 3.0637 | 2026-11-24 | 2 | Yes | Not started | OK
| J-4102 | Halden Robotics | Gripper plate GP-12 | VMC-2 | 400 | 2 | 6 | 2026-11-02 | 2026-11-11 | 95% | 42 | 11.968 | 3.5094 | 2026-11-05 | 4 | Yes | Overdue | OK | Last 20 plates held for rework
| J-4106 | Aldermoor Valves | Bonnet BN-40 | VMC-2 | 300 | 2 | 7.5 | 2026-11-06 | 2026-11-16 | 75% | 39.5 | 11.968 | 3.3005 | 2026-11-11 | 3 | Yes | In progress | OK
| J-4110 | Halden Robotics | Arm bracket AB-3 | VMC-2 | 150 | 3 | 16 | 2026-11-12 | 2026-11-19 | 0% | 43 | 11.968 | 3.5929 | 2026-11-17 | 2 | Yes | Not started | OK
| J-4114 | Brightwater Instruments | Lid LD-7 | VMC-2 | 800 | 1 | 2.4 | 2026-11-18 | 2026-11-26 | 0% | 33 | 11.968 | 2.7574 | 2026-11-23 | 3 | Yes | Not started | OK
| J-4103 | Corvane Pumps | Impeller casing IC-90 | HMC-1 | 80 | 4 | 55 | 2026-11-02 | 2026-11-10 | 100% | 77.3333 | 17.8112 | 4.3418 | 2026-11-06 | 2 | Yes | Complete | OK
| J-4107 | Marlow Hydraulics | Manifold MF-6 | HMC-1 | 200 | 3.5 | 21 | 2026-11-09 | 2026-11-18 | 40% | 73.5 | 17.8112 | 4.1266 | 2026-11-13 | 3 | Yes | In progress | OK
| J-4111 | Marlow Hydraulics | Manifold MF-8 | HMC-1 | 150 | 3.5 | 27 | 2026-11-16 | 2026-11-24 | 0% | 71 | 17.8112 | 3.9863 | 2026-11-19 | 2 | Yes | Not started | OK
| J-4115 | Halden Robotics | Base frame BF-1 | HMC-1 | 40 | 5 | 75 | 2026-11-23 | 2026-11-30 | 0% | 55 | 17.8112 | 3.0879 | 2026-11-26 | 2 | Yes | Not started | OK | Fixture from J-4110 reused
| J-4104 | Aldermoor Valves | Stem ST-40 | LATHE-1 | 600 | 1.5 | 3.2 | 2026-11-02 | 2026-11-11 | 100% | 33.5 | 6.48 | 5.1698 | 2026-11-09 | 2 | Yes | Complete | OK
| J-4108 | Marlow Hydraulics | Fitting FT-12 | LATHE-1 | 1200 | 1 | 1.8 | 2026-11-10 | 2026-11-19 | 15% | 37 | 6.48 | 5.7099 | 2026-11-17 | 2 | Yes | In progress | OK
| J-4112 | Corvane Pumps | Shaft SH-220 | LATHE-1 | 250 | 2 | 9.5 | 2026-11-18 | 2026-11-30 | 0% | 41.5833 | 6.48 | 6.4172 | 2026-11-27 | 1 | Yes | Not started | OK | Bar stock arrives 13 Nov
| J-4116 | Brightwater Instruments | Spindle SP-7 | LATHE-1 | 400 | 1.5 | 5 | 2026-11-30 | 2026-12-02 | 0% | 34.8333 | 6.48 | 5.3755 | 2026-12-07 | -3 | No | Not started | OK | Customer asked for 3 Dec
Formulas:
End = IF(tblJobs[[#This Row],[Job]]="","",IF(tblJobs[[#This Row],[Days (working)]]="","",WORKDAY(tblJobs[[#This Row],[Start]],MAX(1,ROUNDUP(tblJobs[[#This Row],[Days (working)]],0))-1,tblHolidays[Date])))

## Timeline
Production Schedule Gantt
| The day-by-day Gantt grid: one row per job, one column per working day. Green = done, blue = still to do. | [18 empty] | mfgcalcs.com
Each row is a job of the Schedule (in the same order); each column a working day from the plan start, skipping weekends and the Setup holidays. Green = done (the job's calendar span x percent complete), blue = still to do. The grid shows the first 16 jobs and 20 working days.
Working days from the plan start
| Job (machine) | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-30
| J-4101 (VMC-1) | 2026-11-02: 2; 2026-11-03: 2; 2026-11-04: 2; 2026-11-05: 2
| J-4105 (VMC-1) | 2026-11-06: 2; 2026-11-09: 2; 2026-11-10: 2; 2026-11-11: 1
J-4109 (VMC-1) | bar: 2026-11-12 to 2026-11-17
J-4113 (VMC-1) | bar: 2026-11-18 to 2026-11-24
| J-4102 (VMC-2) | 2026-11-02: 2; 2026-11-03: 2; 2026-11-04: 2; 2026-11-05: 2
| J-4106 (VMC-2) | 2026-11-06: 2; 2026-11-09: 2; 2026-11-10: 2; 2026-11-11: 1
J-4110 (VMC-2) | bar: 2026-11-12 to 2026-11-17
J-4114 (VMC-2) | bar: 2026-11-18 to 2026-11-23
| J-4103 (HMC-1) | 2026-11-02: 2; 2026-11-03: 2; 2026-11-04: 2; 2026-11-05: 2; 2026-11-06: 2
| J-4107 (HMC-1) | 2026-11-09: 2; 2026-11-10: 2; 2026-11-11: 1; 2026-11-12: 1; 2026-11-13: 1
J-4111 (HMC-1) | bar: 2026-11-16 to 2026-11-19
J-4115 (HMC-1) | bar: 2026-11-23 to 2026-11-26
| J-4104 (LATHE-1) | 2026-11-02: 2; 2026-11-03: 2; 2026-11-04: 2; 2026-11-05: 2; 2026-11-06: 2; 2026-11-09: 2
| J-4108 (LATHE-1) | 2026-11-10: 2; 2026-11-11: 2; 2026-11-12: 1; 2026-11-13: 1; 2026-11-16: 1; 2026-11-17: 1
J-4112 (LATHE-1) | bar: 2026-11-18 to 2026-11-27
J-4116 (LATHE-1) | bar: 2026-11-30

## Dashboard
Production Schedule Gantt
| Jobs on a Gantt chart, machine load against usable capacity, and the jobs that are late or behind. | [8 empty] | mfgcalcs.com
| Plan starts | 2026-11-02 |  |  | Plan ends | 2026-11-30 |  |  | Status as of | 2026-11-11
| JOBS ON THE SCHEDULE |  | JOBS PLANNED TO FINISH LATE |  |  | JOBS BEHIND SCHEDULE |  |  | BUSIEST MACHINE LOAD
| 16 |  | 1 |  |  | 1 |  |  | 113.4%
| Rows on the Schedule sheet |  | 0 |  |  | 0 |  |  | 100%
|  |  | Above target |  |  | Above target |  |  | Over capacity
| Green = done (span x percent complete), blue = still to do. Bars run from start to end date, weekends included. | [5 empty] | Usable capacity = usable hours per day x working days in the horizon.
Machine load over the plan horizon
| Machine | Jobs | Scheduled (h) | Usable capacity (h) | Load | Hours over capacity | Jobs late | Capacity
| VMC-1 | 4 | 165.5 | 244.8 | 67.61% | 0 | 0 | Under capacity
| VMC-2 | 4 | 157.5 | 239.36 | 65.8% | 0 | 0 | Under capacity
| HMC-1 | 4 | 276.8333 | 356.224 | 77.71% | 0 | 0 | Under capacity
| LATHE-1 | 4 | 146.9167 | 129.6 | 113.4% | 17.3167 | 1 | Over capacity
Jobs in Schedule order (chart data for the Gantt)
| Job (machine) | Start | End | Due | Slack (days) | Offset (days) | Done (days) | Remaining (days) | On time | Progress
| J-4101 (VMC-1) | 2026-11-02 | 2026-11-05 | 2026-11-10 | 3 | 0 | 4 | 0 | Yes | Complete
| J-4105 (VMC-1) | 2026-11-06 | 2026-11-11 | 2026-11-13 | 2 | 4 | 4.5 | 1.5 | Yes | In progress
| J-4109 (VMC-1) | 2026-11-12 | 2026-11-17 | 2026-11-24 | 4 | 10 | 0 | 6 | Yes | Not started
| J-4113 (VMC-1) | 2026-11-18 | 2026-11-24 | 2026-11-26 | 2 | 16 | 0 | 7 | Yes | Not started
| J-4102 (VMC-2) | 2026-11-02 | 2026-11-05 | 2026-11-11 | 4 | 0 | 3.8 | 0.2 | Yes | Overdue
| J-4106 (VMC-2) | 2026-11-06 | 2026-11-11 | 2026-11-16 | 3 | 4 | 4.5 | 1.5 | Yes | In progress
| J-4110 (VMC-2) | 2026-11-12 | 2026-11-17 | 2026-11-19 | 2 | 10 | 0 | 6 | Yes | Not started
| J-4114 (VMC-2) | 2026-11-18 | 2026-11-23 | 2026-11-26 | 3 | 16 | 0 | 6 | Yes | Not started
| J-4103 (HMC-1) | 2026-11-02 | 2026-11-06 | 2026-11-10 | 2 | 0 | 5 | 0 | Yes | Complete
| J-4107 (HMC-1) | 2026-11-09 | 2026-11-13 | 2026-11-18 | 3 | 7 | 2 | 3 | Yes | In progress
| J-4111 (HMC-1) | 2026-11-16 | 2026-11-19 | 2026-11-24 | 2 | 14 | 0 | 4 | Yes | Not started
| J-4115 (HMC-1) | 2026-11-23 | 2026-11-26 | 2026-11-30 | 2 | 21 | 0 | 4 | Yes | Not started
| J-4104 (LATHE-1) | 2026-11-02 | 2026-11-09 | 2026-11-11 | 2 | 0 | 8 | 0 | Yes | Complete
| J-4108 (LATHE-1) | 2026-11-10 | 2026-11-17 | 2026-11-19 | 2 | 8 | 1.2 | 6.8 | Yes | In progress
| J-4112 (LATHE-1) | 2026-11-18 | 2026-11-27 | 2026-11-30 | 1 | 16 | 0 | 10 | Yes | Not started
| J-4116 (LATHE-1) | 2026-11-30 | 2026-12-07 | 2026-12-02 | -3 | 28 | 0 | 8 | No | Not started
The Dashboard and Timeline show the first 16 jobs and 4 machines. If you schedule more, extend the blocks (see Method) or split the plan by area.
Formulas:
Jobs = IF(B41="","",INDEX(tblJobs[Start],1))
JOBS PLANNED TO FINISH LATE = IF(B41="","",INDEX(tblJobs[End],1))
Usable capacity (h) = IF(B41="","",INDEX(tblJobs[Due],1))

## Method
Production Schedule Gantt
| How every number is calculated, with assumptions, limits and sources. |  | mfgcalcs.com
What this workbook calculates
The schedule works in whole working days. A job's work hours (setup plus quantity x cycle time) divided by its machine's usable hours per day give the working days it needs; Excel's WORKDAY counts that many working days from the start date, skipping weekends and the holiday list, to give the end date. The Gantt chart and the Timeline grid draw each job from its start to its end; the Dashboard compares each machine's scheduled hours with its usable capacity over the horizon.
Calculations
| Quantity | How it is calculated | Units
| Usable hours per day | Hours per day x availability x efficiency, per machine on Setup. | h/day
| Work | Setup hours + quantity x cycle minutes / 60. | h
| Working days needed | Work / the machine's usable hours per day (looked up by machine). | working days
| End date | WORKDAY(start, MAX(1, ROUNDUP(working days needed, 0)) - 1, holidays): the last working day of the job. A job needing 0.4 days ends on its start day. | date
| Gantt offset, done, remaining | In the Dashboard job list: offset = start - plan start; span = end - start + 1 (calendar days, so a bar covers the weekends inside a job); done = span x percent complete; remaining = span - done. | days
| Slack | Working days from the end date to the due date: NETWORKDAYS(end, due, holidays) - 1, negative when the end is after the due date. | working days
| On time | Yes when the end date is on or before the due date, No otherwise. | -
| Progress | As of the status date: Complete (100%), Overdue (end date before the status date and not complete), In progress (started), Not started. | -
| Plan end | The horizon's last working day: WORKDAY from the first working day on or after the plan start, horizon - 1 working days on. | date
| Usable capacity | Usable hours per day x the horizon in working days, per machine. | h
| Machine load | Scheduled hours (sum of the work of every job on the machine) / usable capacity. Under capacity below the near threshold, Near capacity from it, Over capacity above the over threshold. | %
| Timeline cells | A job's row is filled on each working day from its start to its end date; dark while the day is before start + done days. | -
Assumptions
| • | A job runs on one machine; split a multi-operation job into one row per operation, each with its own machine and start date.
| • | Usable hours per day are the same on every working day; overtime days are best entered as a higher hours per day or a shorter cycle.
| • | Every job on a machine counts against the horizon's capacity, so list only jobs inside the plan (or move a finished plan's jobs to an archive copy).
| • | Weekends are Saturday and Sunday (Excel WORKDAY and NETWORKDAYS).
Limitations
| • | It does not sequence jobs for you: you type the start dates, and the Check column flags overlaps on a machine.
| • | Days are whole: a job ending part-way through a day still occupies the day, and the next job starts on the next working day.
| • | The Dashboard and Timeline have fixed blocks for 16 jobs, 4 machines and 20 working days; extend them by copying the last row or column of a block and widening the chart ranges, or keep one workbook per area.
| • | Percent complete is what you type; the workbook does not read machine data.
Agreement with the live calculator
The Dashboard's usable capacity per machine is the live Finite Capacity Load calculator's 'usable finite capacity' with a working day as the scheduling bucket: hours per day x working days in the horizon x availability x efficiency. For the calculator's own example (16 h per bucket, 10 buckets, 88% availability, 92% efficiency) both give 129.5 usable hours out of 160 calendar hours; verify.py checks the template's reference against the calculator's engine on every build. The calculator stops at capacity; this workbook adds the jobs, the dates and the Gantt.
Open the Finite Capacity Load Calculator
Self-check
The Verify sheet holds fixed test inputs. Its formulas are the same formula text as the working sheets, placed against those inputs, and each result is compared with a value computed independently by the template's Python reference implementation when the file was built. If you edit a formula on a working sheet, the Verify sheet still tests the original formula text, so it will not detect your change.
Sources and standards
| • | Microsoft Excel function reference: WORKDAY and NETWORKDAYS (working-day arithmetic used for end dates and slack).
| • | MFG Calcs Finite Capacity Load calculator (finite-capacity-load): usable capacity = hours per bucket x buckets x availability x efficiency.
Standards are cited by name so you can look them up; no copyrighted standard text or tables are reproduced. Statistical constants used are public.
Version history
| Version | Change | Date
| 1.0.0 | First release. | 15 October 2026
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Verify
Production Schedule Gantt
| Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference. | [17 empty] | mfgcalcs.com
| Self-check status |  | PASS |  | 29 of 29 checks pass
This sheet recomputes the workbook's own formulas on fixed test inputs and compares each result with a value computed independently by the template's Python reference implementation when the file was built. Every row should read PASS. The test inputs are fixed and do not change when you edit Setup or the working sheets.
Checks
| No. | Check |  |  |  | Expected (reference) | Workbook result | Difference | Tolerance | Result
| 1 | M1 (calculator example): usable hours per day |  |  |  | 12.9536 | 12.9536 | 0 | 1e-09 | PASS
| 2 | T1 (one day, complete): work hours |  |  |  | 12 | 12 | 0 | 1e-09 | PASS
| 3 | T1 (one day, complete): working days needed |  |  |  | 0.92638 | 0.92638 | 0 | 1e-09 | PASS
| 4 | T1 (one day, complete): end date |  |  |  | 2026-01-05 | 2026-01-05 | 0 | 1e-09 | PASS
| 5 | T1 (one day, complete): slack (working days) |  |  |  | 2 | 2 | 0 | 1e-09 | PASS
| 6 | T1 (one day, complete): on time |  |  |  | Yes | Yes |  | exact | PASS
| 7 | T1 (one day, complete): progress |  |  |  | Complete | Complete |  | exact | PASS
| 8 | T2 (crosses the holiday, late): work hours |  |  |  | 33 | 33 | 0 | 1e-09 | PASS
| 9 | T2 (crosses the holiday, late): working days needed |  |  |  | 2.5476 | 2.5476 | 0 | 1e-09 | PASS
| 10 | T2 (crosses the holiday, late): end date |  |  |  | 2026-01-12 | 2026-01-12 | 0 | 1e-09 | PASS
| 11 | T2 (crosses the holiday, late): slack (working days) |  |  |  | -1 | -1 | 0 | 1e-09 | PASS
| 12 | T2 (crosses the holiday, late): on time |  |  |  | No | No |  | exact | PASS
| 13 | T2 (crosses the holiday, late): progress |  |  |  | Overdue | Overdue |  | exact | PASS
| 14 | T3 (in progress): work hours |  |  |  | 11 | 11 | 0 | 1e-09 | PASS
| 15 | T3 (in progress): working days needed |  |  |  | 1.375 | 1.375 | 0 | 1e-09 | PASS
| 16 | T3 (in progress): end date |  |  |  | 2026-01-14 | 2026-01-14 | 0 | 1e-09 | PASS
| 17 | T3 (in progress): slack (working days) |  |  |  | 4 | 4 | 0 | 1e-09 | PASS
| 18 | T3 (in progress): on time |  |  |  | Yes | Yes |  | exact | PASS
| 19 | T3 (in progress): progress |  |  |  | In progress | In progress |  | exact | PASS
| 20 | T4: Check reports the overlap with T2 |  |  |  | Overlaps another job on this machine | Overlaps another job on this machine |  | exact | PASS
| 21 | T5: Check reports a Saturday start |  |  |  | Starts on a non-working day | Starts on a non-working day |  | exact | PASS
| 22 | All rows: jobs planned late (Dashboard formula) |  |  |  | 1 | 1 | 0 | 1e-09 | PASS
| 23 | All rows: jobs behind schedule (Dashboard formula) |  |  |  | 2 | 2 | 0 | 1e-09 | PASS
| 24 | M1: scheduled hours |  |  |  | 47 | 47 | 0 | 1e-09 | PASS
| 25 | M1: usable capacity over 10 working days (= calculator) |  |  |  | 129.536 | 129.536 | 0 | 1e-09 | PASS
| 26 | M1: machine load |  |  |  | 36.28% | 36.28% | 0 | 1e-09 | PASS
| 27 | Gantt data, T2: done days (span x complete) |  |  |  | 3 | 3 | 0 | 1e-09 | PASS
| 28 | Gantt data, T2: remaining days |  |  |  | 3 | 3 | 0 | 1e-09 | PASS
| 29 | Gantt data, T3: offset from the plan start |  |  |  | 8 | 8 | 0 | 1e-09 | PASS
Fixed test inputs
White cells are fixed test inputs; blue cells are the workbook's formulas evaluated on them.
Parameters
| Plan start |  |  | 2026-01-05
| Status as of |  |  | 2026-01-14
| Horizon (working days) |  |  | 10
| Near capacity from |  |  | 85%
| Over capacity above |  |  | 100%
Test table: Holidays
| Date | Name
| 2026-01-09 | Test holiday
Test table: Machines
| Machine | Description | Hours per day (h) | Availability (%) | Efficiency (%) | Usable (h/day)
| M1 | Calculator example | 16 | 88% | 92% | 12.9536
| M2 | One shift | 8 | 100% | 100% | 8
Test table: Jobs
| Job | Customer | Part | Machine | Qty (pcs) | Setup (h) | Cycle (min/pc) | Start | Due | Complete (%) | Work (h) | Usable (h/day) | Days (working) | End | Slack (days) | On time | Progress | Check | Notes
| T1 | C | P | M1 | 100 | 2 | 6 | 2026-01-05 | 2026-01-07 | 100% | 12 | 12.9536 | 0.92638 | 2026-01-05 | 2 | Yes | Complete | OK
| T2 | C | P | M1 | 300 | 3 | 6 | 2026-01-07 | 2026-01-08 | 50% | 33 | 12.9536 | 2.5476 | 2026-01-12 | -1 | No | Overdue | Overlaps another job on this machine
| T3 | C | P | M2 | 50 | 1 | 12 | 2026-01-13 | 2026-01-20 | 25% | 11 | 8 | 1.375 | 2026-01-14 | 4 | Yes | In progress | OK
| T4 | C | P | M1 | 10 | 1 | 6 | 2026-01-12 | 2026-01-13 | 0% | 2 | 12.9536 | 0.1544 | 2026-01-12 | 1 | Yes | Overdue | Overlaps another job on this machine
| T5 | C | P | M2 | 20 | 0.5 | 3 | 2026-01-17 | 2026-01-23 | 0% | 1.5 | 8 | 0.1875 | 2026-01-17 | 4 | Yes | Not started | Starts on a non-working day
Test grid: ByMachine
| Machine | Jobs | Scheduled (h) | Usable capacity (h) | Load | Hours over capacity | Jobs late | Capacity
| M1 | 3 | 47 | 129.536 | 36.28% | 0 | 1 | Under capacity
| M2 | 2 | 12.5 | 80 | 15.62% | 0 | 0 | Under capacity
Test grid: Plan
| Job (machine) | Start | End | Due | Slack (days) | Offset (days) | Done (days) | Remaining (days) | On time | Progress
| T1 (M1) | 2026-01-05 | 2026-01-05 | 2026-01-07 | 2 | 0 | 1 | 0 | Yes | Complete
| T2 (M1) | 2026-01-07 | 2026-01-12 | 2026-01-08 | -1 | 2 | 3 | 3 | No | Overdue
| T3 (M2) | 2026-01-13 | 2026-01-14 | 2026-01-20 | 4 | 8 | 0.5 | 1.5 | Yes | In progress
| T4 (M1) | 2026-01-12 | 2026-01-12 | 2026-01-13 | 1 | 7 | 0 | 1 | Yes | Overdue
| T5 (M2) | 2026-01-17 | 2026-01-17 | 2026-01-23 | 4 | 12 | 0 | 1 | Yes | Not started
Formulas:
End = IF(tblVerifyJobs[[#This Row],[Job]]="","",IF(tblVerifyJobs[[#This Row],[Days (working)]]="","",WORKDAY(tblVerifyJobs[[#This Row],[Start]],MAX(1,ROUNDUP(tblVerifyJobs[[#This Row],[Days (working)]],0))-1,tblVerifyHolidays[Date])))
Check = IF(B77="","",INDEX(tblVerifyJobs[Start],1))
Hours per day (h) = IF(B77="","",INDEX(tblVerifyJobs[End],1))
Availability (%) = IF(B77="","",INDEX(tblVerifyJobs[Due],1))