## Start Here
Supplier Risk Assessment
| Read this first: what the workbook does and how to use it. |  |  |  | mfgcalcs.com
Supplier Risk Assessment
Score every supplier risk for severity, occurrence and detection, see which ones to act on, and track the mitigation actions to closure.
For: Supplier quality engineers, buyers, purchasing and supply-chain managers, and the plant leadership that reviews supply risk.
Version 1.0.0 · updated 15 October 2026
Quick start
| 1. | On Setup, agree the RPN threshold, the severity floor and the as-of date, read the rating guide, and replace the example suppliers with yours, with annual spend and single-source flags.
| 2. | On Risk Register, add one row per supplier risk: category, what could fail, and severity, occurrence and detection from 1 to 10.
| 3. | For every row that says Act, enter the mitigation action, owner and due date; type the closed date when it is done.
| 4. | Fix anything the Check column flags, then open the Dashboard for the risks to act on and the overdue actions.
What is in this workbook
|  | Start Here | Read this first: what the workbook does and how to use it.
|  | Setup | Scoring rules, the as-of date, a rating guide and the supplier and risk category lists.
|  | Risk Register | One row per supplier risk: ratings, RPN, priority, the mitigation action and its status.
|  | Dashboard | The supplier risks to act on, overdue actions and where the risk sits, by supplier and category.
|  | Method | How every number is calculated, with assumptions, limits and sources.
|  | Verify | Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference.
Colour key
|  | Input | Yellow cells are yours: type a value or pick from the list. Each one says what it accepts when you click it.
|  | Calculated | Blue cells are formulas. They update as you type; overwrite one and that row stops calculating.
|  | Note | Grey boxes are guidance and labelled example data.
|  | Status words | On target / PASS / OK | Near target / Check | Below target / FAIL
Status is always written in words; the colour only repeats it, so the workbook reads the same in black-and-white print and for colour-blind readers.
Self-check and links
|  | Self-check | PASS | 24 of 24 checks pass
The Verify sheet recomputes this workbook's formulas on fixed test inputs and compares them with an independent reference calculation. PASS means every check agreed when you opened the file.
|  | Run it live | Supplier Risk Score Calculator on mfgcalcs.com
|  | Latest version | mfgcalcs.com/templates/supplier-risk-assessment
|  | More free templates | mfgcalcs.com/templates
|  | Version | 1.0.0 (updated 15 October 2026)
About the example data
Every number already in this workbook is example data for Brenmoor Conveyors, a fictional business invented for this template, so the dashboard and charts show something meaningful on day one. It covers eight suppliers and 26 assessed risks with their actions, status as of 12 October 2026. Suppliers, spend and ratings are invented for the example. To clear it: on each working sheet, select the example rows of the table, right-click and choose Delete > Table Rows. The formulas stay, and every new row you type below the table picks them up.
Good to know
| • | Sheets Start Here, Dashboard, Method, Verify are protected without a password so formulas and layout are not overwritten by accident. To change them: Review > Unprotect Sheet.
| • | Setup and the working sheets are not protected, so tables grow as you add rows.
| • | Works in Excel 2016 and later, Microsoft 365, LibreOffice 24 and Google Sheets (File > Import). No macros, no external links, no add-ins.
| • | Money is shown in the currency you type on Setup; no exchange rates are applied.
Free from MFG Calcs - keep this credit when you share it.
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Setup
Supplier Risk Assessment
| Scoring rules, the as-of date, a rating guide and the supplier and risk category lists. |  |  |  | mfgcalcs.com
Company and scoring rules
| Company or plant | Brenmoor Conveyors (example)
| Currency label | EUR
| Act when RPN is at least | 100 | RPN
| Act when severity is at least | 9 | of 10
| Action status as of | 2026-10-12
| Due soon window | 14 | days
RPN = severity x occurrence x detection, each rated 1-10, so RPN runs from 1 to 1,000. RPN is a ranking, not a measurement: 120 is not twice as risky as 60. That is why a severity floor also triggers action.
Rating guide (agree your own anchors before scoring)
Severity, the effect on you or your customer if it happens: 1-2 hardly noticed; 3-4 minor rework or a short delay; 5-6 scrap, a missed delivery or a customer complaint; 7-8 a line stop of days or a major customer escalation; 9-10 safety, regulatory or a stop of weeks.
Occurrence, how likely it is in the next 12 months: 1-2 very unlikely, never seen; 3-4 unlikely, seen elsewhere; 5-6 possible, seen at this supplier; 7-8 likely, happens most years; 9-10 almost certain or already happening.
Detection, how late you would find out: 1-2 early warning is certain (monitored, contractual notice); 3-4 likely to be seen weeks ahead; 5-6 found at goods-in or at a planned review; 7-8 found on the line or when stock runs out; 9-10 found by the customer or not at all.
Lists that feed the dropdowns
Suppliers (fictional; spend is invented)
EUR/year
| Supplier | Commodity | Country | Annual spend | Single source
| Kallax Gearmotors | Gear motors | Italy | 1850000 | Yes
| Ostra Steel Service | Sheet and tube | Poland | 2400000 | No
| Linden Belting | Conveyor belts | Germany | 950000 | Yes
| Tarn Bearings | Bearings | Czechia | 620000 | No
| Vireo Controls | PLCs and drives | Netherlands | 1300000 | Yes
| Sundra Castings | Pulley castings | India | 480000 | No
| Hollin Fasteners | Fasteners | Germany | 210000 | No
| Porto Rollers | Idler rollers | Portugal | 770000 | No
Risk categories
| Category | Covers
| Quality | Escapes, process capability, inspection gaps
| Delivery and capacity | Late deliveries, capacity, lead time
| Single source | No qualified alternative
| Financial | Insolvency, credit, ownership change
| Trade and tariffs | Tariffs, export controls, sanctions, customs
| Natural hazard | Flood, fire, storm, earthquake at the site
| Cyber and IT | Ransomware, EDI or ERP outage
| Compliance | Material declarations, conflict minerals

## Risk Register
Supplier Risk Assessment
| One row per supplier risk: ratings, RPN, priority, the mitigation action and its status. | [19 empty] | mfgcalcs.com
Example register for Brenmoor Conveyors (fictional). Replace it with your own: select the example rows, right-click, Delete > Table Rows. Yellow = you type; blue = calculated; Check names any problem.
| ID | Supplier | Commodity | Category | Risk | Severity | Occurrence | Detection | RPN | Criticality | Vs threshold | Priority | Trigger | Action | Owner | Due | Closed | Action status | Sort key | Check | Notes
| R-01 | Kallax Gearmotors | Gear motors | Single source | Sole source for the 0.55 kW motor: stops assembly | 9 | 4 | 3 | 108 | 36 | 8 | Act | RPN and severity | Qualify a second gear motor source on two conveyor models | Purchasing | 2026-12-15 |  | In progress | 108.9999 | OK
| R-02 | Kallax Gearmotors | Gear motors | Delivery and capacity | Lead time up from 6 to 14 weeks; shipments slip | 7 | 6 | 3 | 126 | 42 | 26 | Act | RPN at or over threshold | Agree a 4-week consignment stock of the top three motors | Buyer | 2026-10-05 |  | Overdue | 126.9999 | OK | Draft agreement with supplier
| R-03 | Ostra Steel Service | Sheet and tube | Trade and tariffs | Steel safeguard quota used up; extra duty on sheet | 6 | 5 | 2 | 60 | 30 | -40 | Monitor |  | Track quota fill weekly; price the domestic mill option | Buyer | 2026-11-30 |  | In progress | 60.9999 | OK
| R-04 | Ostra Steel Service | Sheet and tube | Quality | Sheet thickness at the low tolerance limit | 5 | 4 | 4 | 80 | 20 | -20 | Monitor | [6 empty] | 80.9999 | OK | Monitor at goods-in
| R-05 | Linden Belting | Conveyor belts | Single source | Food-grade belt made in one plant only | 8 | 3 | 3 | 72 | 24 | -28 | Monitor |  | Ask the customer to approve an equivalent belt | Engineering | 2026-09-30 |  | Overdue | 72.9999 | OK | Approval pack sent 22 Sep
| R-06 | Linden Belting | Conveyor belts | Natural hazard | Belt plant sits in a river flood zone | 8 | 2 | 2 | 32 | 16 | -68 | Monitor | [6 empty] | 32.9999 | OK | Supplier has flood barriers; review yearly
| R-07 | Linden Belting | Conveyor belts | Quality | Belt splice failures on two customer lines | 9 | 3 | 5 | 135 | 27 | 35 | Act | RPN and severity | Supplier 8D and splice process audit | SQE | 2026-10-20 |  | Due soon | 135.9999 | OK | 8D at D5
| R-08 | Tarn Bearings | Bearings | Quality | Counterfeit bearings found at a local distributor | 8 | 2 | 6 | 96 | 16 | -4 | Closed |  | Buy only through the authorised channel; add a goods-in check | SQE | 2026-08-31 | 2026-08-28 | Complete |  | OK | Closed: authorised channel only
| R-09 | Tarn Bearings | Bearings | Delivery and capacity | Allocation on 6205 bearings in peak season | 5 | 5 | 3 | 75 | 25 | -25 | Monitor | [6 empty] | 75.9999 | OK
| R-10 | Vireo Controls | PLCs and drives | Single source | Drive brand sold through one distributor only | 8 | 3 | 4 | 96 | 24 | -4 | Closed |  | Second distributor account opened | Buyer | 2026-09-15 | 2026-09-12 | Complete |  | OK | Closed
| R-11 | Vireo Controls | PLCs and drives | Delivery and capacity | Chip shortage: allocation on the 4 kW drive | 7 | 5 | 3 | 105 | 35 | 5 | Act | RPN at or over threshold | Last-time buy of 120 drives; redesign for the 5.5 kW model | Engineering | 2026-10-30 |  | In progress | 105.9998 | OK
| R-12 | Vireo Controls | PLCs and drives | Cyber and IT | Distributor EDI outage stopped confirmations | 4 | 3 | 2 | 24 | 12 | -76 | Monitor | [6 empty] | 24.9998 | OK
| R-13 | Vireo Controls | PLCs and drives | Trade and tariffs | Export licence needed for one PLC family | 6 | 3 | 5 | 90 | 18 | -10 | Monitor |  | Classify the PLC family and file licences early | Logistics | 2026-10-16 |  | Due soon | 90.9998 | OK
| R-14 | Sundra Castings | Pulley castings | Quality | Porosity in pulley hubs found at machining | 7 | 5 | 4 | 140 | 35 | 40 | Act | RPN at or over threshold | Supplier to add X-ray sampling; tighten the PPAP | SQE | 2026-11-14 |  | In progress | 140.9998 | OK
| R-15 | Sundra Castings | Pulley castings | Delivery and capacity | Sea transit varies from 5 to 9 weeks | 5 | 6 | 2 | 60 | 30 | -40 | Monitor | [6 empty] | 60.9998 | OK | Safety stock covers 3 weeks
| R-16 | Sundra Castings | Pulley castings | Trade and tariffs | Anti-dumping case opened on castings from origin | 6 | 3 | 3 | 54 | 18 | -46 | Monitor | [6 empty] | 54.9998 | OK | Watch the case
| R-17 | Sundra Castings | Pulley castings | Financial | Supplier reported a loss and a covenant breach | 8 | 3 | 6 | 144 | 24 | 44 | Act | RPN at or over threshold | Credit check every quarter; pay on receipt to support cash | Purchasing | 2026-10-31 |  | In progress | 144.9998 | OK
| R-18 | Hollin Fasteners | Fasteners | Compliance | REACH declarations missing for zinc-flake coating | 5 | 3 | 3 | 45 | 15 | -55 | Monitor | [6 empty] | 45.9998 | OK
| R-19 | Hollin Fasteners | Fasteners | Delivery and capacity | Kanban bins run short twice a month | 3 | 6 | 2 | 36 | 18 | -64 | Monitor | [6 empty] | 36.9998 | OK
| R-20 | Porto Rollers | Idler rollers | Quality | Roller run-out above drawing on one lot | 6 | 3 | 3 | 54 | 18 | -46 | Monitor | [6 empty] | 54.9997 | OK | Contained at goods-in
| R-21 | Porto Rollers | Idler rollers | Natural hazard | Wildfire season near the roller plant | 7 | 2 | 2 | 28 | 14 | -72 | Monitor | [6 empty] | 28.9997 | OK
| R-22 | Porto Rollers | Idler rollers | Financial | Change of ownership announced | 5 | 3 | 5 | 75 | 15 | -25 | Monitor | [6 empty] | 75.9997 | OK | Meet the new owners in Q4
| R-23 | Kallax Gearmotors | Gear motors | Cyber and IT | Ransomware at a sister company of the supplier | 7 | 3 | 4 | 84 | 21 | -16 | Monitor |  | Ask for the supplier's recovery plan and test date | IT | 2026-10-09 |  | Overdue | 84.9997 | OK
| R-24 | Ostra Steel Service | Sheet and tube | Financial | Service centre credit rating cut | 6 | 2 | 4 | 48 | 12 | -52 | Monitor | [6 empty] | 48.9997 | OK
| R-25 | Linden Belting | Conveyor belts | Compliance | Food-contact declaration out of date | 9 | 2 | 2 | 36 | 18 | -64 | Closed | Severity at or over floor | Get the updated declaration of compliance | SQE | 2026-09-20 | 2026-09-18 | Complete |  | OK | Closed: new declaration on file
| R-26 | Tarn Bearings | Bearings | Trade and tariffs | Bearing origin moving to a country with a tariff | 5 | 4 | 3 | 60 | 20 | -40 | Monitor | [6 empty] | 60.9997 | OK

## Dashboard
Supplier Risk Assessment
| The supplier risks to act on, overdue actions and where the risk sits, by supplier and category. | [8 empty] | mfgcalcs.com
Register for Brenmoor Conveyors (example): 26 risks. Act = RPN of 100 or more, or severity of 9 or more. Action status as of 12 Oct 2026.
| OPEN RISKS TO ACT ON |  | OVERDUE ACTIONS |  |  | HIGHEST OPEN RPN |  |  | SPEND WITH AN ACT RISK (EUR)
| 6 |  | 3 |  |  | 144 |  |  | 4580000
| RPN or severity at its Setup limit |  | 0 |  |  | 100 |  |  | 53% of annual spend on Setup
|  |  | Above target |  |  | Above target
Top 10 open risks by RPN
| Risk (ID and supplier) | Risk |  |  |  |  | RPN | Severity | Owner | Due | Action status
| R-17 Sundra Castings | Supplier reported a loss and a covenant breach |  |  |  |  | 144 | 8 | Purchasing | 2026-10-31 | In progress
| R-14 Sundra Castings | Porosity in pulley hubs found at machining |  |  |  |  | 140 | 7 | SQE | 2026-11-14 | In progress
| R-07 Linden Belting | Belt splice failures on two customer lines |  |  |  |  | 135 | 9 | SQE | 2026-10-20 | Due soon
| R-02 Kallax Gearmotors | Lead time up from 6 to 14 weeks; shipments slip |  |  |  |  | 126 | 7 | Buyer | 2026-10-05 | Overdue
| R-01 Kallax Gearmotors | Sole source for the 0.55 kW motor: stops assembly |  |  |  |  | 108 | 9 | Purchasing | 2026-12-15 | In progress
| R-11 Vireo Controls | Chip shortage: allocation on the 4 kW drive |  |  |  |  | 105 | 7 | Engineering | 2026-10-30 | In progress
| R-13 Vireo Controls | Export licence needed for one PLC family |  |  |  |  | 90 | 6 | Logistics | 2026-10-16 | Due soon
| R-23 Kallax Gearmotors | Ransomware at a sister company of the supplier |  |  |  |  | 84 | 7 | IT | 2026-10-09 | Overdue
| R-04 Ostra Steel Service | Sheet thickness at the low tolerance limit |  |  |  |  | 80 | 5
| R-09 Tarn Bearings | Allocation on 6205 bearings in peak season |  |  |  |  | 75 | 5
Open risks by severity and occurrence (count of risks; top-right is the danger corner)
| Open risks (count) | Occurrence 1-2 | Occurrence 3-4 | Occurrence 5-6 | Occurrence 7-8 | Occurrence 9-10 | Total
| Severity 9-10 | 0 | 2 | 0 | 0 | 0 | 2
| Severity 7-8 | 2 | 3 | 3 | 0 | 0 | 8
| Severity 5-6 | 1 | 7 | 3 | 0 | 0 | 11
| Severity 3-4 | 0 | 1 | 1 | 0 | 0 | 2
| Severity 1-2 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 3 | 13 | 7 | 0 | 0
By supplier
| Supplier | Annual spend | Single source | Act | Monitor | Overdue actions | Highest open RPN | Spend with an Act risk
|  | EUR |  | risks | risks | actions | RPN | EUR
| Kallax Gearmotors | 1850000 | Yes | 2 | 1 | 2 | 126 | 1850000
| Ostra Steel Service | 2400000 | No | 0 | 3 | 0 | 80 | 0
| Linden Belting | 950000 | Yes | 1 | 2 | 1 | 135 | 950000
| Tarn Bearings | 620000 | No | 0 | 2 | 0 | 75 | 0
| Vireo Controls | 1300000 | Yes | 1 | 2 | 0 | 105 | 1300000
| Sundra Castings | 480000 | No | 2 | 2 | 0 | 144 | 480000
| Hollin Fasteners | 210000 | No | 0 | 2 | 0 | 45 | 0
| Porto Rollers | 770000 | No | 0 | 3 | 0 | 75 | 0
By risk category
| Category | Act | Monitor | Closed | Overdue actions | Highest open RPN
|  | risks | risks | risks | actions | RPN
| Quality | 2 | 2 | 1 | 0 | 140
| Delivery and capacity | 2 | 3 | 0 | 1 | 126
| Single source | 1 | 1 | 1 | 1 | 108
| Financial | 1 | 2 | 0 | 0 | 144
| Trade and tariffs | 0 | 4 | 0 | 0 | 90
| Natural hazard | 0 | 2 | 0 | 0 | 32
| Cyber and IT | 0 | 2 | 0 | 1 | 84
| Compliance | 0 | 1 | 1 | 0 | 45
The Dashboard shows the 8 suppliers and 8 categories of the Setup lists. If you add more, extend the supplier and category blocks (see Method) or they will not appear here. Severity and occurrence bands count open risks only.
Formulas:
Due = IFERROR(IF(INDEX(tblRisks[Due],MATCH(LARGE(tblRisks[Sort key],1),tblRisks[Sort key],0))="","",INDEX(tblRisks[Due],MATCH(LARGE(tblRisks[Sort key],1),tblRisks[Sort key],0))),"")

## Method
Supplier Risk Assessment
| How every number is calculated, with assumptions, limits and sources. |  | mfgcalcs.com
What this workbook calculates
Each supplier risk is rated on three 1-10 scales: severity (how bad the effect would be), occurrence (how likely it is) and detection (how late you would find out). Their product, the risk priority number (RPN), ranks the register. Because a product can hide a severe risk behind low occurrence and good detection, a risk is acted on when its RPN reaches your threshold or its severity reaches your floor. Actions carry an owner and a due date, and their status is judged against the as-of date on Setup, never the computer clock.
Calculations
| Quantity | How it is calculated | Units
| RPN | Severity x occurrence x detection (blank ratings count as 0 and the Check column says so). | 1-1,000
| Criticality | Severity x occurrence: the risk before any credit for detection. | 1-100
| Vs threshold | RPN - the RPN threshold on Setup. Positive is over the threshold. | RPN
| Priority | Closed when a closed date is typed; otherwise Act when RPN >= threshold or severity >= the severity floor, else Monitor. | -
| Trigger | Which rule made the risk Act: RPN, severity, or both. | -
| Action status | Complete when closed; otherwise Overdue when the due date is before the as-of date, Due soon within the due-soon window, In progress after that; blank with no due date. | -
| Sort key (helper) | For open risks, RPN + 1 - ROW()/100000: the RPN plus a tie-breaker below 1 that keeps register order. The top-ten list takes LARGE(sort key, k) and finds its row with MATCH. | -
| Open risks to act on, overdue actions | COUNTIFS of Priority = Act, and of Action status = Overdue, over the whole register. | count
| Highest open RPN | INT(MAX(sort key)); by supplier and category, SUMPRODUCT(MAX((key matches) x (not closed) x RPN)). | RPN
| Spend with an Act risk | Sum of the annual spend on Setup of every supplier with at least one Act risk (SUMPRODUCT over the supplier list with COUNTIFS > 0). | currency
| Severity x occurrence matrix | COUNTIFS of open risks (Act or Monitor) whose severity and occurrence fall in each pair of bands (1-2, 3-4, 5-6, 7-8, 9-10). | count
Assumptions
| • | The team agrees written anchors for each rating before scoring (the guide on Setup is a starting point) and scores together, so ratings are comparable across suppliers.
| • | One row is one risk at one supplier. A risk shared by several suppliers is logged once per supplier.
| • | When an action is complete the risk is closed; if a residual risk remains, re-score it as a new row so the history stays visible.
| • | Annual spend is the last 12 months or the budget, in the currency on Setup.
Limitations
| • | RPN is ordinal: it ranks risks but does not measure them, and equal RPNs can mean very different risks. Read severity alongside it.
| • | Ratings are judgements, not probabilities; the workbook does not estimate the cost or likelihood of a disruption.
| • | The AIAG-VDA FMEA Handbook (2019) replaces RPN with action-priority tables for design and process FMEA; those tables are not reproduced here. If your customer requires them, use the handbook.
| • | The Dashboard has fixed blocks for the number of suppliers and categories in the example lists; longer lists need the blocks extended (a warning appears).
Agreement with the live calculator
For one register row, this workbook and the live Supplier Risk Score calculator use the same inputs and formulas: RPN = severity x occurrence x detection; criticality = severity x occurrence; over or under the threshold = RPN - your threshold. The calculator advises acting on severity 9-10 whatever the total; the workbook makes that a severity floor you set on Setup. The build checks the reference implementation against the calculator's engine for its own example (severity 6, occurrence 4, detection 3, threshold 100: RPN 72, criticality 24, 28 under) and for one row of the example register.
Open the Supplier Risk Score Calculator
Self-check
The Verify sheet holds fixed test inputs. Its formulas are the same formula text as the working sheets, placed against those inputs, and each result is compared with a value computed independently by the template's Python reference implementation when the file was built. If you edit a formula on a working sheet, the Verify sheet still tests the original formula text, so it will not detect your change.
Sources and standards
| • | IEC 60812:2018, Failure modes and effects analysis (FMEA and FMECA): severity, occurrence and detection ratings and the risk priority number.
| • | AIAG and VDA, FMEA Handbook, 1st edition 2019: action priority in place of RPN (named, not reproduced).
| • | ISO 31000:2018, Risk management - Guidelines: risk identification, analysis, treatment and review.
| • | MFG Calcs Supplier Risk Score calculator: RPN, criticality and distance from your threshold for one risk.
Standards are cited by name so you can look them up; no copyrighted standard text or tables are reproduced. Statistical constants used are public.
Version history
| Version | Change | Date
| 1.0.0 | First release. | 15 October 2026
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Verify
Supplier Risk Assessment
| Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference. | [19 empty] | mfgcalcs.com
| Self-check status |  | PASS |  | 24 of 24 checks pass
This sheet recomputes the workbook's own formulas on fixed test inputs and compares each result with a value computed independently by the template's Python reference implementation when the file was built. Every row should read PASS. The test inputs are fixed and do not change when you edit Setup or the working sheets.
Checks
| No. | Check |  |  |  | Expected (reference) | Workbook result | Difference | Tolerance | Result
| 1 | Row 1: RPN |  |  |  | 72 | 72 | 0 | 1e-09 | PASS
| 2 | Row 1: priority |  |  |  | Monitor | Monitor |  | exact | PASS
| 3 | Row 2: RPN |  |  |  | 36 | 36 | 0 | 1e-09 | PASS
| 4 | Row 2: priority |  |  |  | Act | Act |  | exact | PASS
| 5 | Row 3: RPN |  |  |  | 120 | 120 | 0 | 1e-09 | PASS
| 6 | Row 3: priority |  |  |  | Act | Act |  | exact | PASS
| 7 | Row 4: RPN |  |  |  | 150 | 150 | 0 | 1e-09 | PASS
| 8 | Row 4: priority |  |  |  | Closed | Closed |  | exact | PASS
| 9 | Row 5: RPN |  |  |  | 140 | 140 | 0 | 1e-09 | PASS
| 10 | Row 5: priority |  |  |  | Act | Act |  | exact | PASS
| 11 | Row 1 (calculator example): criticality |  |  |  | 24 | 24 | 0 | 1e-09 | PASS
| 12 | Row 1 (calculator example): vs threshold |  |  |  | -28 | -28 | 0 | 1e-09 | PASS
| 13 | Row 2: trigger (severity floor) |  |  |  | Severity at or over floor | Severity at or over floor |  | exact | PASS
| 14 | Row 2: action status |  |  |  | Overdue | Overdue |  | exact | PASS
| 15 | Row 3: trigger (RPN) |  |  |  | RPN at or over threshold | RPN at or over threshold |  | exact | PASS
| 16 | Row 3: action status |  |  |  | Due soon | Due soon |  | exact | PASS
| 17 | Row 4: action status |  |  |  | Complete | Complete |  | exact | PASS
| 18 | Row 5: Check reports the missing action |  |  |  | Act risk has no action | Act risk has no action |  | exact | PASS
| 19 | Row 1: Check is OK |  |  |  | OK | OK |  | exact | PASS
| 20 | All rows: open risks to act on (Dashboard formula) |  |  |  | 3 | 3 | 0 | 1e-09 | PASS
| 21 | All rows: overdue actions (Dashboard formula) |  |  |  | 1 | 1 | 0 | 1e-09 | PASS
| 22 | All rows: highest open RPN (Dashboard formula) |  |  |  | 140 | 140 | 0 | 1e-09 | PASS
| 23 | All rows: spend with an Act risk (Dashboard formula) |  |  |  | 700000 | 700000 | 0 | 1e-09 | PASS
| 24 | Top-ten list: rank 1 is the highest open RPN |  |  |  | T-5 | T-5 |  | exact | PASS
Fixed test inputs
White cells are fixed test inputs; blue cells are the workbook's formulas evaluated on them.
Parameters
| RPN threshold |  |  | 100
| Severity floor |  |  | 9
| As-of date |  |  | 2026-10-12
| Due soon window (days) |  |  | 14
Test table: Suppliers
EUR/year
| Supplier | Commodity | Country | Annual spend | Single source
| S1 | C1 |  | 500000 | Yes
| S2 | C2 |  | 200000 | No
| S3 | C3 |  | 300000 | No
Test table: Risks
| ID | Supplier | Commodity | Category | Risk | Severity | Occurrence | Detection | RPN | Criticality | Vs threshold | Priority | Trigger | Action | Owner | Due | Closed | Action status | Sort key | Check | Notes
| T-1 | S1 | C1 | Quality | Calculator example | 6 | 4 | 3 | 72 | 24 | -28 | Monitor | [6 empty] | 72.9995 | OK
| T-2 | S1 | C1 | Quality | Severe, rare, well detected | 9 | 2 | 2 | 36 | 18 | -64 | Act | Severity at or over floor | Second source | Buyer | 2026-10-09 |  | Overdue | 36.9995 | OK
| T-3 | S2 | C2 | Quality | Frequent, late detection | 5 | 6 | 4 | 120 | 30 | 20 | Act | RPN at or over threshold | Audit | SQE | 2026-10-22 |  | Due soon | 120.9994 | OK
| T-4 | S3 | C3 | Quality | Closed risk | 10 | 5 | 3 | 150 | 50 | 50 | Closed | RPN and severity | Done | SQE | 2026-09-22 | 2026-09-17 | Complete |  | OK
| T-5 | S2 | C2 | Quality | Act without action | 7 | 5 | 4 | 140 | 35 | 40 | Act | RPN at or over threshold | [5 empty] | 140.9994 | Act risk has no action