## Start Here
Job Shop Work Order Tracker
| Read this first: what the workbook does and how to use it. |  |  |  | mfgcalcs.com
Job Shop Work Order Tracker
Track every work order from release to shipment and see on-time delivery, open work by stage, and estimated versus actual hours, cost and margin.
For: Job shop owners, production managers and planners, estimators and the people who run the open-order meeting.
Version 1.0.0 · updated 15 October 2026
Quick start
| 1. | On Setup, type your shop name, currency, estimating and costing rates, targets and status date, then replace the example customers and stages.
| 2. | On Work Orders, add one row per job at release: customer, part, quantity, due date, order value and the estimated hours and material.
| 3. | As the job runs, keep its stage and actual hours current; when it ships, type the ship date and the actual material.
| 4. | Read the Check column: anything other than OK names the problem in words.
| 5. | Before the open-order meeting, set the status date on Setup and open the Dashboard; filter by customer or ship dates as needed.
What is in this workbook
|  | Start Here | Read this first: what the workbook does and how to use it.
|  | Setup | Rates, targets, status date and the lists that feed the dropdowns.
|  | Work Orders | One row per work order from release to shipment. Cost, variance, margin, days late and status are calculated.
|  | Dashboard | On-time delivery and open work by stage, then estimate versus actual hours, cost and margin of shipped jobs.
|  | Method | How every number is calculated, with assumptions, limits and sources.
|  | Verify | Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference.
Colour key
|  | Input | Yellow cells are yours: type a value or pick from the list. Each one says what it accepts when you click it.
|  | Calculated | Blue cells are formulas. They update as you type; overwrite one and that row stops calculating.
|  | Note | Grey boxes are guidance and labelled example data.
|  | Status words | On target / PASS / OK | Near target / Check | Below target / FAIL
Status is always written in words; the colour only repeats it, so the workbook reads the same in black-and-white print and for colour-blind readers.
Self-check and links
|  | Self-check | PASS | 19 of 19 checks pass
The Verify sheet recomputes this workbook's formulas on fixed test inputs and compares them with an independent reference calculation. PASS means every check agreed when you opened the file.
|  | Run it live | Job Costing Variance Calculator on mfgcalcs.com
|  | Latest version | mfgcalcs.com/templates/work-order-tracker
|  | More free templates | mfgcalcs.com/templates
|  | Version | 1.0.0 (updated 15 October 2026)
About the example data
Every number already in this workbook is example data for Brennan Precision, a fictional business invented for this template, so the dashboard and charts show something meaningful on day one. It covers 72 work orders for six customers of a CNC machining and fabrication job shop, released from 1 July to 7 October 2026, with status as of 9 October 2026, generated from a fixed seed. To clear it: on each working sheet, select the example rows of the table, right-click and choose Delete > Table Rows. The formulas stay, and every new row you type below the table picks them up.
Good to know
| • | Sheets Start Here, Dashboard, Method, Verify are protected without a password so formulas and layout are not overwritten by accident. To change them: Review > Unprotect Sheet.
| • | Setup and the working sheets are not protected, so tables grow as you add rows.
| • | Works in Excel 2016 and later, Microsoft 365, LibreOffice 24 and Google Sheets (File > Import). No macros, no external links, no add-ins.
| • | Money is shown in the currency you type on Setup; no exchange rates are applied.
Free from MFG Calcs - keep this credit when you share it.
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Setup
Job Shop Work Order Tracker
| Rates, targets, status date and the lists that feed the dropdowns. |  | mfgcalcs.com
Shop, rates and targets
| Shop name | Brennan Precision (example)
| Currency label | USD
| Estimating shop rate | 95 | USD per hour
| Costing shop rate | 98 | USD per hour
| Status date | 2026-10-09
| Due soon window | 5 | days
| On-time delivery target | 95%
| Margin target | 25%
| Hours overrun tolerance | 10%
Rates and targets are yours to set; the example figures are invented. 'Near target' means within 5% of a target (90.25% to 95% against a 95% on-time target).
Lists that feed the dropdowns
Customers
| Customer | Contact | Notes
| Corvane Aero | Purchasing | Anodise and NDT by outside vendors; long routings
| Delta Hydraulics | Buyer | Repeat manifold blocks
| Hollis Agri | Supply chain | Welded frames and brackets
| Marlow Packaging | Maintenance | Machine parts, often rush
| Pinecrest Medical | Quality | Small lots, full inspection
| Trent Robotics | Engineering | Prototype and low-volume parts
Stages (where an open work order is)
Keep names unique. Rows that use a renamed customer or stage stop matching, and their Check column says so.
| Stage | Meaning
| Released | Paperwork out, waiting to start
| Material | Waiting for or cutting material
| Machining | On a mill or lathe
| Fabrication | Forming or welding
| Finishing | Deburr, paint or in-house finish
| Outside processing | At a plating, heat treat or NDT vendor
| Inspection | Final inspection and paperwork
| Ready to ship | Packed, waiting for pickup

## Work Orders
Job Shop Work Order Tracker
| One row per work order from release to shipment. Cost, variance, margin, days late and status are calculated. | [23 empty] | mfgcalcs.com
Example data for Brennan Precision (fictional; prices, hours and rates are invented examples). Replace it with your own: select the example rows, right-click, Delete > Table Rows. Status and days late are measured to the status date on Setup.
[9 empty] | USD | h | h | USD | USD | USD | USD | USD |  |  | days | days
| WO No. | Customer | Part no. | Qty | Released | Due | Shipped | Stage | Order value | Est hours | Actual hours | Est material | Actual material | Est cost | Actual cost | Cost variance | Margin | Hours used | Days late | Lead time | Status | On time | View ship | View open | Check
| WO-2611 | Trent Robotics | TR-3157 | 1 | 2026-07-01 | 2026-07-20 | 2026-07-17 |  | 1310 | 8 | 10.75 | 115 | 125 | 875 | 1178.5 | 303.5 | 10.04% | 134.4% | 0 | 16 | Complete | Yes | 2026-07-17 |  | OK
| WO-2612 | Hollis Agri | HA-1741 | 50 | 2026-07-02 | 2026-07-17 | 2026-07-17 |  | 3630 | 22.5 | 22.5 | 295 | 310 | 2432.5 | 2515 | 82.5 | 30.72% | 100% | 0 | 15 | Complete | Yes | 2026-07-17 |  | OK
| WO-2613 | Delta Hydraulics | DH-2157 | 4 | 2026-07-03 | 2026-07-17 | 2026-07-27 |  | 1560 | 9.5 | 9.75 | 160 | 160 | 1062.5 | 1115.5 | 53 | 28.49% | 102.6% | 10 | 24 | Complete | No | 2026-07-27 |  | OK
| WO-2614 | Pinecrest Medical | PM-1572 | 40 | 2026-07-06 | 2026-07-29 | 2026-07-29 |  | 1840 | 13.5 | 13.75 | 95 | 95 | 1377.5 | 1442.5 | 65 | 21.6% | 101.9% | 0 | 23 | Complete | Yes | 2026-07-29 |  | OK
| WO-2615 | Marlow Packaging | MP-5574 | 2 | 2026-07-06 | 2026-07-20 | 2026-07-20 |  | 1090 | 7 | 6 | 35 | 35 | 700 | 623 | -77 | 42.84% | 85.71% | 0 | 14 | Complete | Yes | 2026-07-20 |  | OK
| WO-2616 | Hollis Agri | HA-4372 | 2 | 2026-07-07 | 2026-07-21 | 2026-07-21 |  | 4900 | 27.5 | 26.75 | 575 | 580 | 3187.5 | 3201.5 | 14 | 34.66% | 97.27% | 0 | 14 | Complete | Yes | 2026-07-21 |  | OK
| WO-2617 | Pinecrest Medical | PM-3740 | 5 | 2026-07-09 | 2026-07-29 | 2026-07-29 |  | 2210 | 14.5 | 15.5 | 275 | 285 | 1652.5 | 1804 | 151.5 | 18.37% | 106.9% | 0 | 20 | Complete | Yes | 2026-07-29 |  | OK
| WO-2618 | Pinecrest Medical | PM-3471 | 5 | 2026-07-10 | 2026-07-27 | 2026-07-27 |  | 5060 | 29.5 | 32.75 | 600 | 610 | 3402.5 | 3819.5 | 417 | 24.52% | 111% | 0 | 17 | Complete | Yes | 2026-07-27 |  | OK
| WO-2619 | Marlow Packaging | MP-8172 | 100 | 2026-07-13 | 2026-07-23 | 2026-07-23 |  | 1380 | 10 | 8.75 | 65 | 70 | 1015 | 927.5 | -87.5 | 32.79% | 87.5% | 0 | 10 | Complete | Yes | 2026-07-23 |  | OK
| WO-2620 | Delta Hydraulics | DH-8712 | 25 | 2026-07-13 | 2026-07-31 | 2026-07-30 |  | 3290 | 23 | 20 | 210 | 220 | 2395 | 2180 | -215 | 33.74% | 86.96% | 0 | 17 | Complete | Yes | 2026-07-30 |  | OK
| WO-2621 | Delta Hydraulics | DH-3737 | 100 | 2026-07-14 | 2026-07-28 | 2026-07-27 |  | 2350 | 17.5 | 15.5 | 100 | 110 | 1762.5 | 1629 | -133.5 | 30.68% | 88.57% | 0 | 13 | Complete | Yes | 2026-07-27 |  | OK
| WO-2622 | Corvane Aero | CA-9765 | 40 | 2026-07-15 | 2026-08-17 | 2026-09-02 |  | 8270 | 46 | 54.5 | 1010 | 1030 | 5380 | 6371 | 991 | 22.96% | 118.5% | 16 | 49 | Complete | No | 2026-09-02 |  | OK
| WO-2623 | Trent Robotics | TR-8933 | 20 | 2026-07-17 | 2026-07-30 | 2026-07-29 |  | 3760 | 23.5 | 30 | 290 | 305 | 2522.5 | 3245 | 722.5 | 13.7% | 127.7% | 0 | 12 | Complete | Yes | 2026-07-29 |  | OK
| WO-2624 | Corvane Aero | CA-5890 | 40 | 2026-07-20 | 2026-08-21 | 2026-08-21 |  | 8650 | 51 | 65 | 1015 | 1045 | 5860 | 7415 | 1555 | 14.28% | 127.5% | 0 | 32 | Complete | Yes | 2026-08-21 |  | OK
| WO-2625 | Marlow Packaging | MP-1978 | 4 | 2026-07-20 | 2026-07-27 | 2026-07-27 |  | 1280 | 9.5 | 11.5 | 50 | 50 | 952.5 | 1177 | 224.5 | 8.047% | 121.1% | 0 | 7 | Complete | Yes | 2026-07-27 |  | OK
| WO-2626 | Marlow Packaging | MP-2597 | 100 | 2026-07-21 | 2026-07-27 | 2026-07-30 |  | 1920 | 12.5 | 14.5 | 200 | 205 | 1387.5 | 1626 | 238.5 | 15.31% | 116% | 3 | 9 | Complete | No | 2026-07-30 |  | OK
| WO-2627 | Pinecrest Medical | PM-3914 | 1 | 2026-07-22 | 2026-08-14 | 2026-08-20 |  | 1790 | 12.5 | 13.5 | 60 | 60 | 1247.5 | 1383 | 135.5 | 22.74% | 108% | 6 | 29 | Complete | No | 2026-08-20 |  | OK
| WO-2628 | Pinecrest Medical | PM-4889 | 2 | 2026-07-24 | 2026-08-10 | 2026-08-06 |  | 1320 | 8.5 | 7.25 | 45 | 45 | 852.5 | 755.5 | -97 | 42.77% | 85.29% | 0 | 13 | Complete | Yes | 2026-08-06 |  | OK
| WO-2629 | Trent Robotics | TR-7277 | 25 | 2026-07-27 | 2026-08-06 | 2026-08-13 |  | 3410 | 23.5 | 23.5 | 265 | 265 | 2497.5 | 2568 | 70.5 | 24.69% | 100% | 7 | 17 | Complete | No | 2026-08-13 |  | OK
| WO-2630 | Delta Hydraulics | DH-5791 | 5 | 2026-07-27 | 2026-08-17 | 2026-08-17 |  | 1640 | 10.5 | 9.75 | 170 | 185 | 1167.5 | 1140.5 | -27 | 30.46% | 92.86% | 0 | 21 | Complete | Yes | 2026-08-17 |  | OK
| WO-2631 | Marlow Packaging | MP-5572 | 4 | 2026-07-28 | 2026-08-07 | 2026-08-03 |  | 1990 | 13.5 | 12.5 | 210 | 215 | 1492.5 | 1440 | -52.5 | 27.64% | 92.59% | 0 | 6 | Complete | Yes | 2026-08-03 |  | OK
| WO-2632 | Delta Hydraulics | DH-4273 | 40 | 2026-07-29 | 2026-08-10 | 2026-08-10 |  | 3720 | 23.5 | 19.5 | 225 | 245 | 2457.5 | 2156 | -301.5 | 42.04% | 82.98% | 0 | 12 | Complete | Yes | 2026-08-10 |  | OK
| WO-2633 | Hollis Agri | HA-5968 | 4 | 2026-07-30 | 2026-08-13 | 2026-08-12 |  | 1880 | 14 | 16 | 60 | 60 | 1390 | 1628 | 238 | 13.4% | 114.3% | 0 | 13 | Complete | Yes | 2026-08-12 |  | OK
| WO-2634 | Delta Hydraulics | DH-1290 | 1 | 2026-08-03 | 2026-08-21 | 2026-08-19 |  | 1650 | 9.5 | 9.25 | 190 | 195 | 1092.5 | 1101.5 | 9 | 33.24% | 97.37% | 0 | 16 | Complete | Yes | 2026-08-19 |  | OK
| WO-2635 | Corvane Aero | CA-2611 | 100 | 2026-08-03 | 2026-08-31 | 2026-08-31 |  | 4170 | 25 | 25.75 | 425 | 440 | 2800 | 2963.5 | 163.5 | 28.93% | 103% | 0 | 28 | Complete | Yes | 2026-08-31 |  | OK
| WO-2636 | Delta Hydraulics | DH-9872 | 50 | 2026-08-04 | 2026-08-17 | 2026-08-13 |  | 3030 | 19 | 18.5 | 245 | 250 | 2050 | 2063 | 13 | 31.91% | 97.37% | 0 | 9 | Complete | Yes | 2026-08-13 |  | OK
| WO-2637 | Marlow Packaging | MP-3430 | 20 | 2026-08-05 | 2026-08-17 | 2026-08-17 |  | 2240 | 13 | 14 | 220 | 215 | 1455 | 1587 | 132 | 29.15% | 107.7% | 0 | 12 | Complete | Yes | 2026-08-17 |  | OK
| WO-2638 | Pinecrest Medical | PM-1682 | 4 | 2026-08-06 | 2026-08-31 | 2026-08-27 |  | 1300 | 9 | 8.75 | 90 | 100 | 945 | 957.5 | 12.5 | 26.35% | 97.22% | 0 | 21 | Complete | Yes | 2026-08-27 |  | OK
| WO-2639 | Marlow Packaging | MP-4856 | 40 | 2026-08-10 | 2026-08-17 | 2026-08-17 |  | 450 | 3 | 3 | 15 | 15 | 300 | 309 | 9 | 31.33% | 100% | 0 | 7 | Complete | Yes | 2026-08-17 |  | OK
| WO-2640 | Trent Robotics | TR-8622 | 5 | 2026-08-10 | 2026-08-24 | 2026-08-24 |  | 3630 | 24 | 29.25 | 200 | 205 | 2480 | 3071.5 | 591.5 | 15.39% | 121.9% | 0 | 14 | Complete | Yes | 2026-08-24 |  | OK
| WO-2641 | Trent Robotics | TR-1744 | 12 | 2026-08-10 | 2026-08-27 | 2026-08-24 |  | 1490 | 10.5 | 11.75 | 55 | 60 | 1052.5 | 1211.5 | 159 | 18.69% | 111.9% | 0 | 14 | Complete | Yes | 2026-08-24 |  | OK
| WO-2642 | Delta Hydraulics | DH-7263 | 1 | 2026-08-12 | 2026-08-27 | 2026-09-01 |  | 3140 | 22 | 21.75 | 225 | 230 | 2315 | 2361.5 | 46.5 | 24.79% | 98.86% | 5 | 20 | Complete | No | 2026-09-01 |  | OK
| WO-2643 | Marlow Packaging | MP-2904 | 20 | 2026-08-13 | 2026-08-25 | 2026-08-24 |  | 1360 | 9 | 10.75 | 80 | 80 | 935 | 1133.5 | 198.5 | 16.65% | 119.4% | 0 | 11 | Complete | Yes | 2026-08-24 |  | OK
| WO-2644 | Hollis Agri | HA-1660 | 10 | 2026-08-14 | 2026-09-01 | 2026-08-31 |  | 2170 | 14 | 15.75 | 160 | 160 | 1490 | 1703.5 | 213.5 | 21.5% | 112.5% | 0 | 17 | Complete | Yes | 2026-08-31 |  | OK
| WO-2645 | Trent Robotics | TR-8044 | 50 | 2026-08-17 | 2026-09-07 | 2026-09-21 |  | 2030 | 12.5 | 14.25 | 275 | 280 | 1462.5 | 1676.5 | 214 | 17.41% | 114% | 14 | 35 | Complete | No | 2026-09-21 |  | OK
| WO-2646 | Hollis Agri | HA-9445 | 2 | 2026-08-17 | 2026-09-02 | 2026-09-02 |  | 4290 | 29 | 35 | 145 | 155 | 2900 | 3585 | 685 | 16.43% | 120.7% | 0 | 16 | Complete | Yes | 2026-09-02 |  | OK
| WO-2647 | Corvane Aero | CA-2018 | 12 | 2026-08-19 | 2026-09-21 | 2026-09-29 |  | 3920 | 26.5 | 26.25 | 420 | 455 | 2937.5 | 3027.5 | 90 | 22.77% | 99.06% | 8 | 41 | Complete | No | 2026-09-29 |  | OK
| WO-2648 | Corvane Aero | CA-7688 | 1 | 2026-08-20 | 2026-09-14 | 2026-09-23 |  | 8880 | 54.5 | 63 | 655 | 660 | 5832.5 | 6834 | 1001.5 | 23.04% | 115.6% | 9 | 34 | Complete | No | 2026-09-23 |  | OK
| WO-2649 | Delta Hydraulics | DH-7602 | 5 | 2026-08-21 | 2026-09-03 | 2026-09-03 |  | 2840 | 17.5 | 18 | 365 | 350 | 2027.5 | 2114 | 86.5 | 25.56% | 102.9% | 0 | 13 | Complete | Yes | 2026-09-03 |  | OK
| WO-2650 | Delta Hydraulics | DH-3680 | 2 | 2026-08-24 | 2026-09-04 | 2026-09-03 |  | 2770 | 19.5 | 18.5 | 180 | 195 | 2032.5 | 2008 | -24.5 | 27.51% | 94.87% | 0 | 10 | Complete | Yes | 2026-09-03 |  | OK
| WO-2651 | Hollis Agri | HA-7849 | 20 | 2026-08-24 | 2026-09-14 | 2026-09-10 |  | 3540 | 23.5 | 31.75 | 135 | 145 | 2367.5 | 3256.5 | 889 | 8.008% | 135.1% | 0 | 17 | Complete | Yes | 2026-09-10 |  | OK
| WO-2652 | Trent Robotics | TR-4047 | 100 | 2026-08-25 | 2026-09-08 | 2026-09-21 |  | 1280 | 8.5 | 10.75 | 40 | 40 | 847.5 | 1093.5 | 246 | 14.57% | 126.5% | 13 | 27 | Complete | No | 2026-09-21 |  | OK
| WO-2653 | Delta Hydraulics | DH-3949 | 2 | 2026-08-27 | 2026-09-11 | 2026-09-10 |  | 2770 | 18.5 | 19 | 120 | 115 | 1877.5 | 1977 | 99.5 | 28.63% | 102.7% | 0 | 14 | Complete | Yes | 2026-09-10 |  | OK
| WO-2654 | Marlow Packaging | MP-9682 | 20 | 2026-08-28 | 2026-09-07 | 2026-09-07 |  | 1720 | 12.5 | 11.5 | 70 | 75 | 1257.5 | 1202 | -55.5 | 30.12% | 92% | 0 | 10 | Complete | Yes | 2026-09-07 |  | OK
| WO-2655 | Marlow Packaging | MP-5564 | 50 | 2026-08-31 | 2026-09-07 | 2026-09-07 |  | 1060 | 7 | 7.75 | 35 | 35 | 700 | 794.5 | 94.5 | 25.05% | 110.7% | 0 | 7 | Complete | Yes | 2026-09-07 |  | OK
| WO-2656 | Delta Hydraulics | DH-2148 | 10 | 2026-08-31 | 2026-09-14 | 2026-09-14 |  | 1940 | 12 | 13.75 | 155 | 150 | 1295 | 1497.5 | 202.5 | 22.81% | 114.6% | 0 | 14 | Complete | Yes | 2026-09-14 |  | OK
| WO-2657 | Hollis Agri | HA-3748 | 2 | 2026-09-01 | 2026-09-17 | 2026-09-15 |  | 5690 | 33 | 32 | 530 | 515 | 3665 | 3651 | -14 | 35.83% | 96.97% | 0 | 14 | Complete | Yes | 2026-09-15 |  | OK
| WO-2658 | Corvane Aero | CA-6638 | 20 | 2026-09-02 | 2026-10-07 |  | Outside processing | 5720 | 39 | 41.75 | 550 | 530 | 4255 | 4621.5 |  |  | 107.1% | 2 |  | Overdue |  |  | 2026-09-02 | OK
| WO-2659 | Delta Hydraulics | DH-4194 | 1 | 2026-09-04 | 2026-09-23 | 2026-09-23 |  | 1210 | 7.5 | 8.25 | 110 | 105 | 822.5 | 913.5 | 91 | 24.5% | 110% | 0 | 19 | Complete | Yes | 2026-09-23 |  | OK
| WO-2660 | Marlow Packaging | MP-1719 | 100 | 2026-09-07 | 2026-09-21 | 2026-09-18 |  | 1310 | 9 | 11.25 | 70 | 75 | 925 | 1177.5 | 252.5 | 10.11% | 125% | 0 | 11 | Complete | Yes | 2026-09-18 |  | OK
| WO-2661 | Delta Hydraulics | DH-1190 | 40 | 2026-09-07 | 2026-09-28 | 2026-09-28 |  | 1940 | 13 | 15 | 75 | 80 | 1310 | 1550 | 240 | 20.1% | 115.4% | 0 | 21 | Complete | Yes | 2026-09-28 |  | OK
| WO-2662 | Hollis Agri | HA-8123 | 40 | 2026-09-08 | 2026-09-23 |  | Fabrication | 6230 | 35.5 | 32 | 725 | 740 | 4097.5 | 3876 |  |  | 90.14% | 16 |  | Overdue |  |  | 2026-09-08 | OK
| WO-2663 | Corvane Aero | CA-5578 | 10 | 2026-09-09 | 2026-10-14 |  | Inspection | 5110 | 34.5 | 31.25 | 310 | 310 | 3587.5 | 3372.5 |  |  | 90.58% | 0 |  | Due soon |  |  | 2026-09-09 | OK
| WO-2664 | Delta Hydraulics | DH-7900 | 40 | 2026-09-11 | 2026-09-30 | 2026-09-30 |  | 1310 | 8.5 | 8.25 | 120 | 125 | 927.5 | 933.5 | 6 | 28.74% | 97.06% | 0 | 19 | Complete | Yes | 2026-09-30 |  | OK
| WO-2665 | Marlow Packaging | MP-5375 | 100 | 2026-09-14 | 2026-09-25 |  | Inspection | 1940 | 13.5 | 15 | 150 | 150 | 1432.5 | 1620 |  |  | 111.1% | 14 |  | Overdue |  |  | 2026-09-14 | OK
| WO-2666 | Corvane Aero | CA-9323 | 2 | 2026-09-14 | 2026-10-12 |  | Ready to ship | 7920 | 54 | 63 | 410 | 410 | 5540 | 6584 |  |  | 116.7% | 0 |  | Due soon |  |  | 2026-09-14 | OK
| WO-2667 | Corvane Aero | CA-5477 | 50 | 2026-09-15 | 2026-10-12 |  | Ready to ship | 5290 | 37 | 30.5 | 350 | 350 | 3865 | 3339 |  |  | 82.43% | 0 |  | Due soon |  |  | 2026-09-15 | OK
| WO-2668 | Corvane Aero | CA-1793 | 5 | 2026-09-16 | 2026-10-07 | 2026-10-07 |  | 5100 | 32.5 | 32.25 | 710 | 695 | 3797.5 | 3855.5 | 58 | 24.4% | 99.23% | 0 | 21 | Complete | Yes | 2026-10-07 |  | OK
| WO-2669 | Corvane Aero | CA-9500 | 2 | 2026-09-17 | 2026-10-19 |  | Inspection | 5590 | 42 | 33.5 | 240 | 240 | 4230 | 3523 |  |  | 79.76% | 0 |  | In progress |  |  | 2026-09-17 | OK
| WO-2670 | Marlow Packaging | MP-1927 | 12 | 2026-09-21 | 2026-09-28 | 2026-09-28 |  | 1230 | 8.5 | 10.25 | 50 | 50 | 857.5 | 1054.5 | 197 | 14.27% | 120.6% | 0 | 7 | Complete | Yes | 2026-09-28 |  | OK
| WO-2671 | Corvane Aero | CA-7871 | 100 | 2026-09-21 | 2026-10-12 | 2026-10-08 |  | 3360 | 24.5 | 25.25 | 105 | 105 | 2432.5 | 2579.5 | 147 | 23.23% | 103.1% | 0 | 17 | Complete | Yes | 2026-10-08 |  | OK
| WO-2672 | Pinecrest Medical | PM-4040 | 40 | 2026-09-22 | 2026-10-12 |  | Inspection | 3950 | 26 | 25.5 | 175 | 175 | 2645 | 2674 |  |  | 98.08% | 0 |  | Due soon |  |  | 2026-09-22 | OK
| WO-2673 | Pinecrest Medical | PM-1205 | 2 | 2026-09-23 | 2026-10-12 |  | Outside processing | 3890 | 26.5 | 18.25 | 180 | 180 | 2697.5 | 1968.5 |  |  | 68.87% | 0 |  | Due soon |  |  | 2026-09-23 | OK
| WO-2674 | Pinecrest Medical | PM-7735 | 10 | 2026-09-24 | 2026-10-13 | 2026-10-09 |  | 3050 | 19.5 | 24.25 | 170 | 185 | 2022.5 | 2561.5 | 539 | 16.02% | 124.4% | 0 | 15 | Complete | Yes | 2026-10-09 |  | OK
| WO-2675 | Pinecrest Medical | PM-4896 | 50 | 2026-09-28 | 2026-10-22 |  | Finishing | 3770 | 24 | 14.75 | 355 | 355 | 2635 | 1800.5 |  |  | 61.46% | 0 |  | In progress |  |  | 2026-09-28 | OK
| WO-2676 | Trent Robotics | TR-2919 | 5 | 2026-09-28 | 2026-10-13 |  | Inspection | 1540 | 9.5 | 7.5 | 160 | 160 | 1062.5 | 895 |  |  | 78.95% | 0 |  | Due soon |  |  | 2026-09-28 | OK
| WO-2677 | Corvane Aero | CA-8739 | 50 | 2026-09-28 | 2026-10-19 |  | Finishing | 3580 | 22 | 15 | 315 | 315 | 2405 | 1785 |  |  | 68.18% | 0 |  | In progress |  |  | 2026-09-28 | OK
| WO-2678 | Marlow Packaging | MP-8309 | 12 | 2026-09-30 | 2026-10-12 |  | Inspection | 1630 | 10 | 8 | 160 | 160 | 1110 | 944 |  |  | 80% | 0 |  | Due soon |  |  | 2026-09-30 | OK
| WO-2679 | Hollis Agri | HA-9699 | 4 | 2026-10-01 | 2026-10-22 |  | Material | 3310 | 22.5 | 5.75 | 130 | 130 | 2267.5 | 693.5 |  |  | 25.56% | 0 |  | In progress |  |  | 2026-10-01 | OK
| WO-2680 | Marlow Packaging | MP-5672 | 50 | 2026-10-02 | 2026-10-12 |  | Finishing | 2120 | 13 | 8.5 | 270 | 270 | 1505 | 1103 |  |  | 65.38% | 0 |  | Due soon |  |  | 2026-10-02 | OK
| WO-2681 | Marlow Packaging | MP-5134 | 5 | 2026-10-05 | 2026-10-12 |  | Finishing | 560 | 4 | 2.5 | 20 | 20 | 400 | 265 |  |  | 62.5% | 0 |  | Due soon |  |  | 2026-10-05 | OK
| WO-2682 | Marlow Packaging | MP-4799 | 10 | 2026-10-05 | 2026-10-16 |  | Finishing | 880 | 6 | 3.25 | 40 | 40 | 610 | 358.5 |  |  | 54.17% | 0 |  | In progress |  |  | 2026-10-05 | OK
Formulas:
View open = IF(tblOrders[[#This Row],[Released]]="","",IF(AND(tblOrders[[#This Row],[Shipped]]="",OR(DashCustomer="",tblOrders[[#This Row],[Customer]]=DashCustomer)),tblOrders[[#This Row],[Released]],""))

## Dashboard
Job Shop Work Order Tracker
| On-time delivery and open work by stage, then estimate versus actual hours, cost and margin of shipped jobs. | [8 empty] | mfgcalcs.com
| Customer |  |  |  | Shipped from |  |  |  | Shipped to
Showing 55 shipped and 17 open work orders; status as of 9 Oct 2026. The ship-date filter applies to shipped jobs; the customer filter to both.
| ON-TIME DELIVERY |  | OPEN WORK ORDERS |  |  | OVERDUE WORK ORDERS |  |  | OPEN ORDER VALUE (USD)
| 81.82% |  | 17 |  |  | 3 |  |  | 63030
| 95% |  | Not shipped at the status date |  |  | Open past their due date |  |  | Order value of open work orders
Below target
| ACTUAL HOURS VS ESTIMATE |  | COST VARIANCE, SHIPPED (USD) |  |  | MARGIN ACHIEVED |  |  | AVERAGE LEAD TIME (DAYS)
| 7.881% |  | 10864 |  |  | 23.99% |  |  | 17.3455
| 10% |  | Actual - estimated cost; + is over |  |  | 25% |  |  | Released to shipped, calendar days
| On target |  |  |  |  | Near target
| HOURS VARIANCE (USD) |  | RATE VARIANCE (USD) |  |  | MATERIAL VARIANCE (USD) |  |  | WORK ORDERS SHIPPED
| 7386.25 |  | 3192.75 |  |  | 285 |  |  | 55
| (Actual - est. hours) x estimating rate |  | (Costing - estimating rate) x actual hours |  |  | Actual - estimated material |  |  | Shipped jobs in view
By ship week (last 8 weeks with shipments in view)
| Week shipped (Mon) | Shipped | On time | On-time delivery | Target | Value shipped |  | Est hours | Actual hours | Days late (sum)
[6 empty] | USD |  | h | h
| 2026-08-17 | 6 | 5 | 83.33% | 95% | 16420 |  | 99.5 | 114.5 | 6
| 2026-08-24 | 4 | 4 | 100% | 95% | 7780 |  | 52.5 | 60.5 | 0
| 2026-08-31 | 7 | 5 | 71.43% | 95% | 27650 |  | 173 | 189.25 | 21
| 2026-09-07 | 4 | 4 | 100% | 95% | 9090 |  | 61.5 | 70 | 0
| 2026-09-14 | 3 | 3 | 100% | 95% | 8940 |  | 54 | 57 | 0
| 2026-09-21 | 4 | 1 | 25% | 95% | 13400 |  | 83 | 96.25 | 36
| 2026-09-28 | 4 | 3 | 75% | 95% | 8400 |  | 56.5 | 59.75 | 8
| 2026-10-05 | 3 | 3 | 100% | 95% | 11510 |  | 76.5 | 81.75 | 0
Open work orders by stage
| Stage | Overdue | Due soon | In progress | Open | Open value |  | Est hours | Hours booked | Days late (sum)
[6 empty] | USD |  | h | h
| Released | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Material | 0 | 0 | 1 | 1 | 3310 |  | 22.5 | 5.75 | 0
| Machining | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Fabrication | 1 | 0 | 0 | 1 | 6230 |  | 35.5 | 32 | 16
| Finishing | 0 | 2 | 3 | 5 | 10910 |  | 69 | 44 | 0
| Outside processing | 1 | 1 | 0 | 2 | 9610 |  | 65.5 | 60 | 2
| Inspection | 1 | 4 | 1 | 6 | 19760 |  | 135.5 | 120.75 | 14
| Ready to ship | 0 | 2 | 0 | 2 | 13210 |  | 91 | 93.5 | 0
By customer (shipped jobs in view; open jobs at the status date)
| Customer | Shipped | On-time delivery | Est hours | Actual hours | Hours vs est. | Margin | Margin target | Open | Overdue | Open value
|  |  |  | h | h | [5 empty] | USD
| Corvane Aero | 7 | 57.14% | 260 | 292 | 12.31% | 21.97% | 25% | 6 | 1 | 33210
| Delta Hydraulics | 15 | 86.67% | 231 | 224.75 | -2.706% | 29.63% | 25% | 0 | 0 | 0
| Hollis Agri | 7 | 100% | 163.5 | 179.75 | 9.939% | 25.13% | 25% | 2 | 1 | 9540
| Marlow Packaging | 12 | 91.67% | 114.5 | 121.75 | 6.332% | 23.36% | 25% | 5 | 1 | 7130
| Pinecrest Medical | 7 | 85.71% | 107 | 115.75 | 8.178% | 23.21% | 25% | 3 | 0 | 11610
| Trent Robotics | 7 | 57.14% | 110.5 | 130.25 | 17.87% | 16.95% | 25% | 1 | 0 | 1540
The Dashboard shows the 6 customers and 8 stages of the Setup lists. If you add more, extend the 'By customer' and 'By stage' blocks (see Method) or they will not appear here.
Formulas:
Customer = IF(B62="","",IF(B62-1<MIN(tblOrders[View ship]),"",B62-7))
Customer = IF(COUNT(tblOrders[View ship])=0,"",MAX(tblOrders[View ship])-WEEKDAY(MAX(tblOrders[View ship]),2)+1)

## Method
Job Shop Work Order Tracker
| How every number is calculated, with assumptions, limits and sources. |  | mfgcalcs.com
What this workbook calculates
Each work order is one row from release to shipment. Delivery is judged against the due date promised to the customer, and open jobs against a status date you type, so the file never changes by itself. Cost is estimated hours at the estimating rate plus estimated material, against actual hours at the costing rate plus actual material; the difference splits exactly into an hours, a rate and a material variance. Every Dashboard figure is a SUMIFS or COUNTIFS over the log, so ratios are formed from sums.
Calculations
| Quantity | How it is calculated | Units
| Estimated cost | Est hours x estimating rate + est material. Excel: =[@[Est hours]]*EstRate+[@[Est material]] | currency
| Actual cost | Actual hours x costing rate + actual material. | currency
| Cost variance | Actual cost - estimated cost, for shipped jobs. Positive means the job cost more than estimated. | currency
| Hours, rate and material variance | (Actual - est hours) x estimating rate; (costing - estimating rate) x actual hours; actual - est material. They add up to the cost variance. | currency
| Margin | (Order value - actual cost) / order value, for shipped jobs; over several jobs, from the sums. | %
| Hours used | Actual hours / estimated hours; on the Dashboard, actual / estimated hours of shipped jobs - 1. | %
| Days late | Ship date (status date while open) - due date, if positive. | days
| Lead time | Ship date - release date, in calendar days. | days
| Status | Complete when shipped; Overdue when open past its due date; Due soon when due within the window on Setup; otherwise In progress. | -
| On-time delivery | Shipped jobs with ship date on or before the due date / shipped jobs, inside the Dashboard filters. | %
| Open order value | Order value of jobs not yet shipped, inside the customer filter. | currency
| Weekly, by stage and by customer | The same sums by ship week (Monday start), by the stage of open jobs, and by customer. | -
Assumptions
| • | One row per work order shipped complete; for a partial shipment, split the order into two rows with their own quantities and hours.
| • | Actual hours are all hours booked to the job (setup and run, every operation), costed at one shop-wide costing rate.
| • | Outside processing and bought-in parts are included in material, estimated and actual.
| • | Due date is the date promised to the customer; a job shipped on its due date is on time.
Limitations
| • | Open jobs show cost to date, so their variance and margin stay blank until they ship.
| • | One costing rate for all work centres: a job heavy on an expensive machine will look cheaper than it is. Use machine rates per operation for that.
| • | The Dashboard has fixed blocks for six customers, eight stages and eight weeks; longer lists need the blocks extended (a warning appears on the Dashboard).
| • | The Verify sheet tests the formulas as built; it cannot see later edits to them.
Agreement with the live calculator
For one shipped job, this workbook and the live Job Costing Variance calculator compute the same numbers: estimated and actual job cost, hours variance = (actual - estimated hours) x estimated rate, rate variance = (actual - estimated rate) x actual hours, material variance and their total. The calculator takes the two rates per job; this workbook uses the estimating and costing rates on Setup for every job. The reference implementation is checked against the calculator's engine for the calculator's own example (42 h estimated, 48.5 h actual, 95 and 98 per hour, material 1,850 and 2,010: total variance 923.00).
Open the Job Costing Variance Calculator
Self-check
The Verify sheet holds fixed test inputs. Its formulas are the same formula text as the working sheets, placed against those inputs, and each result is compared with a value computed independently by the template's Python reference implementation when the file was built. If you edit a formula on a working sheet, the Verify sheet still tests the original formula text, so it will not detect your change.
Sources and standards
| • | APICS (ASCM) Dictionary, 16th edition: on-time delivery, lead time and job costing terms.
| • | Horngren, C. T., Datar, S. M., Rajan, M. V., Cost Accounting: A Managerial Emphasis, Pearson (job costing and the split of a cost variance into efficiency, price and material parts).
| • | MFG Calcs Job Costing Variance calculator (job-costing-variance): the same split for one closed job.
Standards are cited by name so you can look them up; no copyrighted standard text or tables are reproduced. Statistical constants used are public.
Version history
| Version | Change | Date
| 1.0.0 | First release. | 15 October 2026
Engineering estimates for planning and improvement work. Verify the results against your own process, data and standards before you rely on them.

## Verify
Job Shop Work Order Tracker
| Self-check: the workbook's formulas recomputed on fixed inputs against an independent reference. | [23 empty] | mfgcalcs.com
| Self-check status |  | PASS |  | 19 of 19 checks pass
This sheet recomputes the workbook's own formulas on fixed test inputs and compares each result with a value computed independently by the template's Python reference implementation when the file was built. Every row should read PASS. The test inputs are fixed and do not change when you edit Setup or the working sheets.
Checks
| No. | Check |  |  |  | Expected (reference) | Workbook result | Difference | Tolerance | Result
| 1 | WO 1 (calculator example): estimated cost |  |  |  | 5840 | 5840 | 0 | 1e-09 | PASS
| 2 | WO 1 (calculator example): actual cost |  |  |  | 6763 | 6763 | 0 | 1e-09 | PASS
| 3 | WO 1 (calculator example): cost variance |  |  |  | 923 | 923 | 0 | 1e-09 | PASS
| 4 | WO 1: margin |  |  |  | 13.29% | 13.29% | 0 | 1e-09 | PASS
| 5 | WO 1: days late |  |  |  | 4 | 4 | 0 | 1e-09 | PASS
| 6 | WO 1: shipped late |  |  |  | No | No |  | exact | PASS
| 7 | WO 2: shipped on time |  |  |  | Yes | Yes |  | exact | PASS
| 8 | WO 2: lead time |  |  |  | 16 | 16 | 0 | 1e-09 | PASS
| 9 | WO 3: status overdue |  |  |  | Overdue | Overdue |  | exact | PASS
| 10 | WO 3: days late to the status date |  |  |  | 7 | 7 | 0 | 1e-09 | PASS
| 11 | WO 4: status due soon |  |  |  | Due soon | Due soon |  | exact | PASS
| 12 | WO 4: hours used |  |  |  | 50% | 50% | 0 | 1e-09 | PASS
| 13 | WO 5: status in progress |  |  |  | In progress | In progress |  | exact | PASS
| 14 | WO 6: Check names shipped before released |  |  |  | Shipped before released | Shipped before released |  | exact | PASS
| 15 | On-time delivery (Dashboard formula) |  |  |  | 66.67% | 66.67% | 0 | 1e-09 | PASS
| 16 | Overdue work orders (Dashboard formula) |  |  |  | 1 | 1 | 0 | 1e-09 | PASS
| 17 | Cost variance of shipped jobs (Dashboard formula) |  |  |  | 755 | 755 | 0 | 1e-09 | PASS
| 18 | Hours + rate + material variance = cost variance |  |  |  | 755 | 755 | 0 | 1e-06 | PASS
| 19 | Margin achieved (Dashboard formula) |  |  |  | 22.69% | 22.69% | 0 | 1e-09 | PASS
Fixed test inputs
White cells are fixed test inputs; blue cells are the workbook's formulas evaluated on them.
Parameters
| Filter: shipped from (0 = no limit) |  |  | 0
| Filter: shipped to (2958465 = no limit) |  |  | 2958465
Filter: customer (blank = all)
| Estimating shop rate |  |  | 95
| Costing shop rate |  |  | 98
| Status date |  |  | 2026-10-09
| Due soon window (days) |  |  | 5
| Margin target |  |  | 25%
Test table: Customers
| Customer | Contact | Notes
C1
C2
Test table: Orders
[9 empty] | USD | h | h | USD | USD | USD | USD | USD |  |  | days | days
| WO No. | Customer | Part no. | Qty | Released | Due | Shipped | Stage | Order value | Est hours | Actual hours | Est material | Actual material | Est cost | Actual cost | Cost variance | Margin | Hours used | Days late | Lead time | Status | On time | View ship | View open | Check
| T-1 | C1 | P | 10 | 2026-08-03 | 2026-08-21 | 2026-08-25 |  | 7800 | 42 | 48.5 | 1850 | 2010 | 5840 | 6763 | 923 | 13.29% | 115.5% | 4 | 22 | Complete | No | 2026-08-25 |  | OK
| T-2 | C2 | P | 10 | 2026-08-10 | 2026-08-28 | 2026-08-26 |  | 4200 | 24 | 21.5 | 600 | 590 | 2880 | 2697 | -183 | 35.79% | 89.58% | 0 | 16 | Complete | Yes | 2026-08-26 |  | OK
| T-3 | C1 | P | 10 | 2026-09-07 | 2026-10-02 |  | Inspection | 3100 | 18 | 19 | 400 | 400 | 2110 | 2262 |  |  | 105.6% | 7 |  | Overdue |  |  | 2026-09-07 | OK
| T-4 | C2 | P | 10 | 2026-09-21 | 2026-10-13 |  | Machining | 2500 | 12 | 6 | 300 | 300 | 1440 | 888 |  |  | 50% | 0 |  | Due soon |  |  | 2026-09-21 | OK
| T-5 | C2 | P | 10 | 2026-10-05 | 2026-10-30 |  | Material | 5600 | 30 | 0 | 900 | 0 | 3750 | 0 |  |  | 0% | 0 |  | In progress |  |  | 2026-10-05 | OK
| T-6 | C1 | P | 10 | 2026-09-14 | 2026-09-30 | 2026-09-11 |  | 1000 | 5 | 5 | 100 | 100 | 575 | 590 | 15 | 41% | 100% | 0 | -3 | Complete | Yes | 2026-09-11 |  | Shipped before released
Formulas:
View open = IF(tblVerifyOrders[[#This Row],[Released]]="","",IF(AND(tblVerifyOrders[[#This Row],[Shipped]]="",OR(E37="",tblVerifyOrders[[#This Row],[Customer]]=E37)),tblVerifyOrders[[#This Row],[Released]],""))